## Online Enrolment
TESTING ESTIMATION
Item No. | Page | Open items | Est. (hours) | Comments | Assigned | Status | Status Date
A |  | Preparation
1 |  | Setup testing machine | 1
2 |  | Write test case (Summary+Description+Steps) | 74
B |  | Execution
3 |  | OES (Online Enrolment System) | 55
- Login
- Online Enrolment System
4 |  | SRS (Student Record System) | 53
C |  | Closing
5 |  | Closing | 1 | Delivery, Backup machine, update delivery tracking, send test report.
|  | Total days | 23
Assumption: This estimation base on specifications: <ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx> <ITS-75-Online Enrolment- Login Workflow v0.2.pdf>