## Estimation
ESTIMATION for ONE BUILD LIFE CYCLE | [6 empty] | This estimation base on specifications:
- ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx
- ITS-75-Online Enrolment- Login Workflow v0.2.pdf
• Number of testing browsers | 1 | (Full Pass Testing, OES Testing only)
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 90.885 | 18.177 | 1.3633
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 181.77 | 36.354 | 2.7266
• Number of testing browsers | 2 | (Full Pass Testing, OES Testing only) |  |  | Suggested browers: | FF11/12, IE8/IE9
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 136.51 | 27.302 | 2.0476
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 273.02 | 54.604 | 4.0953
• Number of testing browsers | 3 | (Full Pass Testing, OES Testing only) |  |  | Suggested browers: | FF11/12, IE8/IE9
Chrome18
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 182.135 | 36.427 | 2.732
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 364.27 | 72.854 | 5.4641
ESTIMATION for TWO BUILD LIFE CYCLE
Note: Assumption that | 70% | of TC's passed on previous cycle
• Number of testing browsers | 1 | (Full Pass Testing, OES Testing only)
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 154.5045 | 30.9009 | 2.3176
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 309.009 | 61.8018 | 4.6351
• Number of testing browsers | 2 | (Full Pass Testing, OES Testing only) |  |  | Suggested browers: | FF11/12, IE8/IE9
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 232.067 | 46.4134 | 3.481
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 464.134 | 92.8268 | 6.962
• Number of testing browsers | 3 | (Full Pass Testing, OES Testing only) |  |  | Suggested browers: | FF11/12, IE8/IE9
Chrome18
# TCs must have: | 747
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 62.25 | 12.45 | 0.93375
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 309.6295 | 61.9259 | 4.6444
# TCs good to have: | 1494
| Start Date | End Date | # Working Date | Est. Working Hrs Need | 20% Buffer Time | Est. Resource Need
Test Case Development | 2012-07-09 | 2012-07-20 | 10 | 124.5 | 24.9 | 1.8675
Test Case Execution | 2012-07-23 | 2012-08-03 | 10 | 619.259 | 123.8518 | 9.2889

## Details
|  |  | Total number of TCs must have |  | 747 | tcs
|  |  | Time of completing writing |  | 62.25 | hours
|  |  | Time of completing execution |  | 90.885 | hours
|  |  | Total number of TCs good to have |  | 1494 | tcs
|  |  | Time of completing writing |  | 124.5 | hours
|  |  | Time of completing execution |  | 181.77 | hours
|  | Note: | Time of writing a test case in average |  | 5 | minutes
|  |  | Time of executing a test case in average |  | 6 | minutes
|  |  | Time of writing bug in average |  | 6 | minutes
Test Case Execution:
- All things are going well. There is no defect. Best Estimate = B
- Assumption that there are 20% cases will be failed. Normal Estimate = N
- Assumption that there are 50% cases will be failed. Worse Estimate = W
Time estimation of completing execution each test case = (B +(4*N)+ W)/6
|  |  | Minutes to execute a test case in average |  | 7.3 | minutes
Test Case Writing:
|  |  | - Assumption that a test requirement includes 3 TC's: | + Possitive Test case
+ Negative Test case
+ Combination Test case
- Number of TCs Must Have = Test Requirement * 1.5
- Number of TCs Good To Have = Test Requirement * 3
Areas | UI/Function | Main Functions | Details | Number of Test Requirements | Number of TCs Must Have |  |  | Number of TCs Good To Have
[5 empty] | Number of Test Case | Estimation (Mins) |  | Number of Test Case | Estimation (Mins)
[6 empty] | Write TCs | Execute TCs |  | Write TCs | Execute TCs
OES | UI |  | Graphic Issues | 24 | 36 | 180 | 262.8 | 72 | 360 | 525.6
Spelling/ Grammar Issues
How much interface is interactive with the end-user
| Functions | Login Function | Validate Data for Fields | 20 | 30 | 150 | 219 | 60 | 300 | 438
Login Function
|  | Enrolment | Course Suggestion | 60 | 90 | 450 | 657 | 180 | 900 | 1314
|  |  | Course Enrolment | 40 | 60 | 300 | 438 | 120 | 600 | 876
|  |  | Add Additional Course | 14 | 21 | 105 | 153.3 | 42 | 210 | 306.6
|  |  | Add AdditionalElectives | 10 | 15 | 75 | 109.5 | 30 | 150 | 219
|  |  | Save Enrolment | 20 | 30 | 150 | 219 | 60 | 300 | 438
|  |  | Program Elective Selection | 10 | 15 | 75 | 109.5 | 30 | 150 | 219
|  |  | General Elective Selection | 12 | 18 | 90 | 131.4 | 36 | 180 | 262.8
|  | E History |  | 12 | 18 | 90 | 131.4 | 36 | 180 | 262.8
|  | Program Map |  | 2 | 3 | 15 | 21.9 | 6 | 30 | 43.8
|  | Timeline |  | 6 | 9 | 45 | 65.7 | 18 | 90 | 131.4
|  | Help Center- FAQ |  | 20 | 30 | 150 | 219 | 60 | 300 | 438
Help Center- Video Turorial
Help Center- Search Result
SRS | UI |  | Graphic Issues | 44 | 66 | 330 | 481.8 | 132 | 660 | 963.6
Spelling/ Grammar Issues
How much interface is interactive with the end-user
| Functions | Overwrite max credits to studen | Default value of OverwriteMax Credits to Student | 8 | 12 | 60 | 87.6 | 24 | 120 | 175.2
Edit/Update
Affection of changes to EOS
|  | Single Course Enrolment List | Permission (Who can access to this function???) | 20 | 30 | 150 | 219 | 60 | 300 | 438
List program code of all programs in the list
Add a Program
Remove a Program
Edit a program
Affection of changes to EOS
|  | OES Admin Menu | Permission (Who can access to this function???) | 4 | 6 | 30 | 43.8 | 12 | 60 | 87.6
The number of tabs shown based on permission
|  | OES Admin- Timeline Mgt- New En OES Admin- Timeline Mgt-Re En | Are we provided the data for checking this? | 34 | 51 | 255 | 372.3 | 102 | 510 | 744.6
Permission (Who can access to this function???)
Displaying Fields (UI)
Validate Data for Fields (16 Fields)
Save/Cancel an Enrolment/Re-Enrolment
Affection of changes to EOS
|  | OES Admin- FAQ Mgt | Permission (Who can access to this function???) | 26 | 39 | 195 | 284.7 | 78 | 390 | 569.4
Add/Edit/Delete Category
Add/Edit/Delete Question/Answer
Affection of changes to EOS
|  | OES Admin-Upload Videos | Permission (Who can access to this function???) | 10 | 15 | 75 | 109.5 | 30 | 150 | 219
List all available videos by title, type and Location
Upload/Remove
Affection of changes to EOS
|  | Email Template - List | Email Template List | 30 | 45 | 225 | 328.5 | 90 | 450 | 657
|  | Email Template - Edit | Insert Tags
Add/Delete a template
Copy/Cut a Current Selected Text
Preview Email Word Wrap
Affection of changes to EOS
|  | View Appl Record (Modification) | Transfer Conditional | 4 | 6 | 30 | 43.8 | 12 | 60 | 87.6
Create New Enrolment
|  | Prepare Diploma Transfer | Validate Data for Fields (2 Fields) | 10 | 15 | 75 | 109.5 | 30 | 150 | 219
Prepare Diploma Transfer functions
Email template: Use New Enrolment Program Preparation email template.
|  | Prepare New Enrolment | Validate Data for Fields (2 Fields) | 16 | 24 | 120 | 175.2 | 48 | 240 | 350.4
Search function
New Enrolment List with Student Information
Student’s application record
Prepare New Enrolment Program functions
Email Template: Use New Enrolment Program Preparation email template.
|  | Prepare Re-Enrolment | Validate Data for Fields (1 Field) | 16 | 24 | 120 | 175.2 | 48 | 240 | 350.4
Search function
Re-Enrolment List with Student Information
Student’s application record
Prepare Re-Enrolment Program
Email Template: Use Re-Enrolment Program Preparation email template.
|  | Finalize Transfer | Transfer Result List | 16 | 24 | 120 | 175.2 | 48 | 240 | 350.4
Finalize Transfer function
Process Appls (Modification)
|  | Review Pre-Enrolment Transfer | Review Pre-Enrol Transfer list | 10 | 15 | 75 | 109.5 | 30 | 150 | 219
Student information
Finalize functions
Note on F28: Reference: + ITS-73-Online Enroment- UI- OES 1.2.xlsx
Note on F31: Author: Reference: + ITS-75-Online Enrolment- Login Workflow v0.2.pdf + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.1. Login, Page: 20
Note on F33: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.2. Enrolment Page: 20-33
Note on F40: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.4. Enrolment History Page: 33
Note on F41: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.3. View Program Map Page: 33
Note on F42: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.5. View Enrolment Timeline Page: 33-34
Note on F43: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.4.6. HelpCenter Page: 34-35
Note on F46: Author: Reference: + ITS-73-Online Enroment- UI- SRS 1.2.xlsx
Note on F49: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.1. OverwriteMax Credits to Student Page: 8
Note on F52: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.2. Single Course Enrolment List Page: 8-9
Note on F58: Author: Reference + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.4. OES Admin Page: 9
Note on F60: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.4.1. Enrolment Timeline Management Page: 9-11
Note on F66: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.4.2. FAQ Management Page: 11-12
Note on F70: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.4.3. Upload Videos Page: 13
Note on F74: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.4.4. Email Template Page: 14-16
Note on F80: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.5. View Application Record (Modification) Page: 16
Note on F82: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.6.1. Prepare Diploma Transfers Page: 17
Note on F85: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.6.2. Prepare New Enrolment Program Page: 17-18
Note on F91: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.6.3. Prepare Re-Enrolment Program Page: 18
Note on F97: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.7. Finalize Transfer Page: 18-19
Note on F100: Author: Reference: + ITS-Project 75- Online Enrolment-Business Rules v1.5- Vendor.docx Section: 3.3.8. Review Pre-Enrolment Transfer Page: 19-20