## Summary
SUMMARY
Duration | Resource Needed (excluded buffer time of Assumption) | Resource Needed (included buffer time for Assumption)
For 2 weeks | 8.7259 | 9.7259
For a month | 3.9663 | 4.4209

## Rough Estimation
Variables
7.5 | # of hours per day can be used for TC Development
3 | Full Test for Desktop Combinations
8 | Smoke Test for Desktop Combinations
4 | Full Test for Mobile Combinations
0 | Smoke Test for Mobile Combinations
61 | Total tentative test cases for Desktop combinations including High, Medium and Low complexity
67 | Total tentative test cases for Mobile combinations including High, Medium and Low complexity
55 | Total tentative actions including High, Medium and Low complexity
15 | Total tentative interfaces
TASK |  |  | Minutes/ Test Module FOR TESTER TA L3 |  |  | Expected Mins/ TM (P.E.R.T) | Standard Deviation
|  |  | Difficult | Medium | Easy
Test Case Implementation and Execution |  |  | 150 | 100 | 45 | 99.1667 | 17.5
Test Case Re-execution and Debugging on other combinations (Desktop) |  |  | 60 | 50 | 20 | 46.6667 | 6.6667
Test Case Re-execution and Debugging on other combinations (Mobile) |  |  | 70 | 60 | 30 | 56.6667 | 6.6667
Action Creation and Execution |  |  | 120 | 45 | 20 | 53.3333 | 16.6667
WBS Reference | Task level 1 | Task Level 2 | Task Level 3 | Unit | Number of items | Effort Spent/1 item (Minutes) | Total Effort (Minutes) | Total Effort (Hours) | Total Man Days
Test Preparation | Set up environment | Install OS | Win 7, Win 8, Win 10 | PC | 6 | 60 | 360 | 6 | 0.8
|  |  | Win7 | Browser | 3 | 5 | 15 | 0.3 | 0.04
|  |  | Win8 | Browser | 3 | 5 | 15 | 0.3 | 0.04
|  |  | Win10 | Browser | 3 | 5 | 15 | 0.3 | 0.04
|  |  | MAC OS X v10.9 Maverick | Browser | 1 | 5 | 5 | 0.1 | 0.02
|  |  | MAC OS X v 10.10 Yosemite | Browser | 1 | 5 | 5 | 0.1 | 0.02
|  |  | MAC OSX v 10.11 El Capitan | Browser | 1 | 5 | 5 | 0.1 | 0.02
[7 empty] | 420 | 7.2 | 0.98
|  | Install TA | Window PC | PC | 6 | 5 | 30 | 0.5 | 0.07
|  |  | MAC | MAC | 3 | 10 | 30 | 0.5 | 0.07
|  |  | Android devices | Real devices | 4 | 5 | 20 | 0.4 | 0.06
|  |  | iOS devices | Real devices | 3 | 60 | 180 | 3 | 0.4
[7 empty] | 260 | 4.4 | 0.6
[7 empty] | 680 | 11.6 | 1.58
Test Case Creation | Explore AUT | Explore Admin and User site on | Desktop | Item | 1 | 320 | 320 | 5.4 | 0.72
|  |  | Mobile | Item | 1 | 240 | 120 | 2 | 0.27
[7 empty] | 440 | 7.4 | 0.99
[7 empty] | 440 | 7.4 | 0.99
Automation Testing | TM Implementation | Prepare Test Design |  | Item | 1 | 320 | 320 | 5.4 | 0.8
|  | Capture interfaces |  | Interface | 15 | 10 | 150 | 2.5 | 0.4
|  | Implement actions and execute on 1 browser | Including High, Medium and Low Complexity | Action | 55 | 53.3333 | 2933.3333 | 48.9 | 6.6
|  | Implement test cases and execute on 1 browser |  | TM | 61 | 99.1667 | 6049.1667 | 100.9 | 13.5
|  | Re-Execute and Debug TMs implemented on desktop/Mac browsers left | 3 Full Test | TM | 183 | 46.6667 | 8540 | 142.4 | 19
|  |  | 8 Smoke Test | TM | 48.8 | 46.6667 | 2277.3333 | 38 | 5.1
|  | Re-Execute and Debug TMs implemented on real devices | 4 Full Test | TM | 268 | 56.6667 | 15186.6667 | 253.2 | 33.8
|  |  | 0 Smoke Test | TM | 0 | 56.6667 | 0 | 0 | 0
|  | Add more variant actions after executing and debugging on other combinations |  | Action | 8.25 | 53.3333 | 440 | 7.4 | 1
[7 empty] | 35896.5 | 598.7 | 80.2
TA Issue Verification | Submit TA issues |  |  | Issue | 5 | 30 | 150 | 2.5 | 0.4
| Submit and follow up concerns and questions |  |  | Concerns | 15 | 20 | 300 | 5 | 0.7
[7 empty] | 450 | 7.5 | 1.1
Test Report | Prepare DSR, WSR | DSR |  | DSR | 44 | 30 | 1320 | 22 | 3
|  | WSR |  | WSR | 8 | 60 | 480 | 8 | 1.1
[7 empty] | 1800 | 30 | 4.1
[7 empty] | 2250 | 37.5 | 5.2
[7 empty] | 39266.5 | 655.2 | 87.97
Total (Man Day) | [8 empty] | 87.2589
Note on G22: An Bui - 1262: IE11, Chrome, FF
Note on G23: An Bui - 1262: IE11, Chrome, FF
Note on G24: An Bui - 1262: IE11, Chrome, FF
Note on G25: An Bui - 1262: Safari 7
Note on G26: An Bui - 1262: Safari 8
Note on G27: An Bui - 1262: Safari 9
Note on D42: An Bui - 1262: Assuming 1 TC is 1 TM
Note on D47: An Bui - 1262: Assuming that 15% of total actions need to be added for other combinations
Note on C50: An Bui - 1262: Assuming there are about 15 concerns/questions about AUT, test case steps,…
Note on D52: An Bui - 1262: Assuming: 2 months = 44 working days
Note on D53: An Bui - 1262: Assuming: 2 months = 8 weeks

## Project Assumptions Log
Project Assumption
Always include a complete description of project assumptions that support the estimates. Assumptions are factors that, initially for project planning/estimation purposes, are assumed to be true or certain
E.g. '- All six resources work full time
'- AUT/"to be tested" features will be available as planned
'- Project scope will not be modified
Assumption Log
Project:
ID | Category | Assumption | Owner | Validated Date | Required Action | Buffer Time (hrs)
001_Assumption Log | … //Base on Project/Testing life cycle we should categorize the assumption list to understand the impact of it. | //Describe briefly the assumption that you think It will be affected to your estimation if it happes | Who will validate/take responsibility as it happens | //this field needs to be updated if during project runs we need to look back this assumtion again. | //List all actions you need to do when this assumption happens | //Add the buffer time for actions you need to do when this assumption happens.
001_Assumption Log | Application | Test Architect site always stay live | Client |  | We need client addresses issues we raise faster and sooner especially issues cause our automation failed…such as sites load too slow, web application is died | 8
002_Assumption Log | Application | Release notes are provided by client | Client |  | There should be release note or something like that for any changes they made to the AUTs. That would help us be aware ahead of time and have a suitable plan for updating our script. | 16
003_Assumption Log | Application | Providing the loading time of each feature | Client |  | We need client provides a document about the loading time of each feature. This will give us an idea as to how client expects the AUT responses to user's interactions. | 8
004_Assumption Log | Devices | Borrowing devices from other teams/clients | Logigear/Client |  | We borrow devices from other project teams. So usually run into the following issues + Conflict borrowing devices + Not able to borrow exact model/firmware + Not able to borrow full day + Plan is affected when the borrower wants to get devices back for their project use + Lender needs to upgrade firmware due to client's request >> affect to our plan + As we have to perform unattended executions day by day, it may cause damage to borrowing devices (battery, hardware, screen..). This is risky as most of devices are owned by other clients. So it would be better if client equip devices they need for the team | 24
005_Assumption Log | Test machines | Borrowing test machines from IT | IT |  | We need IT provide enough test machines or server machines enough strong | 24
|  |  | Total Buffer Time |  |  | 80

## Testing Combinations
Automation Testing
Desktop OS Combinations
| IE11 | Chrome (Latest version that TA already supported) | FireFox (Latest version that TA already supported) | Safari 7 | Safari 8 | Safari 9
Win 7 | Auto Full | Auto Full | Auto Full | OS Not Supported
Win 8 | Auto Smoke | Auto Smoke | Auto Smoke
Win 10 | Auto Smoke | Auto Smoke | Auto Smoke
MAC OS X v10.9 Maverick | OS Not Supported | TA Not Supported |  | Auto Smoke
MAC OS X v 10.10 Yosemite |  |  |  | OS Not Supported | Auto Smoke
MAC OSX v 10.11 El Capitan | [5 empty] | Auto Full
Mobile Browser Combinations
Real Devices
iPhone 6+ | Auto Full
iPad Mini 3 | Auto Full
LG G3 | Auto Full
Motorola Moto X | Auto Full
Note on F6: An Bui - 1262: http://appleinsider.com/articles/12/07/25/apple_kills_windows_pc_support_in_safari_60 http://www.forbes.com/sites/adriankingsleyhughes/2012/07/25/is-apples-safari-for-windows-dead
Note on D9: Hengky Kurniawan: TA Limitation