## Estimation
| Functional Areas | Quantity of TCs | Estimated TC Creation Time |  | Estimated TC Execution Time
|  |  | Average (Hours) | Total (hours) | Average (Hours) | Total (hours)
| 1. Login/ Logout funcion | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 2. Sign Up function | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 3. Edit Profile function | 4 | 0.26389 | 1.0556 | 0.29167 | 1.1667
| 4. Header Menu navigation | 5 | 0.26389 | 1.3194 | 0.29167 | 1.4583
| 5. Check all links on pages (~266 links in total) |  | 0.26389 | 0 | 0.033333 | 8.8667
| 6. Watch all video tutorials (~45 videos) |  | 0.26389 | 0 | 0.11667 | 5.25
| 5. Check images of articles/ posts | 8 | 0.26389 | 2.1111 | 0.29167 | 2.3333
| 6. Search function | 2 | 0.26389 | 0.52778 | 0.29167 | 0.58333
| 7. Open a New Support Ticket | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 8. Check Ticket Status | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 9. Start A New Topic | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 10. Leave a reply on an article/ post | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 11. Follow an article/ post | 3 | 0.26389 | 0.79167 | 0.29167 | 0.875
| 12. Footer Menu navigation | 5 | 0.26389 | 1.3194 | 0.29167 | 1.4583
| 13. Print article | 6 | 0.26389 | 1.5833 | 0.29167 | 1.75
| * Get acquainted with TA Support Forum * Design and Create test cases | * Execute test cases * Rerun blocked and failed test cases * Defect logging * Defect verification * Exploratory testing
| For "Test Creation" Phase | [5 empty] | Factor of safety
| Total test cases have to be created |  |  | 51 | tcs |  | Risks / Blockers | Impact (hours)
| Total time need to complete test cases creation |  |  | 13.4583 | hrs |  | 1. TC creation for Requirements being added/ updated
[A] | Total effort estimated for this Phase |  |  | 13.4583 | man hours |  | 2. Querries/ Doubts while executing TCs
|  |  |  | 1.6823 | man days |  | 3. Time spent for diagnosing defects' root causes
4. New defects coming more than rough estimate
| For "Test Execution" Phase | [5 empty] | 5. Lack of MAC machines for testing
| Total test cases have to be executed for Full Regression against Windows 7 64-bit/ Chrome |  |  | 51 | tcs
| Total test cases have to be executed for Full Regression against MAC OS 10.11/ Safari |  |  | 51 | tcs |  | Total Effort (hours) | 17.7785
| Total test cases have to be executed for Spot-Check against 6 OS/ Browser combinations left |  |  | 51 | tcs
| Total Blocked and Failed test cases have to be re-executed |  |  | 15.3 | tcs
| Total links have to be tested for Full Regression against Windows 7 64-bit/ Chrome |  |  | 266 | links
| Total links have to be tested for Spot-Check against 7 OS/ Browser combinations left |  |  | 266 | links
| Total videos have to be tested Full Regression against Windows 7 64-bit/ Chrome |  |  | 45 | videos
| Total videos have to be tested for Spot-Check against 7 OS/ Browser combinations left |  |  | 45 | videos
| Total defects (New) estimated |  |  | 150 | defects
| Total defects have to be verified |  |  | 150 | defects
| Total time need to complete test cases execution |  |  | 49.0875 | hrs
| Total time need to complete links testing |  |  | 17.7333 | hrs
| Total time need to complete video testing |  |  | 10.5 | hrs
| Total time need to complete defects logging |  |  | 31.25 | hrs
| Total time need to complete defects verification |  |  | 39.5833 | hrs
| Total time need to perform exploratory testing |  |  | 29.6308 | hrs
| Factor of safety (for Risks/ Blockers) |  |  | 17.7785 | hrs
[B] | Total effort estimated for this Phase |  |  | 195.5635 | man hours
|  |  |  | 24.4454 | man days
| Total effort estimated for TA Support Forum project = [A] + [B] |  |  | 209.0218 | man hours
|  |  |  | 26.1277 | man days
| Total resources need to complete TA Support Forum testing for a week |  |  | 5.2255 | resources
| Total resources need to complete TA Support Forum testing for 2 weeks |  |  | 2.6128 | resources
| Total resources need to complete TA Support Forum testing for 3 weeks |  |  | 1.7418 | resources
| Total resources need to complete TA Support Forum testing for 4 weeks |  |  | 1.3064 | resources
Assumptions
1) Estimation is based on defined scope and requirements of TA Support Forum at this time (25-Mar). If there is any update on scope, this estimation will have to be revisited.
2) Total time estimated for Phase "Test Execution" is calculated against on assumption that we can add ~10% of effort factor. Please see table "Factor of safety" above for more details.
3) Please refer to sheet "Baseline" for baseline of TC Creation, TC Execution, Defect Logging and Defect Verification
4) Total number of Blocked and Failed TCs is ~10% of total TCs have to be executed.
5) Exploratory testing time is calculated against on assumption that we can spend ~20% of total efforts (TCs execution, Defects logging and Defects verification) for Phase "Test Execution".
Note on C9: Duy Vu: Break down to 8 test cases for this item for test management purpose
Note on G9: Duy Vu: 2 mins per link
Note on C10: Duy Vu: Break down to 2 test cases for this item for test management purpose
Note on G10: Duy Vu: 7 mins per video

## Compatibility Matrix
OS/ Browser combinations
Functionality Testing | Chrome | IE 11 | Firefox | Safari | Edge
Windows 7/ 32-bit |  |  |  | Spot-check
Windows 7/ 64-bit | Full Regression
Windows 8.1/ (32 or 64-bit) |  |  | Spot-check
Windows 10/ 32-bit |  | Spot-check
Windows 10/ 64-bit |  |  |  |  | Spot-check
MAC OS 10.9 |  |  | Spot-check
MAC OS 10.10 | Spot-check
MAC OS 10.11 |  |  |  | Full Regression
Links/ Video Tutorials Testing | Chrome | IE 11 | Firefox | Safari | Edge
Windows 7/ 32-bit |  |  |  | Spot-check
Windows 7/ 64-bit | Full Regression
Windows 8.1/ (32 or 64-bit) |  |  | Spot-check
Windows 10/ 32-bit |  | Spot-check
Windows 10/ 64-bit |  |  |  |  | Spot-check
MAC OS 10.9 |  |  | Spot-check
MAC OS 10.10 | Spot-check
MAC OS 10.11 |  |  |  | Spot-check

## Baseline
TEST CASE CREATION - PERFORMANCE BASELINE
Resource Type | Minutes/ Test Case |  |  | Expected Mins/ TC (P.E.R.T) | Standard Deviation
| Difficult | Medium | Easy
Tester | 30 | 15 | 5 | 15.8333 | 4.1667
TEST CASE EXECUTION - PERFORMANCE BASELINE
Resource Type | Minutes/ Test Case |  |  | Expected Mins/ TC (P.E.R.T) | Standard Deviation
| Difficult | Medium | Easy
Tester | 40 | 15 | 5 | 17.5 | 5.8333
DEFECT LOGGING - PERFORMANCE BASELINE
Resource Type | Minutes/ Bug |  |  | Expected Mins/ Bug (P.E.R.T) | Standard Deviation
| Difficult | Medium | Easy
Tester | 30 | 10 | 5 | 12.5 | 4.1667
DEFECT VERIFICATION - PERFORMANCE BASELINE
Resource Type | Minutes/ Bug |  |  | Expected Mins/ Bug (P.E.R.T) | Standard Deviation
| Difficult | Medium | Easy
Tester | 30 | 15 | 5 | 15.8333 | 4.1667

## JIRA db (hidden)
iTRACS Corporation
Displaying 5076 issues at 23/Jul/15 12:37 AM.
Issue Type | Key | Summary | Target Release | Sub-Tasks | Assignee | Reporter | Component/s | Status | Created | Original Estimate | Time Spent | Remaining Estimate | Progress | Σ Original Estimate | Σ Time Spent | Σ Remaining Estimate | Σ Progress | Due Date | Linked Issues
Test Case | ICPIM-40556 | ICPIM-27274 Commission - Set Destination: Passing no EQID | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-22 03:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40555 | ICPIM-38540 Commission Within Wizard - Commissioning response | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-22 03:11 | 3600 | 1500 | 2100 | 41% | 3600 | 1500 | 2100 | 41%
Test Case | ICPIM-40554 | ICPIM-38540 Commission Within Wizard - Update Row/U position | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-22 03:08 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40553 | ICPIM-38540 Commission Within Wizard - Associate Assets to CR unsuccessfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-22 03:01 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-40552 | ICPIM-27477 CTMR_018 - Create MPO to fan out patching connection between two assets that are NOT mapped in CPIM - Violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:36 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40551 | ICPIM-40544 Commission Search dialog: Save View State per user | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-22 02:33 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-40550 | ICPIM-40544 Commission Search dialog: Make Toolbar visible by default | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-22 02:32 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-40549 | ICPIM-27477 CTMR_018 - Create MPO to fan out patching connection between two assets that are NOT mapped in CPIM - NOT violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:32 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40548 | ICPIM-40544 Cabinet Commission dialog: Save View State per user | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-22 02:32 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-40547 | ICPIM-40544 Cabinet Commission dialog: Make Toolbar visible by default | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-22 02:31 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-40546 | ICPIM-27477 CTMR_017 - Create MPO to fan out patching connection between two assets that are mapped in CPIM - Violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:30 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40545 | ICPIM-27477 CTMR_017 - Create MPO to fan out patching connection between two assets that are mapped in CPIM - NOT violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:29 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50%
Test Case | ICPIM-40543 | ICPIM-27477 CTMR_016 - Create MPO to MPO cabling connection between two assets that are NOT mapped in CPIM - Violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:25 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50%
Test Case | ICPIM-40542 | ICPIM-27477 CTMR_016 - Create MPO to MPO cabling connection between two assets that are NOT mapped in CPIM - NOT violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:23 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40541 | ICPIM-27477 CTMR_015 - Create MPO to MPO cabling connection between two assets that are mapped in CPIM - Violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:21 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40540 | ICPIM-27477 CTMR_015 - Create MPO to MPO cabling connection between two assets that are mapped in CPIM - NOT violate connection limits | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:19 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40539 | ICPIM-27477 INT_014 - Update the mapping of asset | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:10 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-40538 | ICPIM-27477 INT_010 - Create an asset and the asset has connectors that have already created and mapped in CPIM - Invalid SKU | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:07 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40537 | ICPIM-27477 INT_010 - Create an asset and the asset has connectors that have already created and mapped in CPIM - Valid SKU | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:04 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40536 | ICPIM-27477 INT_009 - Create a new asset - Conflict SKU | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-22 02:02 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50%
Test Case | ICPIM-40535 | ICPIM-27477 CTMR_012_Create a patching connection between iPatch Panel and a non iPatch Panel - Not mapped in CPIM - Over connection limit | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-22 01:56 | 2400 | 600 | 1800 | 25% | 2400 | 600 | 1800 | 25%
Test Case | ICPIM-40534 | ICPIM-27477 CTMR_011_Create a patching connection between an iPatch Panel and a non iPatch Panel - Mapped in CPIM - Over connection limit | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-22 01:47 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-40533 | ICPIM-40532 KPMG - Change order of Columns in Pre-Commission Search | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-22 01:23 | 5400 | 3600 | 1800 | 66% | 5400 | 3600 | 1800 | 66%
Test Case | ICPIM-40531 | ICPIM-27477 CTMR_004_Adding iPatch Panel to a Rack That Contains iPatch Panels – Invalid SKU - Not mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-22 00:59 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-40530 | ICPIM-27477 CTMR_004_Adding iPatch Panel to a Rack That Contains iPatch Panels – Valid SKU - Not mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-22 00:47 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-40529 | ICPIM-27477 CTMR_003 - Adding iPatch Panel to a Rack That Does Not Contain Any iPatch Panels – Valid SKU - Not mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-22 00:36 | 2400 | 600 | 1800 | 25% | 2400 | 600 | 1800 | 25%
Test Case | ICPIM-40528 | ICPIM-40511 Historical Data Export: Populate and export result for criterias: Enable both Start Time and End Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 23:44 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-40527 | ICPIM-40511 Historical Data Export: Populate and export result for criterias: Disable Start Time, emable End Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 23:43 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-40526 | ICPIM-40511 Historical Data Export: Populate and export result for criterias: Enable Start Time, disable End Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 23:42 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-40525 | ICPIM-40511 Historical Data Export: Populate and export result for criterias: Disable both Start Time and End Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 23:41 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-40524 | ICPIM-27477 CTMR_003 - Adding iPatch Panel to a Rack That Does Not Contain Any iPatch Panels – Invalid SKU, Not mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 23:33 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40523 | ICPIM-27477 CTMR_014_Remove a patching connection between an iPatch Panel and a non iPatch Panel - Not mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 21:06 | 2400 | 600 | 1800 | 25% | 2400 | 600 | 1800 | 25%
Test Case | ICPIM-40515 | ICPIM-40511 Historical Data Export: Set End Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 03:15 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75%
Test Case | ICPIM-40514 | ICPIM-40511 Historical Data Export: Set Start Time | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 03:15 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75%
Test Case | ICPIM-40513 | ICPIM-40511 Historical Data Export: Select Historical Datastore | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 03:14 | 2400 | 1860 | 1740 | 51% | 2400 | 1860 | 1740 | 51%
Test Case | ICPIM-40512 | ICPIM-40511 Historical Data Export: Set equipment | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 03:13 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-40510 | ICPIM-27477 CTMR_012_Create a patching connection between iPatch Panel and a non iPatch Panel - Not mapped in CPIM - Within connection limit | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 02:55 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40509 | ICPIM-27477 CTMR_023 - Update attributes of an/a Asset/Location - Assets are mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:38 | 3000 | 2400 | 600 | 80% | 3000 | 2400 | 600 | 80%
Test Case | ICPIM-40508 | ICPIM-27477 CTMR_011_Create a patching connection between an iPatch Panel and a non iPatch Panel - Mapped in CPIM - Within connection limit | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 02:35 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40507 | ICPIM-27477 INT_005 - Create connections - Have no existing connections - Connectors are mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:30 | 3000 | 2400 | 600 | 80% | 3000 | 2400 | 600 | 80%
Test Case | ICPIM-40506 | ICPIM-27477 INT_004 - Create connections - Have no existing connections - Connectors are NOT mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:29 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-40505 | ICPIM-27477 INT_003 - Create connections - Connectors in CPIM have connection rules that prohibit the connection - Connectors are NOT mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:27 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40504 | ICPIM-27477 INT_003 - Create connections - Connectors in CPIM have connection rules that prohibit the connection - Connectors are mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:25 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40503 | ICPIM-27477 CTMR_020 - Remove assets - Assets are NOT mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:23 | 3000 | 1200 | 1800 | 40% | 3000 | 1200 | 1800 | 40%
Test Case | ICPIM-40502 | ICPIM-27477 CTMR_019 - Remove assets - Assets are mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-21 02:15 | 3000 | 1800 | 1200 | 60% | 3000 | 1800 | 1200 | 60%
Test Case | ICPIM-40501 | ICPIM-40499 KPMG - Security rights for Commission Search Settings still exist | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 01:46 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-40500 | ICPIM-40499 KPMG - Commission Search Settings dialog still exists | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-21 01:45 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-40498 | ICPIM-36809 Simple View - Floor View: Add Plugin(s) | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-21 01:16 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40497 | ICPIM-27477 CTMR_010_Remove a cabling connection in imVision between one or more assets - Not Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 01:11 | 2400 | 600 | 1800 | 25% | 2400 | 600 | 1800 | 25%
Test Case | ICPIM-40496 | ICPIM-36809 Simple View - Floor View: Add Panel(s) | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-21 01:10 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40495 | ICPIM-27477 CTMR_009_Remove a cabling connection in imVision between 2 assets - Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 00:45 | 2400 | 600 | 1800 | 25% | 2400 | 600 | 1800 | 25%
Test Case | ICPIM-40494 | ICPIM-27477 CTMR_008_Create a cabling connection in imVision between one or more assets - Not Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 00:42 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40493 | ICPIM-39026 Simple View - GUI: Un-position | Bil (4.1.2) |  | An Vo | An Vo | Web Client | New | 2015-07-21 00:40 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-40492 | ICPIM-27477 CTMR_007_Create a cabling connection in imVision between 2 assets - Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 00:37 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40491 | ICPIM-40488 Library Item Catalog dialog loading time | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-21 00:17 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40490 | ICPIM-27477 CTMR_006_Removing iPatch Panel to a Rack where there are other iPatch Panels present. Panel removed was in the midle of the daisy chain - Not mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 00:15 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40489 | ICPIM-40488 Basic Search dialog loading time | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-21 00:10 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-40487 | ICPIM-27477 CTMR_006_Removing iPatch Panel to a Rack where there are other iPatch Panels present. Panel removed was in the midle of the daisy chain - Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-21 00:04 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40486 | ICPIM-39026 Simple View - GUI: Toolbar | Bil (4.1.2) |  | An Vo | An Vo | Web Client | New | 2015-07-20 23:57 | 3000 | 1800 | 1200 | 60% | 3000 | 1800 | 1200 | 60%
Test Case | ICPIM-40485 | ICPIM-27477 CTMR_005_Removing iPatch Panel to a Rack Where That Panel Was The Only Panel In The Rack - Not mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 23:56 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40484 | ICPIM-40479 This test case verify that references of iSight is removed from the Help file | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-20 23:31 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40483 | ICPIM-40479 Remove iSight from Menu, Toolbar, Security Right(s) and all configuration/management interfaces | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-20 23:30 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40482 | ICPIM-40479 Remove references of iSight from from Installer and all files/artifacts | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-20 23:27 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40481 | ICPIM-39716 Remove Classes from Panel Group: Cable Route, Cable Tray | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-20 23:22
Test Case | ICPIM-40480 | ICPIM-39026 Simple View - GUI: Info panel | Bil (4.1.2) |  | An Vo | An Vo | Web Client | New | 2015-07-20 23:16 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-40478 | ICPIM-39755 Import Default Connection Rules | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-20 21:33 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40477 | ICPIM-39755 Default Connection Rules | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-20 21:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40476 | ICPIM-38540 Commission Within Wizard - Commissioning GUI | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-20 21:27 | 3000 | 1800 | 1200 | 60% | 3000 | 1800 | 1200 | 60%
Test Case | ICPIM-40458 | ICPIM-39591 Commission - Configure Commission Power: GUI | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-20 04:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40457 | ICPIM-27477 CTMR_005_Removing iPatch Panel to a Rack Where That Panel Was The Only Panel In The Rack - Mapped in CPIM | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 03:40 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40456 | ICPIM-27477 CTMR_004_Adding iPatch Panel to a Rack That Contains iPatch Panels – Invalid SKU - Mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 03:35 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40455 | ICPIM-27477 INT_001 - Create connections - Have existing connections - Not violate connection limits - Connectors are NOT mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:32 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40454 | ICPIM-27477 INT_001 - Create connections - Have existing connections - Not violate connection limits - Connectors are mapped in CPIM | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:30 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40453 | ICPIM-27477 CTMR_004_Adding iPatch Panel to a Rack That Contains iPatch Panels – Valid SKU - Mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 03:29 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40452 | ICPIM-27477 INT_009 - Create a new asset - Invalid SKU - Parent asset is NOT mapped | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:29 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40451 | ICPIM-27477 INT_009 - Create a new asset - Invalid SKU - Parent asset is mapped | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40450 | ICPIM-27477 CTMR_003 - Adding iPatch Panel to a Rack That Does Not Contain Any iPatch Panels – Invalid SKU - Mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 03:26 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40449 | ICPIM-27477 INT_009 - Create a new asset - Invalid SKU - Asset is a Module | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40448 | ICPIM-27477 INT_009 - Create a new asset - Invalid SKU - Asset is an Enclosure | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:18 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40447 | ICPIM-27477 INT_008 - Create a new asset - Valid SKU - Parent asset is NOT mapped | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40446 | ICPIM-27477 CTMR_003 - Adding iPatch Panel to a Rack That Does Not Contain Any iPatch Panels – Valid SKU - Mapped parent asset | All |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-07-20 03:16 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-40445 | ICPIM-27477 INT_008 - Create a new asset - Valid SKU - Parent asset is mapped | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-07-20 03:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40444 | ICPIM-21195 Task Management - My Tasks: Associated with account | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-20 03:08 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-40414 | ICPIM-39603 SimpleViewWS - DeleteTileGrid request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40413 | ICPIM-39603 SimpleViewWS - CreateTileGrid request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:50 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40412 | ICPIM-39603 SimpleViewWS - EditTiles request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:48 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40411 | ICPIM-39603 SimpleViewWS - EditEnclosures request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40410 | ICPIM-39603 SimpleViewWS - EditRowPositions request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:26 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40409 | ICPIM-39603 SimpleViewWS - EditRows request | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:24 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40408 | ICPIM-39603 SimpleViewWS - Requests | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-17 03:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40407 | ICPIM-40404 Scheme - Data Collecton: Remove Collection Value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-17 00:12 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40406 | ICPIM-40404 Scheme - Data Collecton: Clone Collection Value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-17 00:06 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40405 | ICPIM-40404 Scheme - Data Collecton: Add Collection Value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-17 00:05 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40403 | ICPIM-39362 User is not associated with any LOB | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-16 22:07 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40363 | ICPIM-39336 Power Swing Simulator: Add/Remove Failover Items | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-16 03:16 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40362 | ICPIM-39336 Power Swing Simulator: Add/Remove Failure Items | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-16 03:12 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40361 | ICPIM-40359 DataExchangeWS - Create asset by className | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-16 03:03 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40360 | ICPIM-40359 DataExchangeWS - Create asset by non-SKU | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Service | New | 2015-07-16 03:01 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40358 | ICPIM-38811 Commission Search Logic: Convert Network to Analytics data - Copper Switch and Fiber Switch | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-07-16 02:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40357 | ICPIM-38811 Commission Search Logic: Convert Space to Analytics data: Pull Enclosure data - Level 10 | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-07-16 02:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40356 | ICPIM-40355 Windows client - Layout (Close all, Cascade, Tile Vertically, Tile horizontally, no windows) | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-16 01:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40354 | ICPIM-32535 Decommission - View Decommission Log (Content) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-16 00:21 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40353 | ICPIM-30822 Commission - View Commission Log (Content) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-15 19:49 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40333 | ICPIM-34148 Define Reports - Help |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-07-15 01:27
Test Case | ICPIM-40332 | ICPIM-28308 Asset Space - RMA Space | All |  | Thuy Tran | Thuy Tran | Analytics | New | 2015-07-15 01:24 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-40331 | ICPIM-30891 Commission - Change Destination for Commission Group | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-15 00:51 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40329 | ICPIM-23142 Web UI - Tooltips: The tooltip.js file | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-14 21:27 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40328 | ICPIM-40305 Web UI - Direct URL: Alert message | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-07-14 21:12 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40314 | ICPIM-28316 Export Asset Hierarchy - Asset Location | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-14 03:35 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40313 | ICPIM-28316 Export Asset Hierarchy - Asset Hierarchy | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-14 03:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40312 | ICPIM-28306 Export Power Data - Computation Logic for Asset contains Utility. | All |  | Thuy Tran | Thuy Tran | Application Layer | New | 2015-07-13 23:57 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-40311 | ICPIM-28306 Export Power Data - Power Source | All |  | Thuy Tran | Thuy Tran | Application Layer | New | 2015-07-13 21:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40295 | ICPIM-28306 Export Power Data - Computation Logic for Asset contains Power Strips/Panel Power Consumer | All |  | Thuy Tran | Thuy Tran | Analytics | New | 2015-07-13 02:46 |  | 6 | 2694 | 0% |  | 6 | 2694 | 0%
Test Case | ICPIM-40294 | ICPIM-30143 Manager window | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-13 02:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40293 | ICPIM-28306 Export Power Data - Power Consumers | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-13 02:12 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40292 | ICPIM-28305 Export Network - Auto deconnecting/ scheduled deconnecting fiber switch ports | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-13 00:31 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40291 | ICPIM-28305 Export Network - Auto connecting/ scheduled connecting fiber switch ports | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-13 00:28 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40290 | ICPIM-28305 Export Network - Auto deconnecting/ scheduled deconnecting copper switch ports | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-13 00:19 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40289 | ICPIM-31817 Report - Remove Categories that is NOT used by reports | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-13 00:17
Test Case | ICPIM-40288 | ICPIM-28305 Export Network - Auto connecting/ scheduled connecting copper switch ports | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-13 00:16 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40287 | ICPIM-28305 Export Network - Auto deconnecting/ scheduled deconnecting fiber pairs | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-12 23:46 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40286 | ICPIM-28305 Export Network - Auto connecting/ scheduled connecting fiber pairs | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-12 23:42 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40285 | ICPIM-28305 Export Network - Auto disconnecting/ scheduled disconnecting copper position | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-12 21:30 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40284 | ICPIM-28305 Export Network - Auto connecting/ scheduled connecting copper position | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-12 21:26 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-40262 | ICPIM-34091 Make sure that you are not able to change the table or class drop downs in standard default reports |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-07-10 03:45 | [9 empty] | ICPIM-34340
Test Case | ICPIM-40261 | ICPIM-34155 Generate Commision Power Balance Report | Magni |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-07-10 03:41 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-40260 | ICPIM-28301 Run Analytics - Export Asset | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-10 03:07 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40259 | ICPIM-40055 Commission Search: Voltages: Run Report without value entered for +- field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 03:00 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40258 | ICPIM-40055 Commission Search: Voltages: Run Report without value entered for Volts field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:59 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40257 | ICPIM-40055 Commission Search: Voltages: Run Report without any value entered for both Volts and +- field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40256 | ICPIM-40055 Commission Search: Voltages: Run Report within the range specified by the User | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40255 | ICPIM-40055 Commission Search: Voltages: Searching without value entered for +- field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40254 | ICPIM-40055 Commission Search: Voltages: Searching without value entered for Volts field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40253 | ICPIM-40055 Commission Search: Voltages: Searching without any value entered for both Volts and +- field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 02:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40252 | ICPIM-28317 Export Asset Inventory - Commission/ Decommission an asset | All |  | Khang Nguyen | Khang Nguyen | Application Layer | Fail | 2015-07-10 02:24 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-40092
Test Case | ICPIM-40251 | ICPIM-28317 Export Asset Inventory - Create/ Delete an asset | All |  | Khang Nguyen | Khang Nguyen | Analytics | Fail | 2015-07-10 02:06 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-40092
Test Case | ICPIM-40250 | ICPIM-40245 Report: Generate Report to Return Future Module Position | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 01:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40249 | ICPIM-40245 Report: Generate Report to Return Current Module Position | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 01:18 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40248 | ICPIM-40245 Report: Add Syscat to Return Current, Future Module Position | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 01:18 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40247 | ICPIM-40245 Add datastore to show the Future slot # for a module | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 00:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40246 | ICPIM-40245 Add datastore to show the Current slot # for a module | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-10 00:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40244 | ICPIM-28303 Export Asset Data - Financial Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-10 00:31 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40243 | ICPIM-28303 Export Asset Data - Asset Compute Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-10 00:03 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40242 | ICPIM-28303 Export Asset Data - Maintenance Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 21:49 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40241 | ICPIM-28303 Export Asset Data - Asset Dimension Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 21:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40240 | ICPIM-28303 Export Asset Data - Asset Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 21:32 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40239 | ICPIM-28302 Asset Cooling - Power Cooling Data | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 19:45 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40230 | ICPIM-23410 Single CR - Navigate to Single CR | All |  | An Vo | An Vo | Web Client | New | 2015-07-09 04:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-19678, ICPIM-19823
Test Case | ICPIM-40229 | ICPIM-22980 Change Request Details - Change list administrative privileges | All |  | An Vo | An Vo | Web Client | New | 2015-07-09 03:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40228 | ICPIM-22980 Change Request Details - View Inactive CRs | All |  | An Vo | An Vo | Web Client | New | 2015-07-09 03:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40227 | ICPIM-40109 ICPIM-38099: Specifying u position for space causes issues during commissioning | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:26 | [9 empty] | ICPIM-38099
Test Case | ICPIM-40226 | ICPIM-40109 ICPIM-39131: Script Error caused when opening the Technician dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:25 | [9 empty] | ICPIM-39131
Test Case | ICPIM-40225 | ICPIM-40109 ICPIM-21506: Users can modify the web browsers work orders and work actions within the Windows client | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:25 | [9 empty] | ICPIM-21506
Test Case | ICPIM-40224 | ICPIM-40109 ICPIM-32780: Remove Work Projects: The Work Project in Projects pane does not disappear after being deleted | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:25 | [9 empty] | ICPIM-32780
Test Case | ICPIM-40223 | ICPIM-40109 ICPIM-30090: Workflow - Commission Search - Results tab: When selecting "Search" tab at the bottom of "Commission Search" window, controls on search tab will be displayed although "Results" tab is selected | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:24 | [9 empty] | ICPIM-30090
Test Case | ICPIM-40222 | ICPIM-40109 ICPIM-30107: Search-Commission Search: Workflow-Commission Search: Wrong class items display in the Search Within drop-down | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:24 | [9 empty] | ICPIM-30107
Test Case | ICPIM-40221 | ICPIM-40109 ICPIM-36258: Workflow Commissioning fails when specifying an available “U” Position. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:24 | [9 empty] | ICPIM-36258
Test Case | ICPIM-40220 | ICPIM-40109 ICPIM-32666: Can not filter on Tech OK Actions in Workflow Manager dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:24 | [9 empty] | ICPIM-32666
Test Case | ICPIM-40219 | ICPIM-40109 ICPIM-9412: Workflow Technician "View" not shown with work action | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:23 | [9 empty] | ICPIM-9412
Test Case | ICPIM-40218 | ICPIM-40109 ICPIM-36306: Workflow Commissioning fails for Power. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:23 | [9 empty] | ICPIM-36306
Test Case | ICPIM-40217 | ICPIM-40109 ICPIM-20923: Workflow- The invalid status work projects still display Editable fields in the Manager dialog within the thick client. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:22 | [9 empty] | ICPIM-20923
Test Case | ICPIM-40216 | ICPIM-40109 ICPIM-36928: Placement option is not updated for Row Position while commission enclosure in Workflow mechanism | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:22 | [9 empty] | ICPIM-36928
Test Case | ICPIM-40215 | ICPIM-40109 ICPIM-32654: Can not select filter options in Workflow Manager dialog. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:22 | [9 empty] | ICPIM-32654
Test Case | ICPIM-40214 | ICPIM-40109 ICPIM-39674: Update Database Utility: Empty row position is associated to enclosure next left to it | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:21 | [9 empty] | ICPIM-39674
Test Case | ICPIM-40213 | ICPIM-39019 Delete Work action that has dependencies on it | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 03:19 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-40212 | ICPIM-39019 Cancel Work action that has dependencies on it | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 03:19 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-40211 | ICPIM-39019 This test case will verify that user is able to update destination for a work action that has dependencies on it. | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 03:18 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-40210 | ICPIM-40109 ICPIM-39681: User Management: 'Lock account', 'Force Password Change' checkboxes an "Login Type" field are enabled for 'administrator' user if no other user is selected before. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:17 | [9 empty] | ICPIM-39681
Test Case | ICPIM-40209 | ICPIM-39019 Update Work action that has dependencies on it | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 03:17 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-40208 | ICPIM-40109 ICPIM-39608: User Management: 'administrator' user login with no role if user logs into the CPIM using a user with no role then login using 'administrator' user | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:16 | [9 empty] | ICPIM-36908
Test Case | ICPIM-40207 | ICPIM-40109 ICPIM-27695: ANLC: Reserved Space Calculation Incorrect | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:16 | [9 empty] | ICPIM-27695
Test Case | ICPIM-40206 | ICPIM-40109 ICPIM-25945: "KVM Switch" is not part of the "Network Device" Class Group by Default setting. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:16 | [9 empty] | ICPIM-25945
Test Case | ICPIM-40205 | ICPIM-40109 ICPIM-27340: Reports: Regenerating Reports After Stopping Them Disconnects the Client | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:15 | [9 empty] | ICPIM-27340
Test Case | ICPIM-40204 | ICPIM-40109 ICPIM-30100: Administrative-Commission Search Settings: The "Fiber patching distance from enclosure" drop-down displays only the first digit when user selects a number greater than 10 (ft) | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:15 | [9 empty] | ICPIM-30100
Test Case | ICPIM-40203 | ICPIM-40109 ICPIM-30122: The saved search does not display in the "Saved Search" drop-down of "Commission Search" window when user sets User Access" of saved search is "<Global>" | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:15 | [9 empty] | ICPIM-30122
Test Case | ICPIM-40202 | ICPIM-28308 Asset Space - Shelf Target Density | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 03:14 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40201 | ICPIM-40109 ICPIM-30137: Administrative Commission Search Settings-Saved Search: The Refresh button does not work when user adds new saved search to the blank saved search list | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:13 | [9 empty] | ICPIM-30137
Test Case | ICPIM-40200 | ICPIM-40109 ICPIM-37163: Commission CR stays in ‘In-Progress’ status without completing - while installing a Blade server into Blade Enclosure | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:13 | [9 empty] | ICPIM-37163
Test Case | ICPIM-40199 | ICPIM-40109 ICPIM-36096: No warning message appears when adding a new preconfigured Commission Search event though it was already loaded. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:12 | [9 empty] | ICPIM-36096
Test Case | ICPIM-40198 | ICPIM-40109 ICPIM-32823: Commission Search Settings: Configuration: The calendar displays unexpectedly when clicking on the daily timer pull down | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:12 | [9 empty] | ICPIM-32823
Test Case | ICPIM-40197 | ICPIM-40109 ICPIM-32831: Commission Search Settings: Configuration: The daily timer control still displays when switching from Configuration to Saved Search tab | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:11 | [9 empty] | ICPIM-32831
Test Case | ICPIM-40196 | ICPIM-40109 ICPIM-34544: Commission Search: Viewer pane: The tile gird is colored black when searching by "Greater Than" a specified temperature | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:11 | [9 empty] | ICPIM-34544
Test Case | ICPIM-40195 | ICPIM-40109 ICPIM-27983: KPMG Script Errors seen when using the Pre-Commission dialog when Cabinet is not selected. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:11 | [9 empty] | ICPIM-27983
Test Case | ICPIM-40194 | ICPIM-40109 ICPIM-30090: Workflow - Commission Search - Results tab: When selecting "Search" tab at the bottom of "Commission Search" window, controls on search tab will be displayed although "Results" tab is selected | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:11 | [9 empty] | ICPIM-30090
Test Case | ICPIM-40193 | ICPIM-40109 ICPIM-26593: Server is removed from Cabinet after refresh when commissioning with Auto Complete | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:10 | [9 empty] | ICPIM-26593
Test Case | ICPIM-40192 | ICPIM-40109 ICPIM-36258: Workflow Commissioning fails when specifying an available “U” Position. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:10 | [9 empty] | ICPIM-36258
Test Case | ICPIM-40191 | ICPIM-40109 ICPIM-38300: itracs 4.0 Commission top to bottom not working for more then one RMA at a time | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:09 | [9 empty] | ICPIM-38300
Test Case | ICPIM-40190 | ICPIM-40109 ICPIM-35949: Unable to type correct values in Commission Search KVA dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:09 | [9 empty] | ICPIM-35949
Test Case | ICPIM-40189 | ICPIM-40109 ICPIM-37487: Commission result is failed when user installs a server into a cabinet | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:09 | [9 empty] | ICPIM-37487
Test Case | ICPIM-40188 | ICPIM-40109 ICPIM-22810: Derating on all power (continuous duty/80%) equipment for commissioning engine | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:09 | [9 empty] | ICPIM-22810
Test Case | ICPIM-40187 | ICPIM-40109 ICPIM-33292: The “Regenerate the Report” button on the “Commission Power Balance Editor” window is not functioning. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:08 | [9 empty] | ICPIM-33292
Test Case | ICPIM-40186 | ICPIM-40109 ICPIM-34538: Commission Search: Result tab: The cabinets do not display in the Viewer pane | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:08 | [9 empty] | ICPIM-34538
Test Case | ICPIM-40185 | ICPIM-40109 ICPIM-34460: User cannot re-configured an equipment on Commission Editor, Equipment tab | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:08 | [9 empty] | ICPIM-34460
Test Case | ICPIM-40184 | ICPIM-40109 ICPIM-30103: Search-Commission Search:Letters and special characters are allowed for the KVA field | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:08 | [9 empty] | ICPIM-30103
Test Case | ICPIM-40183 | ICPIM-40109 ICPIM-32171: "Cabinet Space on Row" calculation does not include Future Commission. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:07 | [9 empty] | ICPIM-32171
Test Case | ICPIM-40182 | ICPIM-40109 ICPIM-25090: Commissioning a patch panel into a cabinet places it in an occupied U position | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:07 | [9 empty] | ICPIM-25090
Test Case | ICPIM-40181 | ICPIM-40109 ICPIM-28272: Commission log status displays incorrect FAIL status even when successful | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:06 | [9 empty] | ICPIM-28272
Test Case | ICPIM-40180 | ICPIM-40109 ICPIM-32808: Commissioning a cabinet onto a row via the Viewer crashes CPIM | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:06 | [9 empty] | ICPIM-32808
Test Case | ICPIM-40179 | ICPIM-40109 ICPIM-28269: Incorrect parent name is displayed in the commission log vs item log for a commission move | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:05 | [9 empty] | ICPIM-28269
Test Case | ICPIM-40178 | ICPIM-40109 ICPIM-26902: Cabinet shows as Gray box in Pre-Commission dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:05 | [9 empty] | ICPIM-26902
Test Case | ICPIM-40177 | ICPIM-40109 ICPIM-37712: itracs 4.0 hotfix commission issue - Disney LV | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:05 | [9 empty] | ICPIM-37712
Test Case | ICPIM-40176 | ICPIM-40109 ICPIM-22738: Viewstate shortcut does not work on Pre-Commission dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:04 | [9 empty] | ICPIM-22738
Test Case | ICPIM-40175 | ICPIM-40109 ICPIM-34289: The Commission Status Report has a Typo in the Planner dialog. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:03 | [9 empty] | ICPIM-34289
Test Case | ICPIM-40174 | ICPIM-40109 ICPIM-35013: Duplicate work actions created for Power during commissioning . | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:03 | [9 empty] | ICPIM-35013
Test Case | ICPIM-40173 | ICPIM-28308 Asset Space - Cabinet Target Density | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 03:03 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40172 | ICPIM-40109 ICPIM-34283: Cannot commission Power to items such as Servers; Switches | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:03 | [9 empty] | ICPIM-34283
Test Case | ICPIM-40171 | ICPIM-40109 ICPIM-34717: The equipment name is changed automatically after commissioning. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:03 | [9 empty] | ICPIM-34717
Test Case | ICPIM-40170 | ICPIM-40109 ICPIM-34286: Network Commissioning not working and No work actions get created | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:02 | [9 empty] | ICPIM-34286
Test Case | ICPIM-40169 | ICPIM-40109 ICPIM-28265: Commission Log sort order is displayed reverse order | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:02 | [9 empty] | ICPIM-28265
Test Case | ICPIM-40168 | ICPIM-40109 ICPIM-38989: Unable to commission using Seeking Service | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:02 | [9 empty] | ICPIM-38989
Test Case | ICPIM-40167 | ICPIM-40109 ICPIM-34309: Space commission is not completed when commissioning a server to a cabinet with Network Services. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:02 | [9 empty] | ICPIM-34309
Test Case | ICPIM-40166 | ICPIM-40109 ICPIM-35679: Seeking Serivce Commission Failure | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:02 | [9 empty] | ICPIM-35679
Test Case | ICPIM-40165 | ICPIM-40109 ICPIM-38560: Unable to perform Commission Swap | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:00 | [9 empty] | ICPIM-38560
Test Case | ICPIM-40164 | ICPIM-40109 ICPIM-35677: Seeking Serivce Commission Failure | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 03:00 | [9 empty] | ICPIM-35677
Test Case | ICPIM-40163 | ICPIM-40109 ICPIM-24516: Commission Validate Power Circuit | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:59 | [9 empty] | ICPIM-24516
Test Case | ICPIM-40162 | ICPIM-40109 ICPIM-26678: CHMGT: Commissioning For Space Fails | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:59 | [9 empty] | ICPIM-26678
Test Case | ICPIM-40161 | ICPIM-40109 ICPIM-23833: Commission Editor randomly closes | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:58 | [9 empty] | ICPIM-23833
Test Case | ICPIM-40160 | ICPIM-40109 ICPIM-36306: Workflow Commissioning fails for Power. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:58 | [9 empty] | ICPIM-36306
Test Case | ICPIM-40159 | ICPIM-40109 ICPIM-26359: Commission Search - Temperature Criteria | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:58 | [9 empty] | ICPIM-26359
Test Case | ICPIM-40158 | ICPIM-28308 Asset Space - Shelf Density | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40157 | ICPIM-40109 ICPIM-22411: The Repurpose Commissioning fails. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:57 | [9 empty] | ICPIM-22411
Test Case | ICPIM-40156 | ICPIM-40109 ICPIM-30125: Admistrative-Commission Search Setting: The "time-selection tool" displays next to "Run Every" drop-down unexpectedly when user switches from "Saved Search" tab to "Configuration" tab | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:57 | [9 empty] | ICPIM-30125
Test Case | ICPIM-40155 | ICPIM-40109 ICPIM-33671: Commission Search Settings window - Configuration tab: Cannot turn off "Redundant named power source" and "Fiber patching distance from enclosure" options | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:57 | [9 empty] | ICPIM-33671
Test Case | ICPIM-40154 | ICPIM-40109 ICPIM-38441: Cannot run commissioning parts list report in 4.1, non-terminating thread is encountered. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:56 | [9 empty] | ICPIM-38441
Test Case | ICPIM-40153 | ICPIM-40109 ICPIM-33708: Commission Part List Report run against store CCM-OBS-01 does not return any data | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:55 | [9 empty] | ICPIM-33708
Test Case | ICPIM-40152 | ICPIM-40109 ICPIM-38250: Specifying a 2 U position and an Interior spacing of 1u while commissioning causes it to fail | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:55 | [9 empty] | ICPIM-38250
Test Case | ICPIM-40151 | ICPIM-28308 Asset Space - Cabinet Density | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40150 | ICPIM-40109 ICPIM-39698: Placement field during Commissioning by Row Position moves cursor to the beginning for every key input. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:54 | [9 empty] | ICPIM-39698
Test Case | ICPIM-40149 | ICPIM-40109 ICPIM-33653: Commission Search Settings: No confirmation displays to ask user while exiting with some changes made on Configuration tab | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:54 | [9 empty] | ICPIM-33653
Test Case | ICPIM-40148 | ICPIM-40109 ICPIM-32971: Commission Editor window - Equipment tab: The value of Quantity drop-down also affects the Clone Item button | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:54 | [9 empty] | ICPIM-32971
Test Case | ICPIM-40147 | ICPIM-40109 ICPIM-34390: B - The Auto Complete does not work when commissioning and replicating Enclosure-type item to various destinations | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:53 | [9 empty] | ICPIM-34390
Test Case | ICPIM-40146 | ICPIM-40109 ICPIM-38322: Script Error seen while attempting to do a Commission Move of a module within a blade enclosure | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:53 | [9 empty] | ICPIM-38322
Test Case | ICPIM-40145 | ICPIM-40109 ICPIM-30093: Administrative-Commission Search Settings:The changes were not saved when user clicks "Yes" to confirm saving | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:53 | [9 empty] | ICPIM-30093
Test Case | ICPIM-40144 | ICPIM-40109 ICPIM-34449: User can view the filtered Commission list by clicking the "Refresh" button instead of the "Apply Filter" button | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:52 | [9 empty] | ICPIM-34449
Test Case | ICPIM-40143 | ICPIM-40109 ICPIM-34535: The Commission Search help page needs to update the Temperature criteria | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:52 | [9 empty] | ICPIM-34535
Test Case | ICPIM-40142 | ICPIM-40109 ICPIM-39482: Specifying u position for space 'top to bottom' fails the commissioning job | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:52 | [9 empty] | ICPIM-39482
Test Case | ICPIM-40141 | ICPIM-28308 Asset Space - shelf_positions_stranded- {Place Holder} | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:52 | 300 |  | 300 | 0% | 300 |  | 300 | 0%
Test Case | ICPIM-40140 | ICPIM-40109 ICPIM-38099: Specifying u position for space causes issues during commissioning | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:52 | [9 empty] | ICPIM-38099
Test Case | ICPIM-40139 | ICPIM-40109 ICPIM-22231: Commissioning cards into a server places them into already occupied card slots. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:51 | [9 empty] | ICPIM-22231
Test Case | ICPIM-40138 | ICPIM-40109 ICPIM-36928: Placement option is not updated for Row Position while commission enclosure in Workflow mechanism | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:51 | [9 empty] | ICPIM-36928
Test Case | ICPIM-40137 | ICPIM-40109 ICPIM-38651: The cabinet is not positioned when commissioning a new cabinet library item to a row. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:50 | [9 empty] | ICPIM-38651
Test Case | ICPIM-40136 | ICPIM-28308 Asset Space - cabinet_positions_stranded - {Place Holder} | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:50 | 300 |  | 300 | 0% | 300 |  | 300 | 0%
Test Case | ICPIM-40135 | ICPIM-40109 ICPIM-36418: Cabinet commission fails for space on a row where there is available space. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:50 | [9 empty] | ICPIM-36418
Test Case | ICPIM-40134 | ICPIM-40109 ICPIM-36309: In Place commissioning for Network fails when seeking service in different cabinet. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:50 | [9 empty] | ICPIM-36309
Test Case | ICPIM-40133 | ICPIM-40109 ICPIM-25596: Commission Parts List report does not return any results | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:49 | [9 empty] | ICPIM-25596
Test Case | ICPIM-40132 | ICPIM-40109 ICPIM-30107: Search-Commission Search: Workflow-Commission Search: Wrong class items display in the Search Within drop-down | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:48 | [9 empty] | ICPIM-30107
Test Case | ICPIM-40131 | ICPIM-40109 ICPIM-38225: During equipment commission specifying an edge spacing along with U- position fails the commission job. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:48 | [9 empty] | ICPIM-38225
Test Case | ICPIM-40130 | ICPIM-40109 ICPIM-33016: Commission Within: Commissioning a "Fuel Cell Rack" rack within a Rack results 2 panels that stick to the selected Rack | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:48 | [9 empty] | ICPIM-33016
Test Case | ICPIM-40129 | ICPIM-28308 Run Analytics Space for PDU Panel Board - Auto completed decomission/ schedule decommission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:47 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40128 | ICPIM-40109 ICPIM-31702: Commission Swap: the Equipment tab of the Commission Editor window only displays the current selected item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:47 | [9 empty] | ICPIM-31702
Test Case | ICPIM-40127 | ICPIM-40109 ICPIM-38142: Commissioning a cabinet to a Row position places it on the wrong position | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:47 | [9 empty] | ICPIM-38142
Test Case | ICPIM-40126 | ICPIM-40109 ICPIM-33079: Commission Search: The Line of Business information fails to display on the Commission Search Report window | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:47 | [9 empty] | ICPIM-33079
Test Case | ICPIM-40125 | ICPIM-40109 ICPIM-32876: Commission Within: The Error 10054 message occurs while commissioning a Cabinet within a Row | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:46 | [9 empty] | ICPIM-32876
Test Case | ICPIM-40124 | ICPIM-40109 ICPIM-37747: Port does not display as connected after Commissioning for power. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:45 | [9 empty] | ICPIM-37747
Test Case | ICPIM-40123 | ICPIM-40109 ICPIM-32845: Add Commission: User can create a commission group that has the Start Date is later than the Finish Date | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:45 | [9 empty] | ICPIM-32845
Test Case | ICPIM-40122 | ICPIM-40109 ICPIM-37917: Commission Move a module successfully but no work actions generated | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:45 | [9 empty] | ICPIM-37917
Test Case | ICPIM-40121 | ICPIM-40109 ICPIM-38231: Commission Move of a module within a blade enclosure is not possible | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:44 | [9 empty] | ICPIM-38231
Test Case | ICPIM-40120 | ICPIM-28308 Run Analytics Space for PDU Panel Board - Auto completed comission/ schedule commission | All |  | Khang Nguyen | Khang Nguyen | Analytics | Fail | 2015-07-09 02:44 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-40060
Test Case | ICPIM-40119 | ICPIM-40109 ICPIM-34943: KPMG - Pre-commission search is crashing the server. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:44 | [9 empty] | ICPIM-34943
Test Case | ICPIM-40118 | ICPIM-40109 ICPIM-25663: Validate Power Circuit fails during commissioning | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:43 | [9 empty] | ICPIM-25663
Test Case | ICPIM-40117 | ICPIM-40109 ICPIM-34541: Need to add the Temperature into the Commission Search Report result | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:43 | [9 empty] | ICPIM-34541
Test Case | ICPIM-40116 | ICPIM-28308 Run Analytics Space for Blade Enclosure- Auto completed decomission/ schedule decommission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:37 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40115 | ICPIM-28308 Run Analytics Space for Blade Enclosure- Auto completed comission/ schedule commission | All |  | Khang Nguyen | Khang Nguyen | Analytics | Fail | 2015-07-09 02:32 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-40060
Test Case | ICPIM-40114 | ICPIM-28308 Run Analaytics Space for Switch - Auto completed decommission/ schedule decommission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40113 | ICPIM-40109 ICPIM-38228: Commission log has incorrect spellings | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:22 | [9 empty] | ICPIM-38228
Test Case | ICPIM-40112 | ICPIM-28308 Run Analytics Space for Switch - Auto completed comission/ schedule commission | All |  | Khang Nguyen | Khang Nguyen | Analytics | Fail | 2015-07-09 02:20 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-40060
Test Case | ICPIM-40111 | ICPIM-28308 Run Analaytics Space for Cabinet - Auto completed decommission/ schedule decommission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:17 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40110 | ICPIM-40109 ICPIM-38330: Failed Power commissioning for Blade Chassis. | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 02:16 | [9 empty] | ICPIM-38330
Test Case | ICPIM-40108 | ICPIM-28308 Run Analaytics Space for Cabinet - Auto completed commission/ schedule commission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:11 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40107 | ICPIM-28308 Run Analytics Space for Row - Auto completed decomission/ schedule decommission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:08 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40106 | ICPIM-28308 Run Analytics Space for Row- Auto completed comission/ schedule commission | All |  | Khang Nguyen | Khang Nguyen | Analytics | New | 2015-07-09 02:05 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40105 | ICPIM-38733 CAD Drawing Manager - Unlink CAD file from CPIM item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 01:37
Test Case | ICPIM-40104 | ICPIM-38733 CAD Drawing Manager - Link CAD file to CPIM item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 01:22
Test Case | ICPIM-40103 | ICPIM-38733 CAD Drawing Manager - Open CAD file | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 01:13
Test Case | ICPIM-40102 | ICPIM-39310 iTRACS Pasted Item Layer - Zoom effect on select multiple pasted items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-09 00:50 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40101 | ICPIM-40024 Task Management - Resolve Work Action - Interact with detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-09 00:06 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40100 | ICPIM-40072 Report: "Get Seed" Syscat Report: Current selection does NOT matches Seed Target: Search return NO item within Current Selection | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 00:05 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40099 | ICPIM-40072 Report: "Get Seed" Syscat Report: Current selection does NOT matches Seed Target: Search returns item within Current Selection | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 00:05 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40098 | ICPIM-40072 Report: "Get Seed" Syscat Report: Current selection matches Seed Target | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-09 00:04 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40097 | ICPIM-38693 CAD Drawing Editor: permission to enter Edit mode | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-08 23:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40096 | ICPIM-38693 CAD Drawing Editor: permission to access viewer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-08 23:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40095 | ICPIM-36440 Report Wizard - Progress Bar | Ran (4.1) |  | An Vo | An Vo | Web Client | New | 2015-07-08 23:19 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40086 | ICPIM-40081 Query subClassName | Tyr (4.2) |  | An Vo | An Vo | Web Service | New | 2015-07-08 00:57 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40085 | ICPIM-40081 Query subClassId | Tyr (4.2) |  | An Vo | An Vo | Web Service | New | 2015-07-08 00:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40084 | ICPIM-40081 Query both ancestors' and children's sub-class | Tyr (4.2) |  | An Vo | An Vo | Web Service | New | 2015-07-08 00:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40083 | ICPIM-40081 Query children's sub-class | Tyr (4.2) |  | An Vo | An Vo | Web Service | New | 2015-07-08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40082 | ICPIM-40081 Query ancestors' sub-class | Tyr (4.2) |  | An Vo | An Vo | Web Service | New | 2015-07-07 23:50 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40074 | ICPIM-40072 Report: Configure Report: Add "Get Seed" Syscat: By Class Group | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-07 04:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40073 | ICPIM-40072 Report: Configure Report: Add "Get Seed" Syscat: By Class | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-07 04:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40071 | ICPIM-40070 Report - Commission Work Action Search syscat | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-07 04:06
Test Case | ICPIM-40069 | ICPIM-40064 Removing from Help content | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen |  | New | 2015-07-07 03:41
Test Case | ICPIM-40068 | ICPIM-40064 Removing from the Security Rights | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen |  | New | 2015-07-07 03:34 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40067 | ICPIM-40064 Removing from Agent Installer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen |  | New | 2015-07-07 03:32 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40066 | ICPIM-40064 Removing from Library Management dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen |  | New | 2015-07-07 03:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40065 | ICPIM-40064 Removing from Install package | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen |  | New | 2015-07-07 03:22 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40063 | ICPIM-28473 Permission check to access Change User Password dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-07 02:33 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40059 | ICPIM-40055 Commission Search: Voltages: Searching within the range specified by the User | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-07 01:47 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40058 | ICPIM-40055 Commission Search: Voltages: Range + or - a value: Enter an invalid value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-07-07 01:46 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-40057 | ICPIM-40055 Commission Search: Voltages: Range + or - a value: Enter a single numeric value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-07-07 01:46 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-40056 | ICPIM-40055 Commission Search: Voltages: Volts field | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-07-07 01:45 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-40054 | ICPIM-23025 Task - Verify CR - Verify CR Passed Flow | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 23:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40053 | ICPIM-23025 Tasks - Verify CR - Verify CR after associating assets | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 21:31 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40044 | ICPIM-20040 View Work Action - View My Change Requests | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 04:01 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-40043 | ICPIM-20040 View Work Action - View All Tasks | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 03:58 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-40042 | ICPIM-20040 View Work Action - Add Comments | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 03:27 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-40041 | ICPIM-20040 View Work Action - Source/Target Location | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 02:56 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40040 | ICPIM-20040 View Work Action - Visual Work Action | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 02:29 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40039 | ICPIM-31803 Report - Report Result: Export to CSV file | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40038 | ICPIM-31803 Report - Report Result: Export to Excel file | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40037 | ICPIM-31803 Report - Report Result: Regenerate the report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:20 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40036 | ICPIM-31803 Report - Report Result: Refresh the Report View | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:20 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40035 | ICPIM-31803 Report - Report Result: Refresh the Report View | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:19 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40034 | ICPIM-31803 Report - Report Result: Stop the current operation | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:18 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40033 | ICPIM-31803 Report - Report Result: Email Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:17 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40032 | ICPIM-31803 Report - Report Result: Print the report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:17 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40031 | ICPIM-31803 Report - Report Result: Save the Report to HTML file | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:16 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40030 | ICPIM-20040 View Work Action - View Status Changes and Comments | All |  | An Vo | An Vo | Web Client | New | 2015-07-06 02:15 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-40029 | ICPIM-31803 Report - Report Result | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-06 02:14 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40028 | ICPIM-40027 Report - Patch Panel Connectivity (Short Circuit) | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-05 21:00 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40025 | ICPIM-40023 Reexecute Reports - Scheduled Report | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-07-03 02:25 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40022 | ICPIM-39019 Stacked Commission - Windows- Commission Panel into position of an enclosure that is scheduled to be commissioned | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-03 00:48 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-40021 | ICPIM-40019 Removed 'Power Strip Connectivity (By X)' reports | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 23:32 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40020 | ICPIM-40019 Reports - Power Reports - Device Connectivity (Short Circuit) | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 23:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40018 | ICPIM-40016 Reports: Remove Repository Reports | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 21:20 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-40017 | ICPIM-40015 Reports - Connection Rules Configurations Report | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 21:18
Test Case | ICPIM-40014 | ICPIM-40013 Remove Switch Connectivity (By Location) legacy report from CPIM | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 20:40 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-40000 | ICPIM-39996 Contiguous Space Report: Run on Enclosure level | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 02:51 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39999 | ICPIM-39996 Contiguous Space Report: Run on Row level | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 02:50 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39998 | ICPIM-39996 Contiguous Space Report: Run on Location level | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 02:49 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39997 | ICPIM-39996 Contiguous Space Report: Condense three reports into one | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 02:48 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39995 | ICPIM-39310 iTRACS Pasted Item Layer - Reposition and Move pasted item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 02:41 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39994 | ICPIM-39310 iTRACS Pasted Item Layer - Remove item via Pasted items list | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 01:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39993 | ICPIM-39990 Stacked Commissions - Update Position and Occupied Space: Commission into space that is currently occupied but has scheduled to remove | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 01:47 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39992 | ICPIM-39990 Stacked Commissions - Update Position and Occupied Space: Commission into space that is currently empty but has scheduled to be occupied by another commission | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 01:47 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39991 | ICPIM-39990 Stacked Commissions - Update Position and Occupied Space: Commission into space that is available for current commission | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-07-02 01:46 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39989 | ICPIM-39310 iTRACS Pasted Item Layer - Add multiple instances of a pasted item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 01:35 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39988 | ICPIM-39310 iTRACS Pasted Item Layer - Add Multiple 'Pasted' Items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 01:29 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39987 | ICPIM-39310 iTRACS Pasted Item Layer - Add Single 'Pasted' Item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-07-02 01:23 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39976 | ICPIM-34900 Report - Commission Work Action Search report |  |  | An Vo | An Vo | Web Client | New | 2015-07-01 02:52 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39975 | ICPIM-27030 Run As Job - Beta Power v2 | Bil (4.1.2) |  | Khang Nguyen | Khang Nguyen | Application Layer | New | 2015-07-01 02:39 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39974 | ICPIM-27030 Run Now - Beta Power v2 | Bil (4.1.2) |  | Khang Nguyen | Khang Nguyen | Application Layer | New | 2015-07-01 02:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39973 | ICPIM-37261 Portfolio - Chart Viewer - Toggle Chart/Data | Ran (4.1) |  | An Vo | An Vo | Web Client | New | 2015-07-01 01:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39972 | ICPIM-39366 Simple View - Overlays: Update config file to hide/show Overlays | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-06-30 23:36 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39971 | ICPIM-39365 Simple View - Filters - Update config file to hide/show Filters | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-30 23:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39970 | ICPIM-39017 Simple View - Viewstates - Update config file to hide/show Viewstates | Bil (4.1.2) |  | An Vo | An Vo | Web Client | New | 2015-06-30 23:19 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39918 | ICPIM-36919 Simple View - Cabinet View: Panel snapping while moving | Tyr (4.2) |  | Tien Pham | An Vo | Windows Client | New | 2015-06-30 03:34 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39917 | ICPIM-36919 Simple View - Cabinet View: Panel placement validation | Tyr (4.2) |  | Tien Pham | An Vo | Windows Client | New | 2015-06-30 03:32 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39916 | ICPIM-30084 3DViewer - Interactive Visualization - Option tab: Apply load options | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-30 02:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39915 | ICPIM-16022 Portfolio - Viewer - Selection of pasted items | All |  | An Vo | An Vo | Web Client | New | 2015-06-30 01:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39914 | ICPIM-29073 Remove Log View | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-30 01:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39913 | ICPIM-29073 Clone Log View | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-30 01:19 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39912 | ICPIM-29073 Configure Log View via Settings tab | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-30 01:17 | 3000 |  | 3000 | 0% | 3000 |  | 3000 | 0%
Test Case | ICPIM-39911 | ICPIM-28896 Log - Search log | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-30 00:16 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39910 | ICPIM-35841 Dynamic Trending - Historical View - Sharing Options | All |  | An Vo | An Vo | Web Client | New | 2015-06-29 21:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39909 | ICPIM-35841 Dynamic Trending - Dynamic View - Sharing Options | All |  | An Vo | An Vo | Web Client | New | 2015-06-29 21:00 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39898 | ICPIM-22989 New Change Request - Submit CR Flow | All |  | An Vo | An Vo | Web Client | New | 2015-06-29 03:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39897 | ICPIM-13471 Uninstalling for: CPIM-ITRACS and SQL on a new drive other than the C drive | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-28 20:14 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-39896 | ICPIM-13471 Uninstalling for: CPIM-iTRACS on C drive and SQL on a different drive other than C | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-28 20:14 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-39895 | ICPIM-13471 Install CPIM-iTRACS on C drive and specify a different drive other than C to install SQL | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-28 20:00 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-39891 | ICPIM-35491 User modifies the capacity percentages for available and/or reserved-1 | All |  | An Vo | Loan Ha | Web Client | New | 2015-06-26 14:18
Test Case | ICPIM-39835 | ICPIM-30248 CSV Import Datastore "Full Update" | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-26 00:23 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39834 | ICPIM-28876 Export a Big Library Item (Datacenter, Building...) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2015-06-25 23:13 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0% |  | ICPIM-39828
Test Case | ICPIM-39786 | ICPIM-27431 Portfolio - Dashboard Viewer: Send email | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:47 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39785 | ICPIM-27431 Portfolio - Dashboard Viewer: Download as PDF | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:45 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39784 | ICPIM-27431 Portfolio - Dashboard Viewer: Download as PNG | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:43 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39783 | ICPIM-30248 CSV Import to Remount Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-25 03:38 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39782 | ICPIM-27431 Portfolio - Dashboard Viewer: View options | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:38 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39781 | ICPIM-27431 Portfolio - Dashboard Viewer: GUI | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:34 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-34249, ICPIM-17435, ICPIM-15735, ICPIM-15737, ICPIM-15739, ICPIM-15741, ICPIM-15743
Test Case | ICPIM-39780 | ICPIM-27431 Portfolio - Dashboard Viewer: Image view | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:29 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-39779 | ICPIM-39777 CSV - Pre-execute filter | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-25 03:22
Test Case | ICPIM-39778 | ICPIM-16022 Portfolio - Viewer: Image view | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 03:13 | 2100 | 1200 | 900 | 57% | 2100 | 1200 | 900 | 57% |  | ICPIM-20792, ICPIM-21630, ICPIM-20795, ICPIM-20801, ICPIM-20804, ICPIM-22110, ICPIM-22113
Test Case | ICPIM-39776 | ICPIM-16022 Portfolio - Viewer: Send email | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 02:19 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50% |  | ICPIM-20828
Test Case | ICPIM-39775 | ICPIM-16022 Portfolio - Viewer: Download as PDF | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 02:06 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-17817
Test Case | ICPIM-39774 | ICPIM-16022 Portfolio - Viewer: Download as PNG | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 01:57 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-17814
Test Case | ICPIM-39773 | ICPIM-39055 Associate Assets - Search SKUs | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-25 01:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39772 | ICPIM-16022 Portfolio - Viewer: GUI | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 01:49 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-39768 | ICPIM-13004 Portfolio - Bar Char: Graph and Slider | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-25 00:41 | 2100 | 1500 | 600 | 71% | 2100 | 1500 | 600 | 71%
Test Case | ICPIM-39766 | ICPIM-13004 Portfolio - Bar Char: Send email | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-24 22:02 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39765 | ICPIM-13004 Portfolio - Bar Char: Download as PDF | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-24 21:56 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39764 | ICPIM-38632 Commission Search: Future View color displays on 3D Viewer | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 21:13 | 5400 |  | 5400 | 0% | 5400 |  | 5400 | 0%
Test Case | ICPIM-39760 | ICPIM-18247 Reject CR From Authorize CR task | All |  | An Vo | An Vo | Web Client | New | 2015-06-24 03:57
Test Case | ICPIM-39759 | ICPIM-18249 Follow Up CR from Authorize CR task | All |  | An Vo | An Vo | Web Client | New | 2015-06-24 02:33
Test Case | ICPIM-39758 | ICPIM-28868 Create Child within Library Item (From Template): Create child within an occupied slot | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 02:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39757 | ICPIM-39755 Configure Connection Rules | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-24 01:38 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39756 | ICPIM-39755 Connection Rules dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-24 01:37 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39754 | ICPIM-23776 Display Sub-class in Nav Trace | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-24 00:21 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39753 | ICPIM-39721 3DViewer: IT Service Search Syscat: Execute filter with 'Hide' Enclosures | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:08 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39752 | ICPIM-39721 3DViewer: IT Service Search Syscat: Execute filter with 'Hide' Panels | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:08 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39751 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result: Color on 3D Viewer result | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:07 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39750 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result: Color on Ancestry | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:07 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39749 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for State 'Connected' | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:06 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39748 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for State 'Unconnected' | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-24 00:05 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39747 | ICPIM-23776 Display Sub-class in Textual Trace | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 23:17 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39734 | ICPIM-39716 New Classes: Edit object on CAD Editor | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 03:28 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39733 | ICPIM-39716 New Classes: Place and Handle object on CAD Viewer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 03:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39732 | ICPIM-39716 New Classes: Assign Template and display on Viewer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 03:23 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39731 | ICPIM-39716 New Classes: Connections | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 03:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39730 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for Type 'Both' | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39729 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for Type 'Carriers' | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39728 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for Type 'Providers' | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39727 | ICPIM-39721 3DViewer: IT Service Search Syscat: Result for selected IT Service | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39726 | ICPIM-39721 3DViewer: IT Service Search Syscat: 'State' dropdown | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:09 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39725 | ICPIM-39721 3DViewer: IT Service Search Syscat: 'Types' dropdown | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:09 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39724 | ICPIM-39721 3DViewer: IT Service Search Syscat: 'IT Services' dropdown | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:08 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39723 | ICPIM-39721 3DViewer: IT Service Search Syscat: Select 'IT Service' filter | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-23 03:08 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39722 | ICPIM-39716 New Classes: Create and Delete objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 03:06 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39720 | ICPIM-39716 Load Balancer: Properties | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 02:59 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39719 | ICPIM-39472 Portfolio - Favorites: Report | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-23 02:56 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-39718 | ICPIM-39472 Portfolio - Favorites: Search Results | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-23 02:51 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-39717 | ICPIM-39716 New Classes Added to Schema | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 02:50 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39715 | ICPIM-30248 CSV - Upload CSV from Windows Client - test with Disney CSV files | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 01:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39706 | ICPIM-13471 Delete registry keys on product uninstall | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-23 01:05 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39658 | ICPIM-13163 Portfolio - Gauge Chart: Dial gauge | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-19 05:20 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-39657 | ICPIM-13163 Portfolio - Gauge Chart: The Pivoted needle | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-19 05:03 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-39654 | ICPIM-39653 System Requirements on Help | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 03:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39652 | ICPIM-38616 CSV Import Log File: Full Datastore Update Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39651 | ICPIM-38616 CSV Import Log File: Data Connections Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39650 | ICPIM-38616 CSV Import Log File: Power Connections Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39649 | ICPIM-38616 CSV Import Log File: Library Item Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39648 | ICPIM-38616 CSV Import Log File: Rename Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:24 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39647 | ICPIM-38616 CSV Import Log File: Datastore Value Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:23 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39646 | ICPIM-38616 CSV Import Log File: Module Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:22 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39645 | ICPIM-38616 CSV Import Log File: Panel Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:21 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39644 | ICPIM-38616 CSV Import Log File: Enclosure Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:20 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39643 | ICPIM-38616 CSV Import Log File: Row Import | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-19 02:20 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39642 | ICPIM-39629 Copy a location that contains room: All Row Position Data | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39641 | ICPIM-39629 Copy a location that contains room: All Row Data | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39640 | ICPIM-39629 Copy a location that contains room: Tile Grid Data: Tile Axis Offsets and Labels | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39639 | ICPIM-39629 Copy a location that contains room: Tile Grid Data: Default Row Position Size | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39638 | ICPIM-39629 Copy a location that contains room: Tile Grid Data: Default Row Size | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39637 | ICPIM-39629 Copy a location that contains room: Tile Grid | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39636 | ICPIM-39629 Copy a room: All Row Position Data | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:10 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39635 | ICPIM-39629 Copy a room: All Row Data | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:10 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39634 | ICPIM-39629 Copy a room: Tile Grid Data: Tile Axis Offsets and Labels | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:09 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39633 | ICPIM-39629 Copy a room: Tile Grid Data: Default Row Position Size | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39632 | ICPIM-39629 Copy a room: Tile Grid Data: Default Row Size | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39631 | ICPIM-39629 Copy a room: Tile Grid | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39630 | ICPIM-39629 Ability to copy a room or an object that contains a room | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-06-19 02:06 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39618 | ICPIM-28898 Active Session - The Footer tab Label | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-18 22:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-39186
Test Case | ICPIM-39607 | ICPIM-22989 New Change Request - Missing Line of Business or Description | All |  | An Vo | An Vo | Web Client | New | 2015-06-18 01:54 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39606 | ICPIM-22989 New Change Request - Secondary Request Number | All |  | An Vo | An Vo | Web Client | New | 2015-06-18 01:44 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39605 | ICPIM-22989 New Change Request - Create with full Information | All |  | An Vo | An Vo | Web Client | New | 2015-06-18 01:32 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39598 | ICPIM-37261 Portfolio - Chart Viewer: Access Chart viewer | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-17 03:20 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-39594 | ICPIM-39591 Commission - Configure Commission Power: Store physical cable | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-17 02:39 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39593 | ICPIM-39591 Commission - Configure Commission Power: Create physical cable for power connection | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-17 02:37 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39592 | ICPIM-35539 Commission - Configure Commission Network: Create physical cable for network connection | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-17 02:28 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39587 | ICPIM-15988 Portfolio - Chart Titles: Changing chart name | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-17 00:30 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-39586 | ICPIM-21575 New CR Confirmation - Return to Previous page | All |  | An Vo | An Vo | Web Client | New | 2015-06-16 21:55 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39585 | ICPIM-21575 New CR Confirmation - Create another CR | All |  | An Vo | An Vo | Web Client | New | 2015-06-16 21:44 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39584 | ICPIM-21575 New CR Confirmation - Verify All CRs | All |  | An Vo | An Vo | Web Client | New | 2015-06-16 21:39 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39567 | ICPIM-27477 Connectivity Contstraints/Web Service Support - Placeholder! | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2015-06-16 12:49
Test Case | ICPIM-39566 | ICPIM-27477 INT_009 - Create a new asset - Invalid SKU - Asset is a Panel | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | New | 2015-06-16 12:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39556 | ICPIM-39554 Support large circuits | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-16 02:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39555 | ICPIM-39554 Web Trace | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-16 02:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39551 | ICPIM-37230 Portfolio - Descendants: Filter and Search | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-16 00:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-39544 | ICPIM-37230 Portfolio - Descendants: Sorting | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-15 21:57 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-39532 | ICPIM-37230 Portfolio - Descendants: Navigation | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-15 21:14 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-39527 | ICPIM-37230 Portfolio - Descendants: Descendants list | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-15 21:00 | 1500 | 1080 | 420 | 72% | 1500 | 1080 | 420 | 72%
Test Case | ICPIM-39494 | ICPIM-33616 Permissions to control item visibility in the App for ‘Portfolio Views - SimpleView’ | Magni |  | An Vo | An Vo | Web Client | New | 2015-06-12 03:35 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39493 | ICPIM-39487 Data Import Mapper: Clear Equipment | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 02:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39492 | ICPIM-39487 Data Import Mapper: Update Mapping | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 02:24 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39491 | ICPIM-39487 Data Import Mapper: Remove Mapping | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 02:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39490 | ICPIM-39487 Data Import Mapper: Import Mapping | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 02:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39489 | ICPIM-39487 Data Import Mapper: Add Mapping | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 02:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39488 | ICPIM-39487 Data Import Mapper: UI Check | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-12 01:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39486 | ICPIM-39055 Associate Assets - Assets have been assigned and unassigned | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-12 00:41 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39471 | ICPIM-39463 Email Drawing: Image file without Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:22 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39470 | ICPIM-39463 Email Drawing: Image with Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:21 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39469 | ICPIM-39463 Email Drawing: Image file without Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:20 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39468 | ICPIM-39463 Email Drawing: Image file with Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39467 | ICPIM-39463 Email Drawing: CAD file without Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39466 | ICPIM-39463 Email Drawing: CAD file with Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39465 | ICPIM-39463 Email Drawing: CAD file without Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39464 | ICPIM-39463 Email Drawing: CAD file with Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 04:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39462 | ICPIM-39454 Print Drawing: Print with Pasted Objects Shown | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39461 | ICPIM-39454 Print Drawing: Print with Pasted Objects Hidden | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39460 | ICPIM-37864 Configure Event - Event Actions |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 03:48 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39459 | ICPIM-39454 Print Drawing: Print Highlighted Section of CAD file | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39458 | ICPIM-37864 Configure Event - Event Handlers |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 03:45 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39457 | ICPIM-39454 Print Drawing: Print Whole CAD file | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39456 | ICPIM-37864 Configure Event - Delete an event |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 03:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39455 | ICPIM-37864 Configure Event - Add a preconfigured event |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 03:38 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39453 | ICPIM-39449 CAD Viewer: Export CAD file WITHOUT Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:22 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39452 | ICPIM-39449 CAD Viewer: Export CAD file with Datastores | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:21 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39451 | ICPIM-39449 CAD Viewer: Export CAD file WITHOUT Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39450 | ICPIM-39449 CAD Viewer: Export CAD file with Pasted Objects | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 03:18 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39448 | ICPIM-39442 User is assigned LOB that are associated assets | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-11 03:03 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39447 | ICPIM-39442 User is not assigned LOBs | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-11 03:00 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39446 | ICPIM-39367 Simple view - Level 9 - Future view: Corresponding highlight | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-11 02:48 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-39445 | ICPIM-37864 Configure Agent - Import Range |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 02:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39444 | ICPIM-37864 Configure Agent - Export Range |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 02:39 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39443 | ICPIM-37864 Configure Agent - Refresh |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 02:11 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39441 | ICPIM-37864 Configure Agent - Enable/ Disable Range |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-11 02:05 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39440 | ICPIM-38693 CAD Drawing Viewer - Zoom and Pan by Mousewheel | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 02:02 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39439 | ICPIM-38693 CAD Drawing Viewer - Zoom and Pan by Hotkeys | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-11 01:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39397 | ICPIM-39396 myDCIM - Favorites | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-10 03:35 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39394 | ICPIM-39390 Reorder Zone Items - Move Order Down | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-10 02:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39393 | ICPIM-39390 Reorder Zone Items - Move Order Up | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-10 02:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39392 | ICPIM-39390 Reorder Zone Items - Remove Member From Zone | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-10 02:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39391 | ICPIM-39390 Reorder Zone Items - Add Member to Zone | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-10 02:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39389 | ICPIM-39388 Remove Routing Zone | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-10 02:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39386 | ICPIM-39385 Configure Routing Zone | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:42 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-39384 | ICPIM-39383 Add Routing Zone | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:37 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-39382 | ICPIM-39377 Routing Zone Editor - Navigator: Update Connection List | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:35 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-39381 | ICPIM-39377 Routing Zone Editor - Navigator: Refresh | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:35 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-39380 | ICPIM-39377 Routing Zone Editor - Navigator: Link Navigator | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:34 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39379 | ICPIM-39377 Routing Zone Editor - Navigator: Crop items | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:34 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-39378 | ICPIM-39377 Routing Zone Editor: UI Check | Tyr (4.2) |  | Mai Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-06-10 02:33 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-39376 | ICPIM-39375 Application Settings - Portfolio Layout | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-10 00:43 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39371 | ICPIM-39362 User without permission to edit the Floor SimpleView | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-09 04:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39370 | ICPIM-39362 User without Feature enabled to view the Floor SimpleView | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-09 04:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39369 | ICPIM-39362 Parents of Assets that are associated with uer's LOB | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-09 04:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39368 | ICPIM-39362 Assets associated with LOB that are descendants of user's LOB | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-09 04:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39364 | ICPIM-37864 Configure Agent - Delete a iDiscover range |  |  | Khang Nguyen | Khang Nguyen | Data Exchange Agent | New | 2015-06-09 03:51 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39363 | ICPIM-39362 Assets are associated directly with User's LOB | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-09 03:50 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39351 | ICPIM-39346 Playback: Remove recording file | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-09 02:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39350 | ICPIM-39346 Playback: Play recording file | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-09 02:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39349 | ICPIM-39346 Playback: GUI check | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-09 02:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39348 | ICPIM-39345 Record: Continuously record | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-09 02:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39347 | ICPIM-39345 Record: Auto Record | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-09 02:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39344 | ICPIM-39336 Power Swing Simulator UPS of a site | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 02:03 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39343 | ICPIM-39336 Power Swing Simulator for UPS of a building | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 02:02 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39342 | ICPIM-39336 Power Swing Simulator for UPS of a floor | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 02:00 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39341 | ICPIM-39336 Power Swing Simulator for UPS of a data-center | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 01:59 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39340 | ICPIM-39336 Power Swing Simulator PDU of a site | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 01:58 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39339 | ICPIM-39336 Power Swing Simulator for PDU of a building | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 01:57 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39338 | ICPIM-39336 Power Swing Simulator for PDU of a floor | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 01:56 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39337 | ICPIM-39336 Power Swing Simulator for PDU of a data-center | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-06-09 01:54 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39335 | ICPIM-39055 Associate Assets - Assets Have Been Assigned to Closed (Inactive CR) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-08 19:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39324 | ICPIM-39310 iTRACS Pasted Item Layer: Right click on Pasted item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:33 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39323 | ICPIM-39310 iTRACS Pasted Item Layer - Zoom on select single pasted item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:31 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39322 | ICPIM-39310 iTRACS Pasted Item Layer: Hide/ Show list of pasted items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:29 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39321 | ICPIM-39310 iTRACS Pasted Item Layer - Global Display Option | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39320 | ICPIM-39310 iTRACS Pasted ITem Layer: Tooltips on Pasted Item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:24 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39319 | ICPIM-39310 iTRACS Pasted Item Layer: Auto Display Options | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:22 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39318 | ICPIM-39310 iTRACS Pasted Item Layer - Pasted Items list updated when new item dropped | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:20 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39317 | ICPIM-39310 iTRACS Pasted Item Layer: Global Hide/ Show | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39316 | ICPIM-39310 iTRACS Pasted Item Layer - Resize pasted item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39315 | ICPIM-39310 iTRACS Pasted Item Layer - Resized item with scale on zooming | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39314 | ICPIM-39310 iTRACS Pasted Item Layer - Remove pasted item via toolbar | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:09 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39313 | ICPIM-26018 Ensure Agent Can Be Cancel Deleting | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-06-08 03:09 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39312 | ICPIM-26018 Ensure Agent Instance Can Be Cancel Deleting | All |  | Thuy Tran | Thuy Tran | Data Exchange Agent | New | 2015-06-08 03:08 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-39311 | ICPIM-39310 iTRACS Pasted Item Layer: Create Custom Layer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-08 03:04 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39242 | ICPIM-35576 Role - User with role 'DEA' |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:31 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39241 | ICPIM-35576 Role - User with role 'Tech' |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:16 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39240 | ICPIM-35576 Role - User with role 'Planner' |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39239 | ICPIM-35576 Role - User with role 'Manager' |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39238 | ICPIM-35576 Role - User with role 'App Owner' |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39237 | ICPIM-35576 Role - User with role Admin |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39236 | ICPIM-35576 Role - User with role All Access |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-06-04 21:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39212 | ICPIM-38968 Active Directory - Not saving Group Name prefix | Cin (4.1.1) |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-06-04 00:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39211 | ICPIM-38968 Active Directory - Saving Group Name prefix by Save button | Cin (4.1.1) |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-06-04 00:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39210 | ICPIM-38968 Active Directory - Saving Group Name prefix by Close button | Cin (4.1.1) |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-06-04 00:33 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39209 | ICPIM-38968 Active Directory - Saving Group Name prefix by Apply button | Cin (4.1.1) |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-06-04 00:30 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39180 | ICPIM-39177 Web Roles: User Role has feature but no associated permission assigned | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-03 02:00 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39179 | ICPIM-39177 Web Roles: User Role does not have feature | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-03 01:59 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39178 | ICPIM-39177 Web Roles: User Role with features and associated permissions assigned | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-06-03 01:59 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39176 | ICPIM-39899 Delete saved and shared Forecasts | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:46 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39175 | ICPIM-39899 Delete shared Forecasts | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:45 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39174 | ICPIM-39899 Delete saved Forecasts | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:43 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39173 | ICPIM-39067 Selects to load a previously saved forecast | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:42 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39172 | ICPIM-39067 Selects to save an updated forecast simulation | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:41 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39171 | ICPIM-39067 Update forecast simulation data | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-06-03 00:40 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39144 | ICPIM-36660 Ruler Settings - Configure X/Y Axis Position | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client, Web Service, Windows Client | Pass | 2015-06-01 21:01 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-39104 | ICPIM-39026 Simple View - GUI: Navigation | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | Pass | 2015-06-01 04:06 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100%
Test Case | ICPIM-39091 | ICPIM-29555 DEA- Flat File - External SKU field | All |  | Thuy Tran | Thuy Tran |  | Pass | 2015-06-01 02:21 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-39090 | ICPIM-39086 Tile Grid Ruler - Adjust Offset - Input valid values for Y Starting Position | Bil (4.1.2) |  | Phuong Phan | Phuong Phan | Web Client, Windows Client | Pass | 2015-06-01 01:28 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-39089 | ICPIM-39086 Tile Grid Ruler - Adjust Offset - Input invalid values for Y Starting Position | Bil (4.1.2) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-06-01 01:26 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-39088 | ICPIM-39086 Tile Grid Ruler - Adjust Offset - Input valid values for X Starting Position | Bil (4.1.2) |  | Phuong Phan | Phuong Phan | Web Client, Windows Client | Pass | 2015-06-01 01:25 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-39087 | ICPIM-39086 Tile Grid Ruler - Adjust Offset - Input invalid values for X Starting Position | Bil (4.1.2) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-06-01 01:23 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-39085 | ICPIM-39049 Forecast - Original author can view and edit a forecast | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-31 20:48 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39084 | ICPIM-39049 Forecast - Verify that recipient is able to remove a shared forecast | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-31 20:41 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39073 | ICPIM-39049 Forecast - Recipient is able to modify and save the shared forecast as his own but read only for the shared forecast | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 03:39 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39072 | ICPIM-39049 Forecast - Result of sending forecast simulation to other iTRACS user | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 03:37 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39071 | ICPIM-39049 Forecast - Sending forecast simulation to other iTRACS user | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 03:36 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39070 | ICPIM-39067 Save Forecast - Labeling saved Forecast | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-29 03:26 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39069 | ICPIM-39067 Save Forecast - Save simulation data per user | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-29 03:24 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39068 | ICPIM-39067 Save Forecast - Save simulation data | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-29 03:22 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-39066 | ICPIM-29555 DEA- Flat File - SKU field | All |  | Thuy Tran | Thuy Tran |  | Pass | 2015-05-29 03:03 | 2400 | 3600 | 0 | 100% | 2400 | 3600 | 0 | 100%
Test Case | ICPIM-39065 | ICPIM-39019 Stacked Commission - Windows - Question mark - Assets are not scheduled to receive different incoming gear | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39064 | ICPIM-39019 Stacked Commission - Windows - Question mark - Power ports are not scheduled to receive different incoming gear | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:27 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39063 | ICPIM-39019 Stacked Commission - Windows - Question mark - Network connectivity ports are not scheduled to receive different incoming gear | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:26 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39062 | ICPIM-39019 Stacked Commission - Windows - Question mark - Space is not scheduled to receive different incoming gear | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:25 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39061 | ICPIM-39019 Stacked Commission - Windows- Commission a switch/ a server into a scheduled - unoccupied space that contains a panel currently | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:22 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39060 | ICPIM-39019 Stacked Commission - Windows- Commission a server into a scheduled - unoccupied space that contains a switch currently | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:20 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39059 | ICPIM-39019 Stacked Commission - Windows- Commission a switch into a scheduled - unoccupied space that contains a server currently | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-29 02:20 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39058 | ICPIM-39019 Stacked Commission - Windows- Commission Power Connectivity to ports that are currently connected but scheduled to disconnect | Tyr (4.2) |  | Mai Nguyen | Phuong Phan | Windows Client | New | 2015-05-29 02:19 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39057 | ICPIM-39019 Stacked Commission - Windows- Commission Network Connectivity to ports that are currently connected but scheduled to disconnect | Tyr (4.2) |  | Mai Nguyen | Phuong Phan | Windows Client | New | 2015-05-29 02:16 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39056 | ICPIM-39055 Associate Assets - Associate Inventory Assets | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-29 01:22 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-18623, ICPIM-19891
Test Case | ICPIM-39054 | ICPIM-39049 Forecasts - CSV data | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 01:07 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39053 | ICPIM-39049 Forecasts - Web client builds the CSV and downloads to the User | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 01:04 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39052 | ICPIM-39049 Forecasts - PDF data | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 01:00 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39051 | ICPIM-39049 Forecasts - Web client supports PNG file for both charts (Bar chart, Line chart) | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 00:56 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39050 | ICPIM-39049 Forecasts - Web client builds the PDF and downloads to the User | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-29 00:54 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39048 | ICPIM-35462 Circuit trace ports on items within their LOB | Bil (4.1.2) |  | An Vo | An Vo | Web Client, Web Service | Pass | 2015-05-29 00:14 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-38902
Test Case | ICPIM-39034 | ICPIM-39017 Simple View - View States: Replace "Enclosure Position" by "Row Position" | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | Pass | 2015-05-28 02:36 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-39033 | ICPIM-39026 Simple View - GUI: Up level navigator | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | Pass | 2015-05-28 02:35 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-39031 | ICPIM-39026 Simple View - GUI: The font size of the Cabinet labels | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | Pass | 2015-05-28 02:35 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-39030 | ICPIM-39614 Stacked Commission - Web- Commission a module into a scheduled - unoccupied space | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-28 02:35 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39029 | ICPIM-39365 Simple View - Filters: The Tooltip hover for the filter | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | Pass | 2015-05-28 02:34 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-39092, ICPIM-39095, ICPIM-39098
Test Case | ICPIM-39028 | ICPIM-39614 Stacked Commission - Web- Commission an equipment into a scheduled - unoccupied space | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-28 02:34 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39027 | ICPIM-39614 Stacked Commission - Web- Commission an enclosure into a scheduled - unoccupied space | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-28 02:33 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-39025 | ICPIM-39019 Stacked Commission - Windows- Commission a module into a scheduled - unoccupied space | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-28 02:32 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39024 | ICPIM-39366 Simple View - Overlays: Performance | Bil (4.1.2) |  | Tien Pham | An Vo | Web Client | Pass | 2015-05-28 02:32 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-39023 | ICPIM-39019 Stacked Commission - Windows- Commission Panel into position where the panel in said position is scheduled for decommissioning | Tyr (4.2) |  | Mai Nguyen | Phuong Phan | Windows Client | New | 2015-05-28 02:32 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-39021 | ICPIM-39019 Stacked Commission - Windows- Commission an enclosure into a scheduled - unoccupied space | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Windows Client | New | 2015-05-28 02:30 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-39020 | ICPIM-39017 Simple View - View States: Displaying performance | Bil (4.1.2) |  | An Vo | An Vo | Web Client | Pass | 2015-05-28 02:30 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-39014 | ICPIM-37314 Portfolio - Home: Collapse/ Expand Pie Chart | Bil (4.1.2) |  | Tien Pham | An Vo | Web Client | Pass | 2015-05-28 01:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-39013 | ICPIM-37314 Portfolio - Home: Collapse/ Expand Asset Attributes | Bil (4.1.2) |  | Tien Pham | An Vo | Web Client | Pass | 2015-05-28 01:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-39011 | ICPIM-37314 Portfolio - Home: Display appropriate message when unable to reach Google Maps | Ran (4.1) |  | An Vo | An Vo | Web Client | Pass | 2015-05-27 22:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-39010 | ICPIM-38968 Active Directory - Configure Group Name Prefix | Cin (4.1.1) |  | Thuy Tran | Thuy Tran |  | New | 2015-05-27 21:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39009 | ICPIM-38811 Convert Commission Search to utilize the new Analytics TERA data | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-27 21:02 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-39008 | ICPIM-38811 Remove Multi-Connector options from Commission Search UI | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-27 21:02 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-39007 | ICPIM-38811 Remove Commission Search job queue scripts | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-27 20:59 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38979 | ICPIM-27274 Commission - Set Destination: Specific Location | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:23 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38978 | ICPIM-27274 Commission - Set Destination: Seeding the widget | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:22 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-38977 | ICPIM-27274 Commission - Set Destination: Result of Asset levels for Module commissions | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:22 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38976 | ICPIM-27274 Commission - Set Destination: Result of Asset levels for Equipment commissions | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:21 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38975 | ICPIM-27274 Commission - Set Destination: Result of Asset levels for Enclosure commissions | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:21 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38974 | ICPIM-27274 Commission - Set Destination: Result sorting | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38973 | ICPIM-27274 Commission - Set Destination: Result Filtering | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38972 | ICPIM-27274 Commission - Set Destination: Result visualization | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 03:18 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38969 | ICPIM-38968 Active Directory - Prefix per type | Cin (4.1.1) |  | Thuy Tran | Thuy Tran |  | New | 2015-05-27 03:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38966 | ICPIM-38959 Technician window - Update Filter setting | Bil (4.1.2) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-05-27 01:36 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38965 | ICPIM-38959 Technician window - Store Filter settings to User's profile | Bil (4.1.2) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-05-27 01:35 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38964 | ICPIM-38959 Technician window - Work Action within filter location | Bil (4.1.2) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-05-27 01:34 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38963 | ICPIM-27274 Commission - Set Destination: Search for Enclosure | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 01:34 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38962 | ICPIM-38959 Technician window - Filter bar | Bil (4.1.2) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-05-27 01:33 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-38961 | ICPIM-27274 Commission - Set Destination: Search for Row | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 01:33 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38960 | ICPIM-27274 Commission - Set Destination: Search for Data Center | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-27 01:32 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38957 | ICPIM-38947 CAPF - Manage saved/shared ForeCasts | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-27 01:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38956 | ICPIM-38947 CAPF - Access Forecast via myDCIM page | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-27 01:27 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38955 | ICPIM-38950 Enable replacement of Enclosure - Update database with Enclosure NOT within a set distance from the floor | Bil (4.1.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-05-27 01:27 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-38954 | ICPIM-38950 Enable replacement of Enclosure - Update database with Enclosure within a set distance from the floor | Bil (4.1.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2015-05-27 01:24 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-38325
Test Case | ICPIM-38953 | ICPIM-38947 CAPF - Access Forecast via Portfolio page | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-27 01:24 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38952 | ICPIM-38950 Disable replacement of Enclosure | Bil (4.1.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-05-27 01:23 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-38951 | ICPIM-38947 CAPF - Access Forecast via direct URL | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-27 01:23 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38948 | ICPIM-38947 CAPF - Role Permission | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-27 01:20 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38945 | ICPIM-38933 ANLC - New GUI -No hook to pre-existing scheduled Analytics event action | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 01:05 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38944 | ICPIM-38933 ANLC - New GUI -Links to help documentation per each Analytics component | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 01:04 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38943 | ICPIM-38933 ANLC - New GUI -Prevent scheduling The Data Stores component | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 01:03 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38942 | ICPIM-38933 ANLC - New GUI - Unschedule a scheduled Analytics component | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:57 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38941 | ICPIM-38933 ANLC - New GUI - Set Log level - Detail level | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:56 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38940 | ICPIM-38933 ANLC - New GUI - Set Log level - High level | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38939 | ICPIM-38933 ANLC - New GUI - Schedule many instances for a single Analytics component with different intervals | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38938 | ICPIM-38933 ANLC - New GUI - Schedule a single Analytics component - Recurrence (Once, Hourly, Daily, Weekly) | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:51 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38936 | ICPIM-38933 ANLC - New GUI - Schedule more than a single Analytics component | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:44 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38935 | ICPIM-38933 ANLC - New GUI - Schedule a single Analytics component | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:43 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38934 | ICPIM-38933 ANLC - New GUI - Display all currently scheduled Analytics components. | Tyr (4.2) |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-05-27 00:40 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38931 | ICPIM-24735 Change Management - Status: 30s Auto refresh | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 21:56 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38928 | ICPIM-39591 Commission - Configure Commission Power: "Route To" visualization | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-26 21:32 | 3000 | 900 | 2100 | 30% | 3000 | 900 | 2100 | 30%
Test Case | ICPIM-38927 | ICPIM-28806 Schema - Classes - Edit Dictionary - Add datastore using wizard |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2015-05-26 21:20 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-38649
Test Case | ICPIM-38926 | ICPIM-14714 Portfolio - Advanced Search: by Circuit ID | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 20:43 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38925 | ICPIM-15839 Portfolio - Trace: Display Circuit ID on web trace | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 20:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38887 | ICPIM-39591 Commission - Configure Commission Power: "Service" drop-down | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-26 02:36 | 3000 | 2400 | 600 | 80% | 3000 | 2400 | 600 | 80%
Test Case | ICPIM-38876 | ICPIM-36809 Simple View - Floor View: Resize a "busy" Row | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-26 01:45 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-38875 | ICPIM-36809 Simple View - Floor View: Resize an Empty Row | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-26 01:43 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-38874 | ICPIM-38540 Commission Within Wizard - Within Equipment | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 01:39 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-38872 | ICPIM-38540 Commission Within Wizard - Within Enclosure | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 01:37 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-38871 | ICPIM-38540 Commission Within Wizard - Within Row Position | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 01:36 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-38870 | ICPIM-38540 Commission Within Wizard - Within Row | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-26 01:33 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-38863 | ICPIM-38540 Commission Within Wizard - Associate Assets to each work project successfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 21:53 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38862 | ICPIM-38540 Commission Within Wizard - Associate Assets to each work project unsuccessfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 21:51 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38861 | ICPIM-38540 Commission Within Wizard - Prompt user when submitting commission | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 21:50 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38860 | ICPIM-38540 Commission Within Wizard - Work summary | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 21:48 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-38859 | ICPIM-38540 Commission Within Wizard - Search SKU and Inventory assets | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 03:05 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38858 | ICPIM-35539 Commission - Configure Commission Network: "Route To" drop-down | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-25 03:02 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38857 | ICPIM-38540 Commission Within Wizard - Associate Assets to CR successfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 03:01 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38856 | ICPIM-38540 Commission Within Wizard - Submit new CR UI | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:56 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38855 | ICPIM-38540 Commission Within Wizard - TargetId, Specific Index | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:55 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-38854 | ICPIM-38540 Commission Within Wizard - Review Work Project UI | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:53 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38853 | ICPIM-38540 Commission Within Wizard - Submit new CR unsuccessfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:51 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38852 | ICPIM-38540 Commission Within Wizard - Submit new CR successfully | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:50 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-38850 | ICPIM-38848 Display U position when specific (or general) location is Asset Level 1-8 | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:34 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38849 | ICPIM-38848 Display U position when specific (or general) location is Asset Level 9 | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-25 02:31 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38847 | ICPIM-35539 Commission - Configure Commission Network: "Route To" visualization | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-25 02:09 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38845 | ICPIM-16022 Portfolio - Viewer: View options | Tyr (4.2) |  | Tien Pham | Khang Nguyen | Web Client | New | 2015-05-25 02:01 | 2700 | 2700 | 0 | 100% | 2700 | 2700 | 0 | 100%
Test Case | ICPIM-38844 | ICPIM-38811 Remove Security Rights | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38843 | ICPIM-39026 Simple View - GUI: New Updated | Tyr (4.2) |  | Tien Pham | Khang Nguyen | Web Client | New | 2015-05-25 01:56 | 2700 | 2400 | 300 | 88% | 2700 | 2400 | 300 | 88%
Test Case | ICPIM-38842 | ICPIM-38811 Remove Configure Commission Search dialog as well as Menu and Toolbar buttons | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38841 | ICPIM-38811 Commission Search Logic: Convert Network to Analytics data - Copper and Fiber Panel | Tyr (4.2) |  | Thuy Tran | Mai Nguyen | Analytics, Windows Client | New | 2015-05-25 01:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38840 | ICPIM-38811 Commission Search Logic: Convert Space to Analytics data: Pull Row data | Tyr (4.2) |  | Thuy Tran | Mai Nguyen | Analytics, Windows Client | New | 2015-05-25 01:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38839 | ICPIM-36605 Portfolio - Asset Attributes: New Attributes for Levels 8, 9, 10 | Tyr (4.2) |  | Tien Pham | Khang Nguyen | Web Client | New | 2015-05-25 01:54 | 2700 | 1200 | 1500 | 44% | 2700 | 1200 | 1500 | 44%
Test Case | ICPIM-38837 | ICPIM-38811 Commission Search Logic: Convert Space to Analytics data: Pull Enclosure data - Level 9 | Tyr (4.2) |  | Thuy Tran | Mai Nguyen | Analytics, Windows Client | New | 2015-05-25 01:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38836 | ICPIM-38811 Commission Search Logic: Convert Power to Analytics data: Asset contains Power Strips | Tyr (4.2) |  | Thuy Tran | Mai Nguyen | Analytics, Windows Client | New | 2015-05-25 01:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38834 | ICPIM-38811 Commission Search Logic: Convert Power to Analytics data: Pull Enclosure data | Tyr (4.2) |  | Thuy Tran | Mai Nguyen | Windows Client | New | 2015-05-25 01:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38832 | ICPIM-35799 User Profile Settings - Colors and Font size | Tyr (4.2) |  | An Vo | Khang Nguyen | Web Client | New | 2015-05-25 01:52 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-38831 | ICPIM-38811 Commission Search: Fiber: Searching by SKU: both switch ports and positions | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:51 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38830 | ICPIM-38811 Commission Search: Fiber: Searching by SKU: Just positions | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:50 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38829 | ICPIM-38811 Commission Search: Fiber: Searching by SKU: Just switch ports | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:50 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38828 | ICPIM-38811 Commission Search: Fiber: Searching by SKU: No Fiber ports | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38827 | ICPIM-38811 Commission Search: Copper: Searching by SKU: both switch ports and positions | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:48 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38826 | ICPIM-38811 Commission Search: Copper: Searching by SKU: Just positions | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:47 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38825 | ICPIM-38811 Commission Search: Copper: Searching by SKU: Just switch ports | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:47 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38823 | ICPIM-38811 Commission Search: Copper: Searching by SKU: No copper ports | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38821 | ICPIM-38811 Commission Search: Copper and Fiber: List Selection saved as User Profile | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38819 | ICPIM-39375 Application Settings - Add New Settings | Tyr (4.2) |  | An Vo | Khang Nguyen | Web Client | New | 2015-05-25 01:45 | 2700 | 1500 | 1200 | 55% | 2700 | 1500 | 1200 | 55%
Test Case | ICPIM-38817 | ICPIM-38811 Commission Search: GUI changes: Fiber | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38816 | ICPIM-36809 Simple View - Floor View: Rotate Enclosure | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-25 01:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38815 | ICPIM-38811 Commission Search: GUI changes: Copper | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-25 01:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38808 | ICPIM-37262 Web Dictionary Configuration - Ability to centralize administration | Tyr (4.2) |  | An Vo | Khang Nguyen | Web Client | New | 2015-05-25 01:40 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38807 | ICPIM-36809 Simple View - Floor View: Copy Object | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-25 01:39 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38804 | ICPIM-37262 Web Dictionary Configuration - Configure by normal user account | Tyr (4.2) |  | An Vo | Khang Nguyen | Web Client | New | 2015-05-25 01:36 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38799 | ICPIM-36809 Simple View - Floor View: Move Enclosure unsucessfully | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-25 01:30 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-38797 | ICPIM-36809 Simple View - Floor View: Move Enclosure sucessfully | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-25 01:28 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-38758 | ICPIM-35691 Define New Requirements | Tyr (4.2) |  | Jason Roth | Jason Roth |  | New | 2015-05-22 08:26
Test Case | ICPIM-38745 | ICPIM-38733 CAD Drawing Manager: Delete CAD files | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 02:37 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38743 | ICPIM-38733 CAD Drawing Manager: Update drawing files | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 02:36 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38742 | ICPIM-36809 Simple View - Floor View: Move/rotate Row | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-22 02:36 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-38741 | ICPIM-38733 CAD Drawing Manager: Importing CAD | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 02:34 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38739 | ICPIM-38733 CAD Drawing Manager: Selection drawing item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 02:33 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38738 | ICPIM-38733 CAD Drawing Manager: Open the dialog | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 02:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38736 | ICPIM-36809 Simple View - Floor View: Add Enclosure(s) | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-22 02:20 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100%
Test Case | ICPIM-38735 | ICPIM-36809 Simple View - Floor View: Add Row(s) | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-22 02:19 | 840 |  | 840 | 0% | 840 |  | 840 | 0%
Test Case | ICPIM-38732 | ICPIM-38693 CAD Drawing Viewer - Selection of Pasted Items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38731 | ICPIM-16022 Portfolio - Viewer: Apply Overlay | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-22 01:46 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38730 | ICPIM-16022 Portfolio - Viewer: Filter "pasted" object(s) | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-22 01:45 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38729 | ICPIM-38693 CAD Drawing Viewer - Filtering Pasted Items result | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38728 | ICPIM-16022 Portfolio - Viewer: Perform actions | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-22 01:44 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38727 | ICPIM-38693 CAD Drawing Viewer - Searching for Pasted Item | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38726 | ICPIM-38693 CAD Drawing Viewer: List of Pasted Items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38715 | ICPIM-38693 CAD Drawing Viewer: display of pasted items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38714 | ICPIM-16022 Portfolio - Viewer: View Background Image, Pane/Zoom, Select pasted object(s) | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-22 01:15 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38712 | ICPIM-38701 Graphical List: Edit mode - Configure the display of a "pasted" object(s) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:13 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38711 | ICPIM-38701 Graphical List: Edit mode - Resize "pasted" object(s) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:12 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38710 | ICPIM-38701 Graphical List: Edit mode - Position (move) "pasted" object(s) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:11 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38709 | ICPIM-38693 CAD Drawing Viewer - Zoom by Toolbar | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 01:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38708 | ICPIM-38701 Graphical List: Edit mode - Remove "pasted" object(s) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:09 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38707 | ICPIM-38701 Graphical List: Edit mode - Add "pasted" object(s) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:07 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38706 | ICPIM-38701 Graphical List: Edit mode - Upload a background image | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38705 | ICPIM-38701 Graphical List: Graphical mode | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:04 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38704 | ICPIM-38701 Graphical List: Replace Google Maps for Asset Level 1-4 | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:01 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38703 | ICPIM-38701 Graphical List: Leveraging Google Maps | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-22 01:00 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38702 | ICPIM-38693 CAD Drawing Editor: toolbar | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38700 | ICPIM-38693 CAD Drawing Viewer - Remove items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38698 | ICPIM-38693 CAD Drawing Viewer - Resize items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38697 | ICPIM-38693 CAD Drawing Viewer - Reposition / Move items | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38696 | ICPIM-38693 CAD Drawing Viewer - Add/ Paste / Place item to viewer | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38695 | ICPIM-38693 CAD Drawing Viewer - Open in Read-Only mode | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:29 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38694 | ICPIM-38693 CAD Drawing Viewer - Open in Edit mode | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-22 00:23 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38692 | ICPIM-38691 KPMG - Resize the cabinet commission dialog |  |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-22 00:13 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-38690 | ICPIM-38687 Log - Report date/time in GMT | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38689 | ICPIM-38687 Log - Export date/time in GMT | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38688 | ICPIM-38687 Log - Displays date/time in local time | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38686 | ICPIM-38682 Remove many Assets by CSV file - Line items match in CPIM | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:37 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-38685 | ICPIM-38682 Remove an Asset by CSV file - Line item match in CPIM | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:36 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0%
Test Case | ICPIM-38684 | ICPIM-38682 Remove Assets by CSV file - Line item not match in CPIM | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:35 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38683 | ICPIM-38682 Remove Assets by CSV file - Aborted | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 23:34 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38680 | ICPIM-38677 Trigger Alarm - Equipment passed to the event is recorded against the Alarm Manager | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-05-21 23:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38679 | ICPIM-38677 Trigger Alarm - Configuration | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-05-21 23:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38678 | ICPIM-38677 Trigger Alarm - Label | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-05-21 23:24 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38673 | ICPIM-38657 "Compare" Data Stores Visual Filter: Execute without select a datastore | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38672 | ICPIM-38657 "Compare" Data Stores Visual Filter: Execute without selecting a class | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38671 | ICPIM-38657 "Compare" Data Stores Visual Filter: Execute and verify result for Asset Level 11 - Module | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38670 | ICPIM-38657 "Compare" Data Stores Visual Filter: Execute and verify result for Asset Level 10 - Equipment | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38669 | ICPIM-38657 "Compare" Data Stores Visual Filter: Execute and verify result for Asset Level 9 - Enclosure | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38668 | ICPIM-38657 "Compare" Data Stores Visual Filter: Field settings should be recorded in the User's Profile | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38667 | ICPIM-38657 "Compare" Data Stores Visual Filter: Ranges: pre-compute button | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38666 | ICPIM-38657 "Compare" Data Stores Visual Filter: Ranges: Browser button | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38665 | ICPIM-38657 "Compare" Data Stores Visual Filter: Ranges: Set Color | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38664 | ICPIM-38657 "Compare" Data Stores Visual Filter: Ranges: Set value | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38663 | ICPIM-38657 "Compare" Data Stores Visual Filter: Datastore list for Asset Level 11 classes | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:37 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38662 | ICPIM-38657 "Compare" Data Stores Visual Filter: Datastore list for Asset Level 10 classes | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:36 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38661 | ICPIM-38657 "Compare" Data Stores Visual Filter: Datastore list for Asset Level 9 classes | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:36 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38660 | ICPIM-38657 "Compare" Data Stores Visual Filter: Class list | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:35 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38659 | ICPIM-38657 "Compare" Data Stores Visual Filter: List of Asset Levels | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:34 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38658 | ICPIM-38657 "Compare" Data Stores Visual Filter: New Type "Compare" | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 21:33 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38656 | ICPIM-35559 Connectivity - Circuit ID: removing Circuit ID using CSV | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-21 20:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38655 | ICPIM-35559 Connectivity - Circuit ID: Remove Circuit ID | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-21 20:36 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38654 | ICPIM-35559 Connectivity - Circuit ID: Edit Circuit ID | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-21 20:35 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38641 | ICPIM-28758 Isle Containment: renamed on TYR | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-21 02:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38640 | ICPIM-38539 Task Management - Tasks: Status Bar | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:47 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-38639 | ICPIM-20047 Task Management - Verify Work Action - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:44 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38638 | ICPIM-38632 Future View color displays on 3D Viewer |  |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-21 02:43 | 5400 |  | 5400 | 0% | 5400 |  | 5400 | 0%
Test Case | ICPIM-38637 | ICPIM-38632 Change the color of objects displaying in Future View |  |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-21 02:40 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-38636 | ICPIM-38632 Enable/ Disable Future View color |  |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-21 02:38 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-38635 | ICPIM-40024 Task Management - Resolve Work Action - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:36 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38634 | ICPIM-38632 Default state of Future View color is disable |  |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-21 02:36 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-38633 | ICPIM-20189 Tasks - Execute Work - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:35 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38631 | ICPIM-23087 Tasks - Delegate Work - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:33 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38630 | ICPIM-23050 Tasks - Schedule CR - View detailed information | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:31 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-24470, ICPIM-24476, ICPIM-24490, ICPIM-24495
Test Case | ICPIM-38629 | ICPIM-23032 Tasks - Authorize CR - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38628 | ICPIM-23025 Tasks - Verify CR - View detailed information | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:26 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38626 | ICPIM-36809 Simple View - Floor View: Remove object |  |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-21 02:23 | 720 | 1500 | 0 | 100% | 720 | 1500 | 0 | 100%
Test Case | ICPIM-38625 | ICPIM-38539 Task Management - Tasks: Task list | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:23 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38624 | ICPIM-38539 Task Management - Tasks: User Settings | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-21 02:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38623 | ICPIM-38539 Task Management - Tasks: Bulk Actions menu | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:20 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-27276
Test Case | ICPIM-38621 | ICPIM-38539 Task Management - Tasks: Bulk comment | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:18 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-27462
Test Case | ICPIM-38619 | ICPIM-38539 Task Management - Tasks: Sidebar | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:16 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-27311
Test Case | ICPIM-38618 | ICPIM-38539 Task Management - Tasks: Ghostbar | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-21 02:14 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-38617 | ICPIM-38616 CSV Import Log File: Basic Import | Tyr (4.2) |  | Vinh Nguyen | Thuy Tran | Windows Client | New | 2015-05-21 01:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38611 | ICPIM-38540 Simple View - Row level: Commission Within an Equipment | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-21 01:11 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38610 | ICPIM-38608 Remove Auto-Complete In Decommission | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 01:02 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38609 | ICPIM-38608 Remove Auto-Complete In Commissioning | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-21 00:59 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38607 | ICPIM-38540 Simple View - Enclosure level: Commission Within an Equipment | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-21 00:50 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38606 | ICPIM-38540 Simple View - Enclosure level: Commission Within an Enclosure | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-21 00:38 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38599 | ICPIM-38540 Simple View - Row level: Commission Within an Enclosure | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-21 00:30 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38596 | ICPIM-38540 Simple View - Enclosure level: Commission Within an U-Position | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-21 00:26 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38594 | ICPIM-38540 Simple View - Row level: Commission Within an U-Position | Tyr (4.2) |  | Tien Pham | Tien Pham | Web Client | New | 2015-05-21 00:24 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38591 | ICPIM-36919 Simple View - Cabinet View: Move Panel | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-21 00:20 | 3600 | 2100 | 1500 | 58% | 3600 | 2100 | 1500 | 58%
Test Case | ICPIM-38590 | ICPIM-38540 Simple View - Row level: Commission Within a Row Position | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-21 00:19 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38587 | ICPIM-38540 Simple View - Floor level: Commission Within an Enclosure | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-21 00:09 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38586 | ICPIM-38585 Configure Search Schema | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Windows Client | New | 2015-05-21 00:06 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-38583 | ICPIM-38540 Simple View - Floor level: Commission Within a Row Position | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38582 | ICPIM-38540 Simple View - Floor level: Commission Within a Row | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-20 23:54 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38581 | ICPIM-38579 Auto-Number: "Send Preview to Manual": More than 50 Items with long string | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-20 23:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38580 | ICPIM-38579 Auto-Number: "Send Preview to Manual": More than 50 Items | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-20 23:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38576 | ICPIM-38575 Basic Search - Wildcard value '%' | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-05-20 21:19 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38574 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Show/Hide options | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 20:04 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38572 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Highlight based on selecting of a connected port within Enclosure | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38571 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Selectable | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38570 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Highlight based on external hover | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38569 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Anchor options | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38568 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Tooltip | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38567 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Left and Right Sides Not sorted | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:51 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38566 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Left and Right Sides Not editable | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38565 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Display Front face only | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38564 | ICPIM-36919 Simple View - Cabinet side mounted Assets: 3D Orientation | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38563 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Rear Orientation | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Windows Client | New | 2015-05-20 19:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38562 | ICPIM-36919 Simple View - Cabinet side mounted Assets: Front Orientation | Tyr (4.2) |  | Thuy Tran | Thuy Tran | Web Client | New | 2015-05-20 19:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38553 | ICPIM-15518 Test Creation | Tyr (4.2) |  | Donna Daigneault | Alok Ghodke |  | New | 2015-05-20 10:33
Test Case | ICPIM-38549 | ICPIM-38540 Simple View - Displaying Commission Within icon only when 1 item is selected | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-20 04:12 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38548 | ICPIM-38540 Simple View - Displaying Commission Within for user has commission permission only | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-20 03:43 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38546 | ICPIM-30248 CSV - Upload CSV from Windows Client | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-20 03:38 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38545 | ICPIM-38540 Simple View - Displaying Commission Within icon in SimpleView | Tyr (4.2) |  | Tien Pham | Tien Pham |  | New | 2015-05-20 03:36 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38544 | ICPIM-22983 Task: Remove All Filters Except Location and Line of Business | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-20 03:18 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38543 | ICPIM-38539 Task Management - Tasks: Split Screen for All, Team and My Tasks | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-20 03:16 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38542 | ICPIM-38539 Task Management - Tasks: Sidebar toggle button | Tyr (4.2) |  | Tien Pham | An Vo | Web Client | New | 2015-05-20 03:12 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-38538 | ICPIM-27274 Commission - Set Destination: Port connection status | Tyr (4.2) |  | Tien Pham | Mai Nguyen | Web Client | New | 2015-05-20 03:00 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38532 | ICPIM-36919 Simple View - Cabinet View: Undo action from Change Log | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-20 02:33 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-38529 | ICPIM-12585 Portfolio - Cooling Pie chart: Historical/ Trending charts | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-20 02:24 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-38527 | ICPIM-12585 Portfolio - Cooling Pie chart: Drill-in | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-20 02:22 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-38525 | ICPIM-12585 Portfolio - Cooling Pie chart: Operates off of the analytics data | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Analytics, Web Client | New | 2015-05-20 02:15 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-38522 | ICPIM-12585 Portfolio - Cooling Pie chart: Asset levels 1-8 | Tyr (4.2) |  | Khang Nguyen | Khang Nguyen | Web Client | New | 2015-05-20 02:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38519 | ICPIM-36919 Simple View - Cabinet View: Rotate Module | Tyr (4.2) |  | Tien Pham | Phuong Phan | Web Client | New | 2015-05-20 02:10 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-38518 | ICPIM-36919 Simple View - Cabinet View: Move Module | Tyr (4.2) |  | Tien Pham | Phuong Phan |  | New | 2015-05-20 02:07 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-38513 | ICPIM-21266 Time Active for Cancelled CR | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-05-20 01:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38512 | ICPIM-20183 Change Management - Complete CR: Time Active for Completed CR | Tyr (4.2) |  | Tien Pham | Mai Nguyen | Web Client | New | 2015-05-20 01:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38508 | ICPIM-36605 Portfolio - Asset Attributes: Log Datastore Editing | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:28 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-38503 | ICPIM-36605 Portfolio - Asset Attributes: Log Asset renaming | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:21 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38498 | ICPIM-38494 SimpleView - Change List: Discard changes to the database | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:09 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-38497 | ICPIM-38494 SimpleView - Change List: Commit changes to the database | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38496 | ICPIM-38494 SimpleView - Change List: Remove | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:07 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-38495 | ICPIM-38494 SimpleView - Change List: GUI | Tyr (4.2) |  | Tien Pham | Thuy Tran | Web Client | New | 2015-05-20 01:06 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-38492 | ICPIM-39026 Simple View - GUI: Colorize connected Fiber ports | Tyr (4.2) |  | Tien Pham | Mai Nguyen | Web Client | New | 2015-05-20 01:02 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38490 | ICPIM-38484 Create scheduled connection: Select Link type - Web UI | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Web Client | New | 2015-05-20 00:59 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-38489 | ICPIM-38484 Commissioning: Auto Routing with connection rules - Web UI | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Web Client | New | 2015-05-20 00:56 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-38488 | ICPIM-38484 Create scheduled connection: Select Link type | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-20 00:51 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-38486 | ICPIM-38484 Commissioning: Auto Routing with connection rules | Tyr (4.2) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-20 00:36 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-38482 | ICPIM-39055 Associate Assets - Assets Have Been Assigned to Open (Active CR) | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-19 23:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38479 | ICPIM-28596 Connectivity - Connect tab - Update on TYR |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-05-19 23:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-35668, ICPIM-37371
Test Case | ICPIM-38478 | ICPIM-38475 Make one to many Connections - Create Type | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-19 23:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38477 | ICPIM-38475 Make one to many Connections - Existing Type | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-19 23:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38476 | ICPIM-38475 Make one to many Connections - Virtual Type | Tyr (4.2) |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-05-19 23:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38472 | ICPIM-38539 Task Management - Tasks: Produce a CSV of work actions list | Tyr (4.2) |  | An Vo | Tien Pham | Web Client | New | 2015-05-19 21:51 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-38470 | ICPIM-38539 Task Management - Tasks: Produce a CSV of non-work action list | Tyr (4.2) |  | An Vo | Tien Pham | Web Client | New | 2015-05-19 21:45 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0% |  | ICPIM-26965
Test Case | ICPIM-38469 | ICPIM-15839 Portfolio - Trace: Future Trace | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-19 21:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38468 | ICPIM-28890 Connectors and Cable Types: Connection Rules | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Invalid | 2015-05-19 21:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-38463 | ICPIM-15839 Portfolio - Trace: Add Sub-Class on Web Trace | Tyr (4.2) |  | An Vo | An Vo | Web Client | New | 2015-05-19 20:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-38404 | ICPIM-36779 Import User Accounts - Duplicate username | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Service | Fail | 2015-05-18 01:35 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-38398
Test Case | ICPIM-38265 | ICPIM-35334 Verify that a user cannot delete someone else's report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-05-13 15:34
Test Case | ICPIM-38254 | ICPIM-19999 myDCIM - Reports - Deleting executed reports will also remove reports from myDCIM page | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | Pass | 2015-05-13 12:24
Test Case | ICPIM-38238 | ICPIM-36810 Simple View - Row View: Displays empty row | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-05-12 21:12 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-38132 | ICPIM-38113 Setting up Template Manager | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-05-11 07:26
Test Case | ICPIM-38116 | ICPIM-38113 Failover Equipment Tables | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-05-10 12:32
Test Case | ICPIM-38115 | ICPIM-38113 Failed Equipment Table | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-05-10 12:31
Test Case | ICPIM-38114 | ICPIM-38113 Power Swing Load: Report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-05-10 12:27
Test Case | ICPIM-38109 | ICPIM-38092 Run Future Floor Space Report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | New | 2015-05-10 10:17
Test Case | ICPIM-38108 | ICPIM-38092 Run the Floor Space Report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | New | 2015-05-10 10:17
Test Case | ICPIM-38104 | ICPIM-38092 Verify Database Update manager | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-05-10 09:41
Test Case | ICPIM-38103 | ICPIM-38092 Verify row data system category | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-05-10 09:38
Test Case | ICPIM-38085 | ICPIM-38084 Define report for asset count to run from a specific LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-05-08 09:11
Test Case | ICPIM-38052 | ICPIM-35576 Manage Role - Clone Default System Role (All Access) |  |  | An Vo | An Vo | Windows Client | Pass | 2015-05-08 00:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-37942 | ICPIM-37941 iPBX TC (iPBX is deprecated) | Ran (4.1) |  | Loan Ha | Loan Ha | Windows Client | Fail | 2015-05-06 14:58 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-37937
Test Case | ICPIM-37930 | ICPIM-37864 Devices are Discovered via SNMP |  |  | Garrett S. | Garrett S. |  | Pass | 2015-05-06 10:30 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100%
Test Case | ICPIM-37929 | ICPIM-37864 Start in Debug |  |  | Garrett S. | Garrett S. |  | Pass | 2015-05-06 10:30 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-37928 | ICPIM-37864 Configure Event - Add a new blank event |  |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2015-05-06 10:30 |  | 3600 | 1200 | 75% |  | 3600 | 1200 | 75%
Test Case | ICPIM-37927 | ICPIM-37864 Configure Agent - Add a new iDiscover range |  |  | Khang Nguyen | Garrett S. | Data Exchange Agent | Pass | 2015-05-06 10:30 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-37926 | ICPIM-37864 Install Agent |  |  | Khang Nguyen | Garrett S. | Data Exchange Agent | Pass | 2015-05-06 10:29 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-37913 | ICPIM-34129 Portfolio - Portfolio view: Image of asset levels 1, 2, 3, 4 | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-05-06 02:40 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-14665, ICPIM-36891, ICPIM-38045
Test Case | ICPIM-37907 | ICPIM-36605 Portfolio - Asset Attributes: Attributes of SKU | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-05-06 02:14 | 1800 | 6000 | 0 | 100% | 1800 | 6000 | 0 | 100% |  | ICPIM-37910
Test Case | ICPIM-37901 | ICPIM-36605 Portfolio - Asset Attributes: Attributes of Physical instance Asset | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-05-06 02:06 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-37890 | ICPIM-36541 Simple View - Space Overlays: For U Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:51 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37889 | ICPIM-39358 Simple View - Space Filters: For U Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:49 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37888 | ICPIM-39358 Simple View - Space Filters: For Row Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:48 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37887 | ICPIM-36541 Simple View - Space Overlays: For Row Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:47 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37886 | ICPIM-36671 Simple View - Thermal Overlays: For U Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37885 | ICPIM-39356 Simple View - Thermal Filters: For U Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:39 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37884 | ICPIM-39356 Simple View - Thermal Filters: For Enclosure Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:38 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37883 | ICPIM-36671 Simple View - Thermal Overlays: For Enclosure Position | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-05-06 00:37 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-37881 | ICPIM-20047 Tasks - Verify Work Action - Bulk Verify WA Tasks | Ran (4.1) |  | An Vo | Phuong Phan | Web Client | Pass | 2015-05-06 00:24 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-37855 | ICPIM-35334 Confirm that a user with no LOB will see all reports | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-05-05 15:44
Test Case | ICPIM-37854 | ICPIM-37275 Confirm report access of descendant LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-05-05 15:29
Test Case | ICPIM-37824 | ICPIM-39352 Simple View - Power Filters: For U Position (on Cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 03:58 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37823 | ICPIM-39352 Simple View - Power Filters: For Port (on Cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 03:56 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37822 | ICPIM-39352 Simple View - Power Filters: For Modules (on Cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 03:54 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37821 | ICPIM-39352 Simple View - Power Filters: For Enclosure Position (on Floor) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 03:51 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37820 | ICPIM-39352 Simple View - Power Filters: For Row (On Floor) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 03:47 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37816 | ICPIM-36393 Simple View - Power Overlays: For U Position (on Cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 02:19 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37815 | ICPIM-36393 Simple View - Power Overlays: For Enclosure Position (on Floor) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 02:12 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37811 | ICPIM-36393 Simple View - Power Overlays: For Row (on Floor) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 01:51 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37810 | ICPIM-36393 Simple View - Power Overlays: For Port (in cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 01:49 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37809 | ICPIM-36393 Simple View - Power Overlays: For Modules (In Cabinet) | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-05-05 01:44 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-37805 | ICPIM-39017 Simple View - View States: Thermal View states | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-05-04 23:44 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37764 | ICPIM-37763 Assign a LOB to an asset via Properties dialog | Ran (4.1) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-05-04 01:03 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-35900
Test Case | ICPIM-37756 | ICPIM-35395 Delete a scheduled report that is running |  |  | Donna Daigneault | Donna Daigneault | Web Client | In Progress | 2015-05-02 08:42
Test Case | ICPIM-37740 | ICPIM-37677 Set up Custom Yearly reports | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Fail | 2015-05-01 09:58 | [9 empty] | ICPIM-37871
Test Case | ICPIM-37730 | ICPIM-37677 Set custom weekly using start and end dates | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-04-30 22:27
Test Case | ICPIM-37685 | ICPIM-37677 Daily custom report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-04-29 20:08
Test Case | ICPIM-37676 | ICPIM-35395 Daily Scheduled report |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-29 13:16
Test Case | ICPIM-37652 | ICPIM-37645 Test search filter Attribute | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-04-28 15:46
Test Case | ICPIM-37651 | ICPIM-37645 Test search filter Kind | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-04-28 15:45
Test Case | ICPIM-37649 | ICPIM-37645 Test search Make/Model | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 15:44
Test Case | ICPIM-37648 | ICPIM-37645 Test search filter Type | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-04-28 15:42
Test Case | ICPIM-37647 | ICPIM-37645 Test search filter Location | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | In Progress | 2015-04-28 15:36 | [9 empty] | ICPIM-37716
Test Case | ICPIM-37646 | ICPIM-37645 Test search filter Lines of Business | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 15:32 | [9 empty] | ICPIM-37697
Test Case | ICPIM-37644 | ICPIM-36440 Select the report category from the report category drop down in report wizard | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 14:55
Test Case | ICPIM-37643 | ICPIM-36440 Search report category in Report Wizard Choose Report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 14:44
Test Case | ICPIM-37642 | ICPIM-36440 Search name of report in report wizard choose report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 14:43
Test Case | ICPIM-37636 | ICPIM-36297 Verify that only the assets assigned to a line of business are visible to that user | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-28 12:46 | [9 empty] | ICPIM-37635
Test Case | ICPIM-37635 | ICPIM-36297 Verify that reports will only be run off the assets assigned to the user LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Invalid | 2015-04-28 10:53 | [9 empty] | ICPIM-37636
Test Case | ICPIM-37519 | ICPIM-23308 Displays of Commissioning Search Result when no Analytics data retrieved | All |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-04-24 21:11 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-35850
Test Case | ICPIM-37498 | ICPIM-13471 Prohibit Install on 32bit OS -TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2015-04-24 09:45 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-35678, ICPIM-35400
Test Case | ICPIM-37486 | ICPIM-37402 iLocator - User not belong to any LOB can access all reports | Ran (4.1) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-04-24 03:24 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50% |  | ICPIM-37479
Test Case | ICPIM-37483 | ICPIM-35576 Role - Web Service: mapping of Feature/Permission for Role |  |  | Tien Pham | Tien Pham | Web Service | Pass | 2015-04-24 03:20 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-37471 | ICPIM-35576 Role - Advanced Remote Access: mask out the feature list |  |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-24 02:27 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-37469 | ICPIM-35841 Dynamic Trending - Historical View: Manual refresh | All |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-24 01:45 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-37812
Test Case | ICPIM-37468 | ICPIM-35841 Dynamic Trending - Historical View: Display when no data available in the selected time | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:44 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-37467 | ICPIM-35841 Dynamic Trending - Historical View: Default Historical options | All |  | Tien Pham | Mai Nguyen | Web Client | Fail | 2015-04-24 01:44 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-37969, ICPIM-37981, ICPIM-38280
Test Case | ICPIM-37466 | ICPIM-35841 Dynamic Trending - Historical View: Time selection template | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:43 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-37969, ICPIM-37975, ICPIM-37981
Test Case | ICPIM-37465 | ICPIM-35841 Dynamic Trending - Dynamic View: Display when no data point available | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:41 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37464 | ICPIM-35841 Dynamic Trending - Dynamic View: Display when no new data point on reach Auto-refresh interval | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:40 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-37969
Test Case | ICPIM-37463 | ICPIM-35841 Dynamic Trending - Dynamic View: Display last 10 minutes data point on loaded | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:39 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-37969
Test Case | ICPIM-37462 | ICPIM-35841 Dynamic Trending - Dynamic View: Appearance of new values on Line chart | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-24 01:39 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-37969
Test Case | ICPIM-37461 | ICPIM-35841 Dynamic Trending - Dynamic View: Manual refresh | All |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-24 01:38 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-37812
Test Case | ICPIM-37460 | ICPIM-35841 Dynamic Trending - Dynamic View: Auto-refresh by configuring the Interval | All |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-24 01:37 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37459 | ICPIM-35841 Dynamic Trending - Dynamic view: Auto-refresh interval defaulted to 1 minute for Line chart | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-24 01:36 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-37969
Test Case | ICPIM-37405 | ICPIM-37402 iLocator - Access to a non-existing report | Ran (4.1) |  | Vinh Nguyen | Thuy Tran | Windows Client | Pass | 2015-04-23 02:52 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-37404 | ICPIM-37402 iLocator - Access to report NOT assigned to a LOB | Ran (4.1) |  | Vinh Nguyen | Thuy Tran | Windows Client | Pass | 2015-04-23 02:51 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-37403 | ICPIM-37402 iLocator - Access to report assigned to LOB | Ran (4.1) |  | Vinh Nguyen | Thuy Tran | Windows Client | Pass | 2015-04-23 02:49 | 3000 | 1500 | 1500 | 50% | 3000 | 1500 | 1500 | 50%
Test Case | ICPIM-37400 | ICPIM-39026 Simple View - GUI: Dashboard | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-04-23 01:44 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-37399 | ICPIM-39026 Simple View - GUI: Viewer | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-04-23 01:40 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100% |  | ICPIM-37475
Test Case | ICPIM-37393 | ICPIM-36605 Portfolio - Asset Attributes: Persistent Data store displaying | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 23:31 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-37389 | ICPIM-37314 Portfolio - Home: Perspective on 3D Viewer Image | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-04-22 21:43 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-34720
Test Case | ICPIM-37358 | ICPIM-37314 Portfolio - Home: Hide Portfolio components through server-side configuration | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-22 03:41 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-37356 | ICPIM-37314 Portfolio - Home: Filter charts | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-22 03:38 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-37344 | ICPIM-37332 Remove Flex Flash functionality | Ran (4.1) |  | Trinh Nguyen | Thuy Tran | Windows Client | Pass | 2015-04-22 03:10 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-37384
Test Case | ICPIM-37340 | ICPIM-39026 Simple View - GUI: Share Options | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-04-22 03:06 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-37450
Test Case | ICPIM-37338 | ICPIM-39026 Simple View - GUI: Horizontal Toolbar | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-04-22 03:03 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-37331 | ICPIM-37324 Force Pwd Change via Web: New Password mismatch | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:41 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-37330 | ICPIM-37324 Force Pwd Change via Web: Wrong current password | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:40 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-37532
Test Case | ICPIM-37329 | ICPIM-37324 Force Pwd Change via Web: Global pwd policy: Minimum length | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:39 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-37482
Test Case | ICPIM-37328 | ICPIM-37324 Force Pwd Change via Web: Successful notification | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:38 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-37327 | ICPIM-37324 Force Pwd Change via Web: Change Password's required fields | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:37 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-37316
Test Case | ICPIM-37326 | ICPIM-37324 Force Pwd Change via Web: User successfully changes Pwd | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:30 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-37325 | ICPIM-37324 Force Pwd Change via Web: User quits the change Pwd | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-22 02:29 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-37321 | ICPIM-37262 Web Dictionary - Reset All | Ran (4.1) |  | Thuy Tran | Thuy Tran | Web Client | Pass | 2015-04-22 02:05 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75%
Test Case | ICPIM-37320 | ICPIM-37262 Web Dictionary - Reset Level | Ran (4.1) |  | Thuy Tran | Thuy Tran | Web Client | Pass | 2015-04-22 02:03 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37319 | ICPIM-37262 Web Dictionary - Configure | Ran (4.1) |  | Vinh Nguyen | Thuy Tran | Web Client | Fail | 2015-04-22 02:02 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-37513, ICPIM-37529
Test Case | ICPIM-37313 | ICPIM-13471 Installation - New DLL (ScriptCtl.dll) for iDiscover & Analyzer | All |  | Phuong Phan | Phuong Phan | Windows Client | Invalid | 2015-04-22 00:53 | 2100 | 2100 | 0 | 100% | 2100 | 2100 | 0 | 100% |  | ICPIM-34672
Test Case | ICPIM-37310 | ICPIM-37309 Web UI - 404 Page Error |  |  | Vinh Nguyen | Vinh Nguyen | Web Client | Pass | 2015-04-21 21:20 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-37292 | ICPIM-35384 View Report - Show/Hide columns | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | Pass | 2015-04-21 14:44 | [9 empty] | ICPIM-37289
Test Case | ICPIM-37284 | ICPIM-34750 Install the DEA | All |  | Garrett S. | Garrett S. |  | Pass | 2015-04-21 11:53 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25%
Test Case | ICPIM-37267 | ICPIM-37261 Portfolio - Chart Viewer: New changes in Chart viewer | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-04-21 03:17 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-37266 | ICPIM-37262 Web Dictionary - UI | Ran (4.1) |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-04-21 03:17 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37260 | ICPIM-36605 Portfolio - Asset Attributes: Add tooltips to buttons | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Fail | 2015-04-21 02:56 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-37547, ICPIM-37550
Test Case | ICPIM-37259 | ICPIM-36605 Asset Attributes popup: Filter and Search by Type, Name AND Value | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-21 02:55 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-37254 | ICPIM-36605 Portfolio - Asset Attributes: Anchor popup - Search field | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-21 02:51 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-37239 | ICPIM-12704 Portfolio - Advanced Navigation: Right side icons tooltips | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-21 01:36 | 2100 | 1800 | 300 | 85% | 2100 | 1800 | 300 | 85% |  | ICPIM-37453
Test Case | ICPIM-37238 | ICPIM-37230 Portfolio - Tooltips: Descendants pane tooltips | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-21 01:34 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-37233 | ICPIM-37230 Portfolio - Descendants: Descendant pane appearance | Ran (4.1) |  | Tien Pham | An Vo | Web Client | Pass | 2015-04-21 01:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-37231 | ICPIM-39367 Simple view - Level 9 - Future view: Tooltips | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-21 01:19 | 2100 | 1800 | 300 | 85% | 2100 | 1800 | 300 | 85%
Test Case | ICPIM-37225 | ICPIM-37224 Web Client Access: Unified | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Web Client | Fail | 2015-04-21 00:49 | 1200 | 3600 | 0 | 100% | 1200 | 3600 | 0 | 100% |  | ICPIM-29488
Test Case | ICPIM-37203 | ICPIM-36334 Assign an asset number that will be included in the Panel Owner and Enclosure Owner reports | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-20 16:58 | [9 empty] | ICPIM-36343
Test Case | ICPIM-37202 | ICPIM-36334 Configure Cost Center | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-20 16:50 | [9 empty] | ICPIM-36342
Test Case | ICPIM-37195 | ICPIM-36300 Maximize, minimize, close the View dialog | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-20 16:05
Test Case | ICPIM-37184 | ICPIM-36300 Confirm that the administrator can delete the reports from the view dialog (report belongs to a user) | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-04-20 14:12 | [9 empty] | ICPIM-37180
Test Case | ICPIM-37183 | ICPIM-36300 Confirm that you cannot delete the reports from the view dialog (report does not belong to the user) | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-20 14:11
Test Case | ICPIM-37154 | ICPIM-35613 Connectivity - Connect regular ports to Punch Down | All |  | Thuy Tran | Thuy Tran | Windows Client | Fail | 2015-04-20 02:59 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-37553
Test Case | ICPIM-37153 | ICPIM-35613 Connectivity - Connect regular ports to Multi Connectors | All |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-04-20 02:58 | 1800 | 4800 | 0 | 100% | 1800 | 4800 | 0 | 100% |  | ICPIM-37760
Test Case | ICPIM-37152 | ICPIM-35613 Connectivity - Connect Punch Downs to Punch Downs | All |  | An Vo | Thuy Tran | Windows Client | Fail | 2015-04-20 02:57 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-37535
Test Case | ICPIM-37149 | ICPIM-39442 Change strings on myDCIM Page | Ran (4.1) |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-20 02:54 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-37142 | ICPIM-35870 Manage Event Action Script: Remove Action Script | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-04-20 01:44 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37141 | ICPIM-36605 Portfolio - Asset Attributes: Floating point values | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-20 01:35 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-37145
Test Case | ICPIM-37139 | ICPIM-35870 Manage Event Action Script: Configure Action Script | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-04-20 01:29 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37138 | ICPIM-35870 Manage Event Action Script: Clone Action Script | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-04-20 01:28 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-37136 | ICPIM-35870 Manage Events - Add Event Action: Visual Filter Data Collection | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:23
Test Case | ICPIM-37135 | ICPIM-35870 Manage Events - Add Event Action: System Maintenance | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:23
Test Case | ICPIM-37134 | ICPIM-35870 Manage Events - Add Event Action: Syslog Message | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:23
Test Case | ICPIM-37133 | ICPIM-35870 Manage Events - Add Event Action: Run Application | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:23
Test Case | ICPIM-37132 | ICPIM-35870 Manage Events - Add Event Action: Picture | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:22
Test Case | ICPIM-37131 | ICPIM-35870 Manage Events - Add Event Action: Email | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:22
Test Case | ICPIM-37130 | ICPIM-35870 Manage Events - Add Event Action: Data Source Mapping Email | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:22
Test Case | ICPIM-37129 | ICPIM-35870 Manage Events - Add Event Action: Change Control | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:21
Test Case | ICPIM-37128 | ICPIM-35870 Manage Events - Add Event Action: Automatic Database Backup | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-20 01:21
Test Case | ICPIM-37124 | ICPIM-37122 Simple View - Web Rulers: Functionalities | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-20 01:07 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-37123 | ICPIM-37122 Simple View - Web Rulers: Ruler button color | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-20 01:05 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-37103 | ICPIM-36300 Confirm the auto-refresh button | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-17 15:29
Test Case | ICPIM-37102 | ICPIM-36300 Confirm that you can delete the reports from the view dialog (report belongs to the user) | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-17 15:29
Test Case | ICPIM-37101 | ICPIM-36300 Confirm that you can filter the reports | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-17 15:29
Test Case | ICPIM-37100 | ICPIM-36300 Verify that the administrator can view all the reports that were run | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-17 15:28
Test Case | ICPIM-37099 | ICPIM-36300 Verify that administrator can see all reports that were run | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-17 15:27 | [9 empty] | ICPIM-37051
Test Case | ICPIM-37098 | ICPIM-35395 Verify emailing a report from the scheduled report path |  |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-04-17 15:13 | [9 empty] | ICPIM-36134
Test Case | ICPIM-37097 | ICPIM-35395 Confirm that you can delete a report schedule |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-17 14:55
Test Case | ICPIM-37013 | ICPIM-30248 CSV Import: modification on Row and Enclosure files to support Row Position | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-04-17 02:56 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25% |  | ICPIM-37045, ICPIM-34827
Test Case | ICPIM-37005 | ICPIM-37000 Database Update - Work Action post conversion | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Fail | 2015-04-17 00:55 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36941
Test Case | ICPIM-37004 | ICPIM-37000 Database Update - Update Row Positions for Enclosure Pad row | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-17 00:54 | 2100 | 3300 | 0 | 100% | 2100 | 3300 | 0 | 100% |  | ICPIM-37048
Test Case | ICPIM-37003 | ICPIM-37000 Database Update - Update Row Positions for Non-Enclosure Pad row | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-17 00:54 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-37048
Test Case | ICPIM-37002 | ICPIM-37000 Database Update - Convert single or multiple Equipment Rooms to use Row Position | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-17 00:54 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-36980 | ICPIM-28308 Run Analytics Space for Row Position | Ran (4.1) |  | Tien Pham | Tien Pham | Analytics | Pass | 2015-04-16 21:12 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-36933 | ICPIM-33977 Commission Enclosure to Row Position - Work Action recorded for Row Position | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Fail | 2015-04-16 05:56 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-36941
Test Case | ICPIM-36925 | ICPIM-33977 Commission Enclosure to Row Position - The Placement options in Workflow mechanism | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Fail | 2015-04-16 04:02 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-36928
Test Case | ICPIM-36924 | ICPIM-39367 Simple View - Cabinet View: Change Request details in Future view | Ran (4.1) |  | An Vo | Phuong Phan | Web Client | Invalid | 2015-04-16 03:44 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-37917, ICPIM-35989, ICPIM-36128
Test Case | ICPIM-36923 | ICPIM-33977 Commission Enclosure to Row Position - The Placement options in Group base mechanism | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-16 03:32 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-36922 | ICPIM-39367 Simple View - Cabinet View: Visualize/display objects in Future view | Ran (4.1) |  | Khang Nguyen | Phuong Phan | Web Client | Fail | 2015-04-16 03:26 | 3000 | 1800 | 1200 | 60% | 3000 | 1800 | 1200 | 60% |  | ICPIM-35989, ICPIM-36128, ICPIM-37956, ICPIM-37966
Test Case | ICPIM-36921 | ICPIM-39367 Simple View - Cabinet View: Future view Colorization | Ran (4.1) |  | An Vo | Phuong Phan | Web Client | Fail | 2015-04-16 03:20 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66% |  | ICPIM-38155, ICPIM-35989, ICPIM-36128, ICPIM-37956, ICPIM-38353
Test Case | ICPIM-36920 | ICPIM-39367 Simple View - Cabinet View: Future view | Ran (4.1) |  | Khang Nguyen | Phuong Phan | Web Client | Pass | 2015-04-16 03:05 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-36128
Test Case | ICPIM-36915 | ICPIM-36809 Simple View - Floor View: Display CR Details info for affected item | Ran (4.1) |  | Tien Pham | Phuong Phan | Windows Client | Invalid | 2015-04-16 02:53 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75% |  | ICPIM-26361, ICPIM-35989
Test Case | ICPIM-36914 | ICPIM-36809 Simple View - Floor View: GUI | Ran (4.1) |  | Vinh Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-16 02:51 | 2100 | 1500 | 600 | 71% | 2100 | 1500 | 600 | 71%
Test Case | ICPIM-36913 | ICPIM-39017 Simple View - View States: LOB View state for Row Position | Ran (4.1) |  | Phuong Phan | Vinh Nguyen | Web Client | Pass | 2015-04-16 02:34 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-36947
Test Case | ICPIM-36912 | ICPIM-36390 Simple View - Module View: Auto completed decommission | Ran (4.1) |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-04-16 02:28 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-36128
Test Case | ICPIM-36911 | ICPIM-36670 Simple View - Panel View: Auto completed decommission | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-16 02:25 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36910 | ICPIM-36390 Simple View - Module View: Scheduled decommission | Ran (4.1) |  | An Vo | Khang Nguyen | Web Client | Pass | 2015-04-16 02:18 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-36128
Test Case | ICPIM-36909 | ICPIM-36670 Simple View - Panel View: Scheduled decommission | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-16 02:13 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36908 | ICPIM-39017 Simple View - View States: LOB View state for Cabinet | Ran (4.1) |  | Thuy Tran | Vinh Nguyen | Web Client | Pass | 2015-04-16 02:11 | 1200 | 2700 | 0 | 100% | 1200 | 2700 | 0 | 100% |  | ICPIM-36947, ICPIM-40208
Test Case | ICPIM-36907 | ICPIM-39361 Simple View - Lines of Business Overlays | Ran (4.1) |  | An Vo | Vinh Nguyen | Web Client | Pass | 2015-04-16 01:45 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-38188, ICPIM-36947
Test Case | ICPIM-36906 | ICPIM-39017 Simple View - View States: Edit Viewstates | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:31 | 3000 | 3600 | 0 | 100% | 3000 | 3600 | 0 | 100%
Test Case | ICPIM-36903 | ICPIM-39365 Simple View - Filters: Remove Filters | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:29 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36902 | ICPIM-39365 Simple View - Filters: Edit Filters | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:27 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-36901 | ICPIM-39365 Simple View - Filters: Add Filters | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:26 | 2400 | 3600 | 0 | 100% | 2400 | 3600 | 0 | 100%
Test Case | ICPIM-36900 | ICPIM-39366 Simple View - Overlays: Remove Overlay | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:25 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36899 | ICPIM-39366 Simple View - Overlays: Edit Ovelay | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:24 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-36898 | ICPIM-39366 Simple View - Overlays: Add Ovelay | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-16 01:23 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75%
Test Case | ICPIM-36897 | ICPIM-39367 Simple view - Level 8 - Future view: "Auto Complete" Decommission | Ran (4.1) |  | An Vo | Thuy Tran | Web Client | Pass | 2015-04-16 01:22 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75%
Test Case | ICPIM-36896 | ICPIM-39367 Simple view - Level 8 - Future view: Scheduled Decommission | Ran (4.1) |  | An Vo | Thuy Tran | Web Client | Pass | 2015-04-16 01:21 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-36895 | ICPIM-36881 Simple View - LOB Filters: Filter Asset with no LOB assigned | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-04-16 01:15 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100% |  | ICPIM-36947
Test Case | ICPIM-36894 | ICPIM-36881 Simple View - LOB Filters: Filter Asset with LOB assigned | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-04-15 23:22 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-36947
Test Case | ICPIM-36875 | ICPIM-36390 Simple View - Module View: Auto completed commission | Ran (4.1) |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-04-15 19:37 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36874 | ICPIM-36390 Simple View - Module View: Scheduled Commission | Ran (4.1) |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-04-15 19:34 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36128, ICPIM-37874
Test Case | ICPIM-36850 | ICPIM-36334 Configure datastore as per Meta data requirements | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-15 10:33
Test Case | ICPIM-36849 | ICPIM-36334 Configure LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-15 10:32
Test Case | ICPIM-36835 | ICPIM-36390 Simple View - Module View: Tooltip | Ran (4.1) |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-04-15 04:42 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36834 | ICPIM-36379 Row Position: Configure the Position Size to keep all enclosures not fit within the Row | Ran (4.1) |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-15 04:40 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-37048
Test Case | ICPIM-36831 | ICPIM-36390 Simple View - Module View: View Trace | Ran (4.1) |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-04-15 04:39 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36826 | ICPIM-36390 Simple View - Module View: View Asset Attributes | Ran (4.1) |  | Phuong Phan | Khang Nguyen | Web Client | Pass | 2015-04-15 04:31 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36825 | ICPIM-39367 Simple view - Level 11 - Future view: Corresponding highlight | Ran (4.1) |  | Phuong Phan | Khang Nguyen | Web Client | Pass | 2015-04-15 04:28 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36824 | ICPIM-39367 Simple view - Level 11 - Future view: Immediate Connection | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-15 04:26 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-36128
Test Case | ICPIM-36823 | ICPIM-39367 Simple view - Level 11 - Future view: Scheduled Connection | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-15 04:24 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-36128
Test Case | ICPIM-36818 | ICPIM-39367 Simple view - Level 8 - Future view: Corresponding highlight | Ran (4.1) |  | Thuy Tran | Thuy Tran | Web Client | Pass | 2015-04-15 03:29 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-36817 | ICPIM-39367 Simple view - Level 8 - Future view: "Auto Complete" Commission | Ran (4.1) |  | An Vo | Thuy Tran | Web Client | Pass | 2015-04-15 03:27 | 3600 | 3900 | 0 | 100% | 3600 | 3900 | 0 | 100%
Test Case | ICPIM-36816 | ICPIM-39367 Simple view - Level 8 - Future view: Scheduled Commission | Ran (4.1) |  | An Vo | Thuy Tran | Web Client | Pass | 2015-04-15 03:25 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-36815 | ICPIM-36810 Simple View - Row View: Filter options | Ran (4.1) |  | Thuy Tran | Thuy Tran | Web Client | Pass | 2015-04-15 03:22 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75%
Test Case | ICPIM-36812 | ICPIM-36810 Simple View - Row View: Descendants' context menu | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-15 03:19 | 2400 | 3000 | 0 | 100% | 2400 | 3000 | 0 | 100%
Test Case | ICPIM-36811 | ICPIM-36810 Simple View - Row View: View the asset | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-15 03:13 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-36804 | ICPIM-36797 Commission to Row Position: Validate value for Row Position field | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-15 01:40 | 3600 | 5700 | 0 | 100% | 3600 | 5700 | 0 | 100% |  | ICPIM-37953
Test Case | ICPIM-36803 | ICPIM-36797 Commission to Row Position: Specify Row Position - Move CR | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-15 01:40 | 3600 | 1500 | 2100 | 41% | 3600 | 1500 | 2100 | 41%
Test Case | ICPIM-36802 | ICPIM-36797 Commission to Row Position: Specify Row Position - Install CR | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-15 01:39 | 3600 | 600 | 3000 | 16% | 3600 | 600 | 3000 | 16% |  | ICPIM-38288
Test Case | ICPIM-36801 | ICPIM-36797 Commission to Row Position: Anywhere - Move CR | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-15 01:39 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-36800 | ICPIM-36797 Commission to Row Position: Anywhere - Install CR | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-15 01:38 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50% |  | ICPIM-38288
Test Case | ICPIM-36795 | ICPIM-34033 Create Tile Grid for existing Datacenter that has Tile grid configured | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-15 01:22 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-36794 | ICPIM-36670 Simple View - Panel View: Auto completed comission | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-15 00:06 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36793 | ICPIM-36670 Simple View - Panel View: Scheduled Comission | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-15 00:03 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36792 | ICPIM-36790 Clone user account - with assignment | Ran (4.1) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-04-14 23:42 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100%
Test Case | ICPIM-36791 | ICPIM-36790 Clone user account - without assignment | Ran (4.1) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-04-14 23:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-36789 | ICPIM-36774 Associating Cost Centers to LOB | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-04-14 23:28 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100%
Test Case | ICPIM-36788 | ICPIM-36786 Overwrite Export File | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-14 22:40 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-36787 | ICPIM-36786 Export Users | Ran (4.1) |  | Mai Nguyen | Phuong Phan | Windows Client | Fail | 2015-04-14 22:33 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-36935, ICPIM-36938, ICPIM-36944, ICPIM-38395
Test Case | ICPIM-36785 | ICPIM-36779 Import User Accounts - Not Match User ID& User Name | Ran (4.1) |  | Mai Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-14 22:30 | 2700 | 3300 | 0 | 100% | 2700 | 3300 | 0 | 100% |  | ICPIM-36981
Test Case | ICPIM-36784 | ICPIM-36779 Import User Accounts - Match ID/Name | Ran (4.1) |  | Mai Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-14 22:29 | 2700 | 4500 | 0 | 100% | 2700 | 4500 | 0 | 100% |  | ICPIM-36981
Test Case | ICPIM-36783 | ICPIM-36774 Associating Users to LOB | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-04-14 22:01 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100%
Test Case | ICPIM-36782 | ICPIM-36779 Import User Accounts - Invalid Assignments | Ran (4.1) |  | Mai Nguyen | Phuong Phan | Windows Client | Fail | 2015-04-14 21:50 | 1800 | 4500 | 0 | 100% | 1800 | 4500 | 0 | 100% |  | ICPIM-36984, ICPIM-38401
Test Case | ICPIM-36781 | ICPIM-36779 Import User Accounts - Import with Invalid Format File | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-14 21:49 | 2400 | 1800 | 600 | 75% | 2400 | 1800 | 600 | 75% |  | ICPIM-36950
Test Case | ICPIM-36780 | ICPIM-36779 Import User Accounts - Import through Client - valid import file | Ran (4.1) |  | Mai Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-14 21:49 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-36981
Test Case | ICPIM-36778 | ICPIM-36775 Dialog Access/Permissions - a User with User Account Management privileges | Ran (4.1) |  | Phuong Phan | Phuong Phan | Windows Client | Fail | 2015-04-14 21:43 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-37029
Test Case | ICPIM-36777 | ICPIM-36775 Dialog Access/Permissions - a User without User Account Management privileges | Ran (4.1) |  | Vinh Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-14 21:42 | 1500 | 3000 | 0 | 100% | 1500 | 3000 | 0 | 100% |  | ICPIM-37026
Test Case | ICPIM-36776 | ICPIM-36775 Dialog Access/Permissions - Administrator account | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-14 21:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-36749 | ICPIM-36390 Simple View - Module View: Filter | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:52 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-36128
Test Case | ICPIM-36748 | ICPIM-35105 Invalid sub-task | Ran (4.1) |  | Khang Nguyen | Khang Nguyen |  | Invalid | 2015-04-14 03:41 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-36745 | ICPIM-36670 Simple View - Panel View: Tooltip | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:38 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-36743 | ICPIM-35421 LOB SLA - Cost per IT Circuit {function not yet implemented} | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-14 03:31
Test Case | ICPIM-36742 | ICPIM-35421 LOB SLA - Cost per Row Position {function not yet implemented} | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-14 03:30
Test Case | ICPIM-36741 | ICPIM-35421 LOB SLA - Cost per kW {function not yet implemented} | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-14 03:30
Test Case | ICPIM-36737 | ICPIM-36670 Simple View - Panel View: View Trace | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Fail | 2015-04-14 03:19 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-36934
Test Case | ICPIM-36736 | ICPIM-36670 Simple View - Panel View: View Asset Attributes | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:17 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-36735 | ICPIM-39367 Simple view - Level 10 - Future view: Corresponding highlight | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:15 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-36734 | ICPIM-39367 Simple view - Level 10 - Future view: "Auto completed" connection | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:13 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36733 | ICPIM-39367 Simple view - Level 10 - Future view: Scheduled connection | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:11 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36732 | ICPIM-36670 Simple View - Panel View: Filter | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:10 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-36731 | ICPIM-36670 Simple View - Panel View: Front View and Rear View | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:08 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-36730 | ICPIM-36670 Simple View - Panel View: Image | Ran (4.1) |  | Khang Nguyen | Khang Nguyen | Web Client | Pass | 2015-04-14 03:05 | 1200 | 3600 | 0 | 100% | 1200 | 3600 | 0 | 100%
Test Case | ICPIM-36729 | ICPIM-36660 Ruler Settings - Tile Grid Ruler Settings in SimpleViewWS | Ran (4.1) |  | Tien Pham | Tien Pham | Web Service | Pass | 2015-04-14 02:55 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-36713 | ICPIM-36605 Asset Attributes popup - LOB view: LOB inherited | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-14 02:31 | 3000 | 5100 | 0 | 100% | 3000 | 5100 | 0 | 100%
Test Case | ICPIM-36711 | ICPIM-36605 Portfolio - Asset Attributes: Sorting by Header | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-14 02:28 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-36710 | ICPIM-36605 Asset Attributes popup: Filter and Search by Type, Name OR Value | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-14 02:24 | 2400 | 5100 | 0 | 100% | 2400 | 5100 | 0 | 100%
Test Case | ICPIM-36709 | ICPIM-36551 Import Team Accounts - Import with Invalid Email Format | Ran (4.1) |  | An Vo | An Vo | Windows Client | Fail | 2015-04-14 02:23 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-36717
Test Case | ICPIM-36708 | ICPIM-36605 Asset Attributes popup: "Web Dictionary" and "All" views | Ran (4.1) |  | Thuy Tran | Thuy Tran | Web Client | Pass | 2015-04-14 02:19 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-35971
Test Case | ICPIM-36707 | ICPIM-36660 Ruler Settings - Configure Label Origin | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client, Windows Client | Fail | 2015-04-14 02:08 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100% |  | ICPIM-39147
Test Case | ICPIM-36696 | ICPIM-24175 Space Overlays/Filters: Add View state with Space Overlays/Filters | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Invalid | 2015-04-14 01:17 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-36695 | ICPIM-39017 Simple View - View States: Add Viewstate with custome Overlays/Filters | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Fail | 2015-04-14 01:16 | 1800 | 4200 | 0 | 100% | 1800 | 4200 | 0 | 100% |  | ICPIM-36128, ICPIM-37894, ICPIM-37891
Test Case | ICPIM-36691 | ICPIM-39356 Simple View - Thermal Filters: Remove filter | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:38 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36690 | ICPIM-39356 Simple View - Thermal Filters: Edit filter | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:38 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-36947
Test Case | ICPIM-36689 | ICPIM-39356 Simple View - Thermal Filters: Add filters | Ran (4.1) |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:37 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-36947
Test Case | ICPIM-36688 | ICPIM-39356 Simple View - Thermal Filters: For Port | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:37 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36687 | ICPIM-39356 Simple View - Thermal Filters: For Module | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:36 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-37069
Test Case | ICPIM-36686 | ICPIM-39356 Simple View - Thermal Filters: For Panel | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:36 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-36685 | ICPIM-39356 Simple View - Thermal Filters: For Enclosures | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:35 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-37062
Test Case | ICPIM-36684 | ICPIM-39356 Simple View - Thermal Filters: For Row | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:35 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-36683 | ICPIM-36671 Simple View - Thermal Overlays: Remove overlay | Ran (4.1) |  | An Vo | Mai Nguyen | Web Client | Pass | 2015-04-14 00:35 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-36682 | ICPIM-36671 Simple View - Thermal Overlays: Edit overlay | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:34 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-36681 | ICPIM-36671 Simple View - Thermal Overlays: Add overlays | Ran (4.1) |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:32 | 1800 | 3300 | 0 | 100% | 1800 | 3300 | 0 | 100% |  | ICPIM-36947
Test Case | ICPIM-36680 | ICPIM-36671 Simple View - Thermal Overlays/Filters: Route refresh data | Ran (4.1) |  | Thuy Tran | Mai Nguyen | Web Client | Pass | 2015-04-14 00:31 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-36128, ICPIM-37036, ICPIM-37037
Test Case | ICPIM-36679 | ICPIM-36671 Simple View - Thermal Overlays: ASHRE Class 1&2 | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:31 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66%
Test Case | ICPIM-36678 | ICPIM-36671 Simple View - Thermal Overlays: For Port | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:30 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-36677 | ICPIM-36671 Simple View - Thermal Overlays: For Module | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:30 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-36676 | ICPIM-36671 Simple View - Thermal Overlays: For Panel | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:29 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-37059
Test Case | ICPIM-36675 | ICPIM-36671 Simple View - Thermal Overlays: For Enclosures | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:29 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-36674 | ICPIM-36671 Simple View - Thermal Overlays: For Row | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:28 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-36673 | ICPIM-39356 Simple View - Thermal Filters: Change color for Enclosure(s) which does NOT have analytics Thermal data stored against | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-14 00:28 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-36128, ICPIM-37877
Test Case | ICPIM-36669 | ICPIM-36660 Ruler Settings - Configure X/Y Axis Start | Ran (4.1) |  | Tien Pham | Tien Pham | Web Client, Windows Client | Pass | 2015-04-13 21:53 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-36668 | ICPIM-36660 Ruler Settings - Open up the Tile Grid Ruler Settings | Ran (4.1) |  | Trinh Nguyen | Tien Pham | Web Client, Windows Client | Pass | 2015-04-13 21:52 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-36738
Test Case | ICPIM-36664 | ICPIM-29891 Access "Manage Lines of Business": Permission | Ran (4.1) |  | An Vo | Vinh Nguyen | Windows Client | Pass | 2015-04-13 20:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-36665
Test Case | ICPIM-36659 | ICPIM-35374 (Place holder) | Ran (4.1) |  | Trinh Nguyen | Khang Nguyen | Windows Client | Invalid | 2015-04-13 19:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-36622
Test Case | ICPIM-36638 | ICPIM-36623 Edit User Account - Secutiry Rights - Management interface for Roles, Lines of Business and Teams | Ran (4.1) |  | An Vo | Phuong Phan |  | Pass | 2015-04-13 04:20 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-36629 | ICPIM-36623 Edit User Account - Edit Assignment | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 04:14 | 3300 | 1200 | 2100 | 36% | 3300 | 1200 | 2100 | 36%
Test Case | ICPIM-36628 | ICPIM-36623 Edit User Account - Edit Account name - Duplicated name | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 04:13 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-36627 | ICPIM-36623 Edit User Account - Edit Account detail - Prompt "Would you like to save your change" dialog | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Fail | 2015-04-13 04:12 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66% |  | ICPIM-37006
Test Case | ICPIM-36626 | ICPIM-36623 Edit User Account - Edit Account detail | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Fail | 2015-04-13 04:08 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-37006
Test Case | ICPIM-36621 | ICPIM-36615 Line of Business Data Conversion Utility | Ran (4.1) |  | Trinh Nguyen | Trinh Nguyen |  | Pass | 2015-04-13 04:03 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-36630
Test Case | ICPIM-36617 | ICPIM-34035 Import Tile Grid: The Row Position default size and Ruler Settings | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-13 03:46 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-36611 | ICPIM-29891 Edit a Line of Business item | Ran (4.1) |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2015-04-13 03:40 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36620, ICPIM-36631
Test Case | ICPIM-36606 | ICPIM-36605 Asset Attributes popup: "Line Of Business" view | Ran (4.1) |  | Tien Pham | Thuy Tran | Web Client | Pass | 2015-04-13 03:31 | 2400 | 6000 | 0 | 100% | 2400 | 6000 | 0 | 100% |  | ICPIM-36616, ICPIM-24143, ICPIM-27593, ICPIM-35973
Test Case | ICPIM-36604 | ICPIM-34036 Export Tile Grid: The Default Row Position and Ruler settings | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-13 03:03 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-36592 | ICPIM-29888 Clone an LOB | All |  | An Vo | Vinh Nguyen | Windows Client | Pass | 2015-04-13 01:35 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-36596
Test Case | ICPIM-36591 | ICPIM-36584 Remove User Accounts - in bulk - Users with assigned single/multiple/all teams | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:33 | 2700 | 1500 | 1200 | 55% | 2700 | 1500 | 1200 | 55%
Test Case | ICPIM-36590 | ICPIM-36584 Remove User Accounts - in bulk - Existing/Just-cloned/Just-created users with Read Only or All Access Role | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:32 | 3300 | 1200 | 2100 | 36% | 3300 | 1200 | 2100 | 36%
Test Case | ICPIM-36589 | ICPIM-36584 Remove User Accounts - Single account - a User with assigned single/multiple teams | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:32 | 2100 | 900 | 1200 | 42% | 2100 | 900 | 1200 | 42%
Test Case | ICPIM-36588 | ICPIM-36584 Remove User Accounts - Single account - Administrator user with All access role | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:31 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-36587 | ICPIM-36584 Remove User Accounts - Single account - Just-created user with Read Only role or Al Access role | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:30 | 2100 | 900 | 1200 | 42% | 2100 | 900 | 1200 | 42%
Test Case | ICPIM-36586 | ICPIM-36584 Remove User Accounts - Single account - Just-cloned user with Read Only role or All Access role | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 01:28 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-36585 | ICPIM-36584 Remove User Accounts - Single account - an existing user with Read Only role or All Access role | Ran (4.1) |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-04-13 01:27 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-36580 | ICPIM-36570 Edit Team - Manage Users | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:50 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-36579 | ICPIM-36570 Edit Team - Unassign User(s) | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:49 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-36576 | ICPIM-36572 LOB - Find an LOB | Ran (4.1) |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-04-13 00:48 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-36575 | ICPIM-36570 Edit Team - Assign User(s) | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:47 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-36573 | ICPIM-36570 Edit Team - # Work Actions | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:46 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36692
Test Case | ICPIM-36571 | ICPIM-36570 Edit Team - Edit information | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:45 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-36566 | ICPIM-36551 Import Team Accounts - Not Match ID&Name | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:37 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-36565 | ICPIM-36551 Import Team Accounts - Match ID/Name | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:35 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-36564 | ICPIM-36551 Import Team Accounts - Import with Invalid Users | Ran (4.1) |  | An Vo | An Vo | Windows Client | Fail | 2015-04-13 00:34 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-36712
Test Case | ICPIM-36563 | ICPIM-39358 Simple View - Space Filters: Remove filter | Ran (4.1) |  | Thuy Tran | Mai Nguyen | Web Client | Fail | 2015-04-13 00:34 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-36128, ICPIM-37042
Test Case | ICPIM-36562 | ICPIM-39358 Simple View - Space Filters: Edit filter | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:33 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36561 | ICPIM-39358 Simple View - Space Filters: Add filters | Ran (4.1) |  | Thuy Tran | Mai Nguyen | Web Client | Pass | 2015-04-13 00:33 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-36128, ICPIM-36947
Test Case | ICPIM-36560 | ICPIM-36551 Import Team Accounts - Import with Invalid Format File | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:32 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-36559 | ICPIM-39358 Simple View - Space Filters: For Port | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:32 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-36558 | ICPIM-39358 Simple View - Space Filters: Module | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:32 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36557 | ICPIM-39358 Simple View - Space Filters: For Panel | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:31 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36556 | ICPIM-36551 Import Team Accounts - Import through Client | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-13 00:31 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-36555 | ICPIM-39358 Simple View - Space Filters: For Enclosures | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:30 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36554 | ICPIM-39358 Simple View - Space Filters: For Row | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:30 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36553 | ICPIM-36541 Simple View - Space Overlays: Remove overlay | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:29 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-37042
Test Case | ICPIM-36552 | ICPIM-36541 Simple View - Space Overlays: Edit overlay | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:29 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36550 | ICPIM-36541 Simple View - Space Overlays: Add overlays | Ran (4.1) |  | Thuy Tran | Mai Nguyen | Web Client | Pass | 2015-04-13 00:28 | 1800 | 3300 | 0 | 100% | 1800 | 3300 | 0 | 100% |  | ICPIM-36128, ICPIM-36947
Test Case | ICPIM-36549 | ICPIM-36541 Simple View - Space Overlays/Filters: Route refresh data | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:27 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-36128, ICPIM-37036, ICPIM-37037
Test Case | ICPIM-36548 | ICPIM-36541 Simple View - Space Overlays: For Port | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:25 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-36547 | ICPIM-36541 Simple View - Space Overlays: For Module | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:24 | 1800 | 2160 | 540 | 80% | 1800 | 2160 | 540 | 80%
Test Case | ICPIM-36546 | ICPIM-36541 Simple View - Space Overlays: For Panel | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:24 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36545 | ICPIM-36541 Simple View - Space Overlays: For Enclosures | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:23 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-36544 | ICPIM-36541 Simple View - Space Overlays: For Row | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:23 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36543 | ICPIM-39358 Simple View - Space Filters: Change color for Enclosure(s) which does NOT have analytics Space data stored against | Ran (4.1) |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-13 00:22 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-36128, ICPIM-37877
Test Case | ICPIM-36542 | ICPIM-39026 Simple View - GUI: Not show colorization for hidden object | Ran (4.1) |  | Tien Pham | Mai Nguyen | Web Client | Pass | 2015-04-13 00:22 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-36128
Test Case | ICPIM-36540 | ICPIM-36356 Create User Account with changing default configuration - Global Password Setting | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 00:06 | 2100 | 1500 | 600 | 71% | 2100 | 1500 | 600 | 71%
Test Case | ICPIM-36539 | ICPIM-36356 Create User Account with changing default configuration - Edit Team - Single Team, Multiple Team, All Team | Ran (4.1) |  | Vinh Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-13 00:05 | 3300 | 1200 | 2100 | 36% | 3300 | 1200 | 2100 | 36%
Test Case | ICPIM-36538 | ICPIM-36356 Create User Account with changing default configuration - Change Login Types - Domain | Ran (4.1) |  | Trinh Nguyen | Phuong Phan | Windows Client | Pass | 2015-04-13 00:04 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-29485
Test Case | ICPIM-36537 | ICPIM-36356 Create User Account with changing default configuration - Change Login Types - Unified | Ran (4.1) |  | Trinh Nguyen | Phuong Phan | Windows Client | Fail | 2015-04-13 00:03 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-29488
Test Case | ICPIM-36536 | ICPIM-36356 Create User Account with changing default configuration - Change Login Types - Default | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 00:02 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-36535 | ICPIM-36356 Create User Account with changing default configuration - Set Lock Account | Ran (4.1) |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-13 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36534 | ICPIM-35401 LOB - Response | Ran (4.1) |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-12 23:50 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-35046
Test Case | ICPIM-36533 | ICPIM-35537 Import Lines of Business: Log entry for individual LOB | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-12 20:41 | 1200 | 600 | 1200 | 33% | 1200 | 600 | 1200 | 33%
Test Case | ICPIM-36516 | ICPIM-36514 Remove Team | Ran (4.1) |  | An Vo | An Vo | Windows Client | Pass | 2015-04-12 20:13 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-36451 | ICPIM-36440 Test the Next button | Ran (4.1) |  | Donna Daigneault | Donna Daigneault |  | Pass | 2015-04-10 16:52 | [9 empty] | ICPIM-36442
Test Case | ICPIM-36442 | ICPIM-36440 Test the back button on the report wizard | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-10 15:47 | [9 empty] | ICPIM-36451
Test Case | ICPIM-36441 | ICPIM-36440 Maximize and minimize the report wizard dialog. | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-10 15:46
Test Case | ICPIM-36413 | ICPIM-36412 Remove 'Cost Centers' tab from 'Configure System' | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 04:18 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100% |  | ICPIM-35995
Test Case | ICPIM-36411 | ICPIM-36394 Legacy 'Web Access' tab is implemented in new interface | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 03:55 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36410 | ICPIM-36379 Row Position: Not able to place an Enclosure to a Row Position of another Enclosure that has just moved outside the row. | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:35 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-36409 | ICPIM-39352 Simple View - Power Filters: Remove filter | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:27 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36408 | ICPIM-39352 Simple View - Power Filters: Edit filter | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:26 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-36407 | ICPIM-39352 Simple View - Power Filters: Add filters | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:26 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36406 | ICPIM-39352 Simple View - Power Filters: For Panels (In Cabinet) | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:25 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-37056
Test Case | ICPIM-36405 | ICPIM-39352 Simple View - Power Filters: For Enclosures (On Floor) | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:25 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-37056
Test Case | ICPIM-36404 | ICPIM-36394 Remove 'Web Access' tab from 'Configure System' | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 03:25 | 180 | 300 | 0 | 100% | 180 | 300 | 0 | 100%
Test Case | ICPIM-36403 | ICPIM-36393 Simple View - Power Overlays: Remove overlay | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:25 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-36402 | ICPIM-36393 Simple View - Power Overlays: Edit overlay | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:24 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36401 | ICPIM-36393 Simple View - Power Overlays: Add overlays | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:24 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-36400 | ICPIM-36393 Simple View - Power Overlays/Filters: Route refresh data | All |  | Mai Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:23 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-36128, ICPIM-37036, ICPIM-37037
Test Case | ICPIM-36399 | ICPIM-36393 Simple View - Power Overlays: For Panels (In Cabinet) | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:23 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-37056
Test Case | ICPIM-36398 | ICPIM-36393 Simple View - Power Overlays: For Enclosures | All |  | Mai Nguyen | Mai Nguyen | Web Client | Fail | 2015-04-10 03:22 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-37056, ICPIM-38359
Test Case | ICPIM-36397 | ICPIM-39352 Simple View - Power Filters: Not change color for Enclosure(s) which does NOT have analytics Space data stored against | All |  | Vinh Nguyen | Mai Nguyen | Web Client | Pass | 2015-04-10 03:22 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-36396 | ICPIM-36390 Simple View - Module View: Top view | Ran (4.1) |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-04-10 03:19 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-36128
Test Case | ICPIM-36391 | ICPIM-36372 Remove Security Rights for Line of business | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 03:14 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36389 | ICPIM-36379 Row Position: Snap to Row Units/Positions | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:10 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36388 | ICPIM-36379 Row Position: Move an Enclosure | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:08 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-36387 | ICPIM-36372 Remove Toolbar | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 03:08 | 180 | 300 | 0 | 100% | 180 | 300 | 0 | 100%
Test Case | ICPIM-36386 | ICPIM-36379 Row Position: Assign a Row Position to a LOB. | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:06 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-36581
Test Case | ICPIM-36385 | ICPIM-36372 Remove Menu Item 'File>Configure>Line of Business' | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 03:05 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36384 | ICPIM-36379 Row Position: User is able to visualize and select Row Position. | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:04 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36383 | ICPIM-35873 Pre-configured Events - iDiscover handling events 2 | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-10 03:04 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36382 | ICPIM-36381 Manage Teams - Dialog Access/Permissions | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-10 03:03 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-36665
Test Case | ICPIM-36380 | ICPIM-36379 Row Position: Configure the Row Position size to keep all enclosures fit within the Row | All |  | Tien Pham | Thuy Tran | Windows Client | Pass | 2015-04-10 03:00 | 2400 | 3600 | 0 | 100% | 2400 | 3600 | 0 | 100% |  | ICPIM-37048
Test Case | ICPIM-36378 | ICPIM-35873 Pre-configured Events - Analyzer Evend Handling: Ports | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-10 02:52 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36377 | ICPIM-35873 Pre-configured Events - Analyzer Evend Handling: Analyzer and Chassis | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-10 02:51 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36376 | ICPIM-36374 Overwrite Export File | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-10 02:48 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-36375 | ICPIM-36374 Export Teams | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-10 02:47 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-36373 | ICPIM-36371 Clone Team | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-10 02:38 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36370 | ICPIM-36354 Move 'Active User Sessions' tab to stand-alone dialog | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2015-04-10 02:34 | 180 | 600 | 0 | 100% | 180 | 600 | 0 | 100%
Test Case | ICPIM-36369 | ICPIM-36368 Create Team | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-10 02:33 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36366 | ICPIM-36356 Create User Account with changing default configuration - Set password\pin - Not Qualify the Minimum password Length rule | All |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-10 02:19 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-36365 | ICPIM-36356 Create User Account with changing default configuration - Set password\pin - Qualify the Minimum password Length rule | All |  | Thuy Tran | Phuong Phan | Windows Client | Pass | 2015-04-10 02:17 | 2700 | 2400 | 300 | 88% | 2700 | 2400 | 300 | 88% |  | ICPIM-36796
Test Case | ICPIM-36364 | ICPIM-36356 Create User Account with changing default configuration - Assign a just-create LOB | All |  | Thuy Tran | Phuong Phan | Windows Client | Pass | 2015-04-10 02:16 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100% |  | ICPIM-36796
Test Case | ICPIM-36363 | ICPIM-36356 Create User Account with changing default configuration - Assign an existing LOB | All |  | Thuy Tran | Phuong Phan | Windows Client | Pass | 2015-04-10 02:13 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100% |  | ICPIM-36796
Test Case | ICPIM-36362 | ICPIM-36356 Create User Account with changing default configuration - Assign a just-create Role | All |  | Thuy Tran | Phuong Phan | Windows Client | Pass | 2015-04-10 02:11 | 2100 | 3000 | 0 | 100% | 2100 | 3000 | 0 | 100% |  | ICPIM-36813
Test Case | ICPIM-36361 | ICPIM-36356 Create User Account with changing default configuration - Assign a clone Read Only Role | All |  | Thuy Tran | Phuong Phan | Windows Client | Invalid | 2015-04-10 02:09 | 2100 | 1200 | 900 | 57% | 2100 | 1200 | 900 | 57% |  | ICPIM-36813
Test Case | ICPIM-36360 | ICPIM-36356 Create User Account with changing default configuration - Assign a clone All Access Role | All |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-10 02:06 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-36359 | ICPIM-36356 Create User Account with changing default configuration - Assign All Access System Role | All |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-10 02:03 | 2400 | 1200 | 1200 | 50% | 2400 | 1200 | 1200 | 50%
Test Case | ICPIM-36358 | ICPIM-36356 Create User Account with changing default configuration - Duplicate user name | All |  | An Vo | Phuong Phan | Windows Client | Pass | 2015-04-10 02:01 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-36357 | ICPIM-36356 Create User Account with default configuration | All |  | Thuy Tran | Phuong Phan | Windows Client | Pass | 2015-04-10 02:00 | 2700 | 3000 | 0 | 100% | 2700 | 3000 | 0 | 100% |  | ICPIM-36796
Test Case | ICPIM-36355 | ICPIM-36350 Remove 'Configure Interfaces' dialog | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 01:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-36353 | ICPIM-36350 Remove Security Rights | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 01:09 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36352 | ICPIM-36350 Remove Toolbar | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 00:57 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36351 | ICPIM-36350 Remove Menu Item | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2015-04-10 00:51 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-36349 | ICPIM-35537 Import Lines of Business: Update LOBs | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-04-10 00:01 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-36348 | ICPIM-36347 Manage Cost Centers Permission | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2015-04-09 21:45 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-36665
Test Case | ICPIM-36346 | ICPIM-36345 Edit Cost Center | All |  | Thuy Tran | An Vo | Windows Client | Pass | 2015-04-09 20:43 | 1200 | 3600 | 0 | 100% | 1200 | 3600 | 0 | 100% |  | ICPIM-36661, ICPIM-38129
Test Case | ICPIM-36344 | ICPIM-36334 Clone a Meta data report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:56
Test Case | ICPIM-36343 | ICPIM-36334 Run the *Enclosure Owner Report* | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-04-09 12:22 | [9 empty] | ICPIM-37203
Test Case | ICPIM-36342 | ICPIM-36334 Run the *Panel Owner Report* | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client, Windows Client | Pass | 2015-04-09 12:21 | [9 empty] | ICPIM-36762, ICPIM-36765, ICPIM-37202
Test Case | ICPIM-36341 | ICPIM-36334 Run the *Enclosure Details Report* | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:21
Test Case | ICPIM-36340 | ICPIM-36334 Run the *Panel Details Report* | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:20
Test Case | ICPIM-36339 | ICPIM-36334 Verify that the 'Enclosure Owner' report is present under the "Assets" report category | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:20
Test Case | ICPIM-36338 | ICPIM-36334 Verify that the 'Panel Owner' report is present under the Assets category | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:19
Test Case | ICPIM-36337 | ICPIM-36334 Verify that the Report 'Enclosure Details' is present under the Assets report category | Ran (4.1) |  | Donna Daigneault | Donna Daigneault |  | Pass | 2015-04-09 12:19
Test Case | ICPIM-36336 | ICPIM-36334 Verify that the Report 'Panel Details' exists under the "Assets" category | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:19
Test Case | ICPIM-36335 | ICPIM-36334 Verify that a new Report Category 'Assets' exists | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-09 12:19
Test Case | ICPIM-36333 | ICPIM-35336 Confirm behavior when the favorite allowed correct execution of the report | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 12:08
Test Case | ICPIM-36332 | ICPIM-35336 Confirm behavior when the user has permission but an error occurs, | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-04-09 12:07
Test Case | ICPIM-36331 | ICPIM-35336 Confirm what happens when the report does not exist at the time of execution | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 12:06
Test Case | ICPIM-36330 | ICPIM-35336 Confirm behavior when user does not have permission to execute a report in the favorite | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 12:06
Test Case | ICPIM-36329 | ICPIM-35336 Confirm behavior when executing a report from a favorite | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | Pass | 2015-04-09 12:04 | [9 empty] | ICPIM-37297, ICPIM-38207
Test Case | ICPIM-36328 | ICPIM-19999 myDCIM - Reports - Displays reports associated with User's LOB | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | Pass | 2015-04-09 12:03
Test Case | ICPIM-36327 | ICPIM-35334 Verify ability to change scheduled setting from "Next Run Date" | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Invalid | 2015-04-09 11:47 | [9 empty] | ICPIM-37952
Test Case | ICPIM-36326 | ICPIM-35334 Confirm deleting a report schedule does not delete the instance of the report itself | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 11:45
Test Case | ICPIM-36325 | ICPIM-35334 Confirm that he Reports tab provides the Users with the ability to view the configurations of scheduled reports | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 11:44
Test Case | ICPIM-36324 | ICPIM-35334 Confirm that Non-complete reports should default sorted to the end of the list | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-04-09 11:42 | [9 empty] | ICPIM-36450
Test Case | ICPIM-36323 | ICPIM-35334 Confirm viewing behavior when permissions change | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-04-09 11:38 | [9 empty] | ICPIM-38297
Test Case | ICPIM-36322 | ICPIM-35334 Confirm that a user can access all reports within there LOB even if they did not run them | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-09 11:34
Test Case | ICPIM-36320 | ICPIM-35845 Import Cost Center through the Client | All |  | Tien Pham | An Vo | Windows Client | Pass | 2015-04-09 04:22 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-36125
Test Case | ICPIM-36319 | ICPIM-35845 Import Cost Center with invalid Format/Data | All |  | Tien Pham | An Vo | Windows Client | Pass | 2015-04-09 04:07 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100% |  | ICPIM-36125
Test Case | ICPIM-36302 | ICPIM-36297 Confirm being able to restrict access of a user in the manage (Define reports) | Ran (4.1) |  | Vinh Nguyen | Donna Daigneault | Windows Client | Pass | 2015-04-08 15:51 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-37434
Test Case | ICPIM-36301 | ICPIM-36297 Confirm what reports are viewed in the Job Queue viewer | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-04-08 15:50
Test Case | ICPIM-36299 | ICPIM-36297 LOB filtering Windows client | Ran (4.1) |  | Donna Daigneault | Donna Daigneault |  | New | 2015-04-08 15:37
Test Case | ICPIM-36298 | ICPIM-36297 LOB filtering Web client | Ran (4.1) |  | Donna Daigneault | Donna Daigneault |  | New | 2015-04-08 15:37
Test Case | ICPIM-36296 | ICPIM-35395 Confirm being able to select and delete scheduled reports |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:29 | [9 empty] | ICPIM-37090
Test Case | ICPIM-36294 | ICPIM-35395 Confirm that you only have access to the reports as defined by the user LOB in the schedule report wizard |  |  | Donna Daigneault | Donna Daigneault | Web Client | In Progress | 2015-04-08 15:24
Test Case | ICPIM-36293 | ICPIM-35395 Confirm that you can maximize and minimize the schedule report wizard |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:22 | [9 empty] | ICPIM-36149
Test Case | ICPIM-36292 | ICPIM-35395 Confirm that you can re-execute a scheduled report |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:19 | [9 empty] | ICPIM-36146, ICPIM-36160, ICPIM-36428
Test Case | ICPIM-36291 | ICPIM-35395 Confirm that the scheduled reports are run to completion at the scheduled times |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:17 | [9 empty] | ICPIM-36151
Test Case | ICPIM-36290 | ICPIM-35395 Confirm that you can set up a seeded search from the schedule report wizard |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:14 | [9 empty] | ICPIM-36143
Test Case | ICPIM-36287 | ICPIM-35395 Verify emailing a report of a scheduled report that has been run |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-04-08 15:10 | [9 empty] | ICPIM-36134
Test Case | ICPIM-36203 | ICPIM-35873 Pre-configured Events - System Event Handler: Handling items | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-08 03:23 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36202 | ICPIM-35873 Pre-configured Events - System Event Handler: Handling jobs | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-08 03:19 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36201 | ICPIM-35873 Pre-configured Events - System Event Handler: Historical datastores | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-08 03:18 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36191 | ICPIM-35464 Reports: HTML5 Schedule Report - Report page's GUI | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 03:01
Test Case | ICPIM-36190 | ICPIM-35464 Reports: HTML5 Schedule Report - Remove report instances | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 03:00
Test Case | ICPIM-36189 | ICPIM-35464 Reports: HTML5 Schedule Report - Edit Recurrence | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:59
Test Case | ICPIM-36188 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - Email to User or Team | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:59
Test Case | ICPIM-36187 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - HTML and CSV output formats | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:59
Test Case | ICPIM-36186 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - HTML output format | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:58
Test Case | ICPIM-36185 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - CSV output format | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:57
Test Case | ICPIM-36184 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - No output format | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:57
Test Case | ICPIM-36183 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - Set Favorite | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:56
Test Case | ICPIM-36182 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report - Set filename | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:56
Test Case | ICPIM-36181 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report with Recurrence on customized time | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:55
Test Case | ICPIM-36180 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report with Recurrence on certain days (monthly) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:55
Test Case | ICPIM-36179 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report with Recurrence on certain days (weekly) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:54
Test Case | ICPIM-36178 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report with Recurrence Every day | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:54
Test Case | ICPIM-36177 | ICPIM-35464 Reports: HTML5 Schedule Report - Create Report with Recurrence Once | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:53
Test Case | ICPIM-36176 | ICPIM-35464 Reports: HTML5 Schedule Report - Seed a set of no, one or many assets for a report instance | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-04-08 02:52
Test Case | ICPIM-36172 | ICPIM-36169 Manage LOB | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-08 01:39 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-35992
Test Case | ICPIM-36171 | ICPIM-36169 Unassociate LOB with Cost Center | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-08 01:25 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-36170 | ICPIM-36169 Associate LOB with Cost Center | All |  | An Vo | An Vo | Windows Client | Pass | 2015-04-08 01:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-36168 | ICPIM-35845 Export Cost Center | All |  | Thuy Tran | An Vo | Windows Client | Fail | 2015-04-08 00:35 | 900 | 3000 | 0 | 100% | 900 | 3000 | 0 | 100% |  | ICPIM-36207, ICPIM-37757
Test Case | ICPIM-36118 | ICPIM-35873 Pre-configured Events - Temperature Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:48 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36117 | ICPIM-35873 Pre-configured Events - System Event Handler: Login and Service status | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:47 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36116 | ICPIM-35873 Pre-configured Events - SNMP Trap Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:47 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36115 | ICPIM-35873 Pre-configured Events - Scheduler Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:47 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36114 | ICPIM-35873 Pre-configured Events - Report Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:46 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36113 | ICPIM-35873 Pre-configured Events - Power Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:46 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36112 | ICPIM-35873 Pre-configured Events - Log Entry Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:45
Test Case | ICPIM-36111 | ICPIM-35873 Pre-configured Events - iPBX Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36110 | ICPIM-35873 Pre-configured Events - iDiscover Event Handler 1 | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:44 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36109 | ICPIM-35873 Pre-configured Events - Humidity Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:43 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36108 | ICPIM-35873 Pre-configured Events - Commission Search Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:42 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36107 | ICPIM-35873 Pre-configured Events - Change Control Event Handler: Work Order | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:41 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36106 | ICPIM-35873 Pre-configured Events - Change Control Event Handler: Work Request | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:40 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36105 | ICPIM-35873 Pre-configured Events - Change Control Event Handler: Work Project | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:38 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36104 | ICPIM-35873 Pre-configured Events - Change Control Event Handler: Work Action 2 | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:37 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36103 | ICPIM-35873 Pre-configured Events - Change Control Event Handler: Work Action 1 | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:35 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-36102 | ICPIM-35873 Pre-configured Events - Analyzer Evend Handling: Cards | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:34 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-36101 | ICPIM-35873 Pre-configured Events - Air Pressure Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:33 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36100 | ICPIM-35873 Pre-configured Events - Air Flow Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:32 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36099 | ICPIM-35873 Pre-configured Events - Agent Event Handler | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-04-07 02:30 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-36095 | ICPIM-35576 Role - Read Only - Set permission for Advanced Remote Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Invalid | 2015-04-06 21:58 | [9 empty] | ICPIM-37209
Test Case | ICPIM-36094 | ICPIM-35576 Role - Read Only - Set permission for Advanced GUI Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Invalid | 2015-04-06 21:57 | [9 empty] | ICPIM-37206, ICPIM-37209
Test Case | ICPIM-35937 | ICPIM-35870 Manage Events - Add Event Action: Automated Template Import | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-04-03 02:22
Test Case | ICPIM-35936 | ICPIM-35870 Manage Events - Add Event Handler: Analytics Service | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-04-03 02:20
Test Case | ICPIM-35893 | ICPIM-35562 Export Browser (including syscat columns) |  |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2015-04-02 03:45 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-35903
Test Case | ICPIM-35885 | ICPIM-35872 Configure Events - Configure Event Actions | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-04-02 03:30
Test Case | ICPIM-35884 | ICPIM-35872 Configure Events - Configure Events Handlers | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-04-02 03:29
Test Case | ICPIM-35881 | ICPIM-35872 Configure Events - Configure Events | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2015-04-02 03:28
Test Case | ICPIM-35880 | ICPIM-35870 Manage Events - Import Events | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2015-04-02 03:24 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-37119
Test Case | ICPIM-35879 | ICPIM-35870 Manage Events - Export Events | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2015-04-02 03:24 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83% |  | ICPIM-37119
Test Case | ICPIM-35878 | ICPIM-35870 Manage Events - Remove Events | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2015-04-02 03:23 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-35877 | ICPIM-35870 Manage Events - Edit Events | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2015-04-02 03:22 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-35876 | ICPIM-35870 Manage Events - Add Events | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2015-04-02 03:21 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-35869 | ICPIM-29076 Basic Search - By Line of Business - Add Inherit to Search UI | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2015-04-02 02:27 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-36744
Test Case | ICPIM-35849 | ICPIM-30850 Commission - View Commission Change Control ("Open" group) | All |  | Thuy Tran | Thuy Tran | Windows Client | Pass | 2015-03-31 23:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35848 | ICPIM-30850 Commission - View Commission Change Control ("Completed" group) | All |  | Mai Nguyen | Thuy Tran | Windows Client | Pass | 2015-03-31 23:41 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35847 | ICPIM-31098 Commission - General Configuration Options - Work Project | All |  | Tien Pham | Tien Pham | Windows Client | New | 2015-03-31 21:57 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-35846 | ICPIM-35845 Import Cost Center | All |  | Khang Nguyen | Trinh Nguyen | Windows Client | Fail | 2015-03-31 21:39 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-36125, ICPIM-37799
Test Case | ICPIM-35844 | ICPIM-35841 Dynamic Trending - Historical View: Zooming in the Line chart | All |  | Tien Pham | Trinh Nguyen | Web Client | Pass | 2015-03-31 21:31 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-35843 | ICPIM-35841 Dynamic Trending at Level 10: Dynamic and Historical views | All |  | Tien Pham | Trinh Nguyen | Web Client | Pass | 2015-03-31 21:31 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-37812
Test Case | ICPIM-35842 | ICPIM-35841 Dynamic Trending at Level 9: Dynamic and Historical views | All |  | Vinh Nguyen | Trinh Nguyen | Web Client | Pass | 2015-03-31 21:30 | 1200 | 1920 | 0 | 100% | 1200 | 1920 | 0 | 100% |  | ICPIM-37969
Test Case | ICPIM-35836 | ICPIM-31456 Commission Move using the Commission Editor | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-03-31 20:52
Test Case | ICPIM-35834 | ICPIM-31456 Commission Move using the Viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-03-31 20:51
Test Case | ICPIM-35806 | ICPIM-31098 Commission - General Configuration Options - Staging Area | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-03-31 03:43 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35805 | ICPIM-39375 Application Settings - Temperature Format | All |  | An Vo | Trinh Nguyen | Web Client | Pass | 2015-03-30 20:55 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-35804 | ICPIM-39375 Application Settings - Modify the Numeric format | All |  | Tien Pham | Trinh Nguyen | Web Client | Fail | 2015-03-30 20:54 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-37446
Test Case | ICPIM-35803 | ICPIM-39375 Application Settings - Modify the date format | All |  | Tien Pham | Trinh Nguyen | Web Client | Pass | 2015-03-30 20:53 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-35802 | ICPIM-35799 Web Interface User Profile Configuration - Update User meta-data | All |  | Tien Pham | Trinh Nguyen | Web Client | Pass | 2015-03-30 20:52 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-35801 | ICPIM-37324 Change password from User Profile Settings | All |  | Tien Pham | Trinh Nguyen | Web Client | Fail | 2015-03-30 20:52 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-37245, ICPIM-37250, ICPIM-38119
Test Case | ICPIM-35800 | ICPIM-35799 Web Interface User Profile Configuration - Access User profile page | All |  | Tien Pham | Trinh Nguyen | Web Client | Pass | 2015-03-30 20:51 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-35739 | ICPIM-35174 yan-meeting |  |  | Yan Dai | Yan Dai |  | In Progress | 2015-03-27 08:34 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-35732 | ICPIM-35714 Move a switch from one rack to another utilizing the commission move features -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 15:32 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35731 | ICPIM-35714 Commission a module-TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 15:29 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35730 | ICPIM-35714 Max Hop Verification in Commissioning Server -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 15:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35729 | ICPIM-35714 Commissioning Equipment Block -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 15:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35728 | ICPIM-35714 Commissioning Single Enclosure -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 15:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35727 | ICPIM-35714 Commissioning Enclosures -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35726 | ICPIM-35714 Commissioning multiple items at the same time seeking service -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35722 | ICPIM-35714 Multi-user Decommissioning -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35721 | ICPIM-35714 Multi-user Commission - TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35720 | ICPIM-35714 In-place commission -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35719 | ICPIM-35714 Commission Power to items such as Servers; Switches and Patch Panels –TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:41 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35717 | ICPIM-35714 Commission within a cabinet Seeking Service from the next cabinet (the service does not exist within the selected cabinet) -TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35716 | ICPIM-35714 Seeking Service Commission within the same cabinet - TC | Ran (4.1) |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2015-03-26 14:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35707 | ICPIM-35401 LOB - Color Code | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-26 10:31 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16%
Test Case | ICPIM-35692 | ICPIM-35421 LOB SLA - Set Duration Days | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-25 15:24 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-35980
Test Case | ICPIM-35647 | ICPIM-35645 Web Reporting - Execute modifed report |  |  | Tien Pham | Tien Pham | Web Client | New | 2015-03-24 03:48 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-35646 | ICPIM-35645 Web Reporting - Modify existing report |  |  | Tien Pham | Tien Pham | Web Client | New | 2015-03-24 03:47 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-35644 | ICPIM-29106 Module - Rotate | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:35 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35643 | ICPIM-35613 Connectivity - Log entry | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:34 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-35930
Test Case | ICPIM-35642 | ICPIM-35628 Automatically delete Report - Report older than 45 days |  |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-03-24 03:34
Test Case | ICPIM-35641 | ICPIM-35628 Delete Report - Previously executed reports |  |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-03-24 03:33
Test Case | ICPIM-35640 | ICPIM-35613 Connectivity - Connect Connection Points between 2 Multi Connectors | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:33 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-35933
Test Case | ICPIM-35639 | ICPIM-35628 Permanently Delete Report - Jaspersoft Reports |  |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-03-24 03:32
Test Case | ICPIM-35638 | ICPIM-35628 Permanently Delete Report - Multiple Reports |  |  | Phuong Phan | Phuong Phan | Web Client | New | 2015-03-24 03:32
Test Case | ICPIM-35636 | ICPIM-35628 Remove Report - Remove report files |  |  | An Vo | Phuong Phan | Web Client | New | 2015-03-24 03:31
Test Case | ICPIM-35635 | ICPIM-35613 Connectivity - Connect Multi Connectors that have existing connections | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:31 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-35633 | ICPIM-35628 Remove Report - Remove records in t_reportrequest and t_reportview tables |  |  | An Vo | Phuong Phan | Web Client | New | 2015-03-24 03:31
Test Case | ICPIM-35632 | ICPIM-35628 Remove Report - Scheduled Reports |  |  | An Vo | Phuong Phan | Web Client | New | 2015-03-24 03:31
Test Case | ICPIM-35631 | ICPIM-35613 Connectivity - Adding Multi Connectors - Descendant connection points are listed | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:31 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-35933
Test Case | ICPIM-35630 | ICPIM-35628 Remove Report - Completed Reports |  |  | An Vo | Phuong Phan | Web Client | New | 2015-03-24 03:30
Test Case | ICPIM-35629 | ICPIM-35619 Notification email: Remove CR | Magni |  | Vinh Nguyen | Vinh Nguyen | Web Client | New | 2015-03-24 03:29
Test Case | ICPIM-35627 | ICPIM-35619 Notification email: Team New Assignment(s) | Magni |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-03-24 03:29 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35625 | ICPIM-35619 Notification email: User New Assignment(s) | Magni |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-03-24 03:29 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-35624 | ICPIM-35619 Notification email: Change Request Create | Magni |  | Tien Pham | Vinh Nguyen | Web Client | Pass | 2015-03-24 03:28 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-35623 | ICPIM-35613 Connectivity - Connect 2 Multi Connectors that have different number of Connection Points | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Fail | 2015-03-24 03:28 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100% |  | ICPIM-35890, ICPIM-37972
Test Case | ICPIM-35622 | ICPIM-35613 Connectivity - Connect Multi Connectors that have no Connection Point | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:28 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-35882
Test Case | ICPIM-35621 | ICPIM-34530 Reports - Patch Panel Connectivity (Full Circuit) | All |  | Mai Nguyen | An Vo | Windows Client | New | 2015-03-24 03:27 | [9 empty] | ICPIM-30840
Test Case | ICPIM-35620 | ICPIM-35613 Connectivity - Connect Multi Connectors that have different template | All |  | Thuy Tran | Trinh Nguyen | Windows Client | New | 2015-03-24 03:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35618 | ICPIM-35613 Connectivity - Connect Multi Connectors that have the same template and Connection Points | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:26 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-35616 | ICPIM-34530 Reports - Device Connectivity (Full Circuit) | All |  | Mai Nguyen | An Vo | Windows Client | New | 2015-03-24 03:26 | [9 empty] | ICPIM-29518, ICPIM-22494, ICPIM-26412
Test Case | ICPIM-35615 | ICPIM-35613 Connectivity - Only able to drag and drop Multi Connector (NOT Connection Points) into MultiConnector window | All |  | Thuy Tran | Trinh Nguyen | Windows Client | Pass | 2015-03-24 03:25 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-35614 | ICPIM-35576 Role - Remove All Access - System role |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:24 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35611 | ICPIM-35576 Role - Look and Feel |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:23
Test Case | ICPIM-35610 | ICPIM-35576 Role - Edit (with permission) User Account associations in bulk |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:23 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35609 | ICPIM-35576 Role - View all User Accounts associated |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:23 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35608 | ICPIM-35576 Role - Number of User Accounts associated |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:22 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35607 | ICPIM-35576 Role - Cloned All Access - Set permission for Advanced Remote Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:22
Test Case | ICPIM-35606 | ICPIM-35598 Configure Schema - Add New Fiber Cable Classes To Class Groups |  |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2015-03-24 03:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-35605 | ICPIM-35576 Role - Cloned All Access - Set permission for Advanced GUI Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:21 | [9 empty] | ICPIM-37117
Test Case | ICPIM-35604 | ICPIM-35598 Configure Schema - Add New Fiber Cable Classes To Class Hierachy |  |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2015-03-24 03:21 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-37242
Test Case | ICPIM-35603 | ICPIM-35576 Role - System All Access- Set permission for Advanced Remote Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:21 | [9 empty] | ICPIM-37125, ICPIM-37143
Test Case | ICPIM-35602 | ICPIM-35576 Role - System All Access - Set permission for Advanced GUI Access |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:20 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35600 | ICPIM-35576 Role - Rename |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:20 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35599 | ICPIM-35576 Role - Import,Export Not allow |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:19 |  | 1830 | 0 | 100% |  | 1830 | 0 | 100%
Test Case | ICPIM-35596 | ICPIM-35576 Role - Remove an Existing Role (Includes associated User Accounts) |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:18 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-35595 | ICPIM-35582 DEA - Rack Mount Position supported | All |  | Trinh Nguyen | Trinh Nguyen |  | Invalid | 2015-03-24 03:18
Test Case | ICPIM-35593 | ICPIM-35576 Role - Remove an Existing Role (No associated User Accounts) |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:17 |  | 1830 | 0 | 100% |  | 1830 | 0 | 100%
Test Case | ICPIM-35590 | ICPIM-35576 Role - Clone an Existing Role |  |  | Phuong Phan | Phuong Phan | Windows Client | Pass | 2015-03-24 03:17 |  | 1830 | 0 | 100% |  | 1830 | 0 | 100%
Test Case | ICPIM-35586 | ICPIM-35576 Role - Create a New Role |  |  | Phuong Phan | Phuong Phan | Windows Client | Invalid | 2015-03-24 03:16
Test Case | ICPIM-35585 | ICPIM-35562 Export Browser (without including syscat columns) |  |  | Thuy Tran | An Vo | Windows Client | Pass | 2015-03-24 03:16 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-37114
Test Case | ICPIM-35580 | ICPIM-35562 Browser - Export tab |  |  | An Vo | An Vo | Windows Client | Blocker | 2015-03-24 03:15 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-35900, ICPIM-37765
Test Case | ICPIM-35574 | ICPIM-35562 Browser Export Security Right |  |  | An Vo | An Vo | Windows Client | Blocker | 2015-03-24 03:13 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-36665
Test Case | ICPIM-35570 | ICPIM-35559 Connectivity - Circuit ID: importing Circuit ID using CSV | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35569 | ICPIM-35559 Connectivity - Circuit ID: Advanced Search | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35567 | ICPIM-35559 Connectivity - Circuit ID: Basic Search | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:11 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35566 | ICPIM-35559 Connectivity - Circuit ID: Work Orders | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35565 | ICPIM-35559 Connectivity - Circuit ID: Tracing | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35563 | ICPIM-35559 Connectivity - Circuit ID: Add Circuit ID | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2015-03-24 03:10 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35553 | ICPIM-39591 Commission - Configure Commission Power: "Route To" drop-down | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-03-24 03:03 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-35550 | ICPIM-35539 Commission - Configure Commission Network: "Service Type" drop-down | All |  | Tien Pham | Tien Pham | Web Client | New | 2015-03-24 03:02 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-35549 | ICPIM-35544 User deselects a resource - Quickly deselect resources | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 03:01 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35547 | ICPIM-35544 User deselects a resource - aggregated graphical chart updated | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 03:01 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35545 | ICPIM-35537 Export via CSV: Line of Business | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-03-24 03:01 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-35866
Test Case | ICPIM-35542 | ICPIM-35537 Import Lines of Business: Create LOBs | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-03-24 03:00 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-35540 | ICPIM-35544 User selects a resource growth rate | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:59 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35534 | ICPIM-35544 User selects another resource - Quickly selects multiple resources | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35533 | ICPIM-35544 User selects another resource - Updates the aggregated graphical chart | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35532 | ICPIM-35544 User selects another resource - Treat resource selection in a toggle fashion | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35529 | ICPIM-35544 Web client loads the single resource capacity graphical chart | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35524 | ICPIM-35544 Web client loads the aggregated resource graphical chart - ceiling line | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35523 | ICPIM-35462 User with non-Root LOB - Associate Assets | All |  | Thuy Tran | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:52 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-35989, ICPIM-36122
Test Case | ICPIM-35522 | ICPIM-35544 Web client loads the aggregated resource graphical chart - Months of data, Percent of Rating | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35520 | ICPIM-35462 User with non-Root LOB - Commission Search | All |  | Thuy Tran | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:51 | 900 | 3000 | 0 | 100% | 900 | 3000 | 0 | 100% |  | ICPIM-35989, ICPIM-36122
Test Case | ICPIM-35517 | ICPIM-35462 User with non-Root LOB - Quick Search | All |  | Thuy Tran | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:50 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-35516 | ICPIM-35544 Selects a resource - Selection and deselection | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:50 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35515 | ICPIM-35544 Selects a resource - Graphic chart elements | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35514 | ICPIM-35462 User with non-Root LOB - Advanced search | All |  | Thuy Tran | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:49 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-35989, ICPIM-36122
Test Case | ICPIM-35513 | ICPIM-35544 Web client loads capacity resources - Display of resources | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:49 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35511 | ICPIM-35544 Web client loads capacity resources - No resources selected | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35510 | ICPIM-35544 Web client loads capacity resources - Resources | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:46 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35509 | ICPIM-35544 Web client loads capacity resources - Available resources for forecast | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:45 | 2700 |  | 2700 | 0% | 2700 |  | 2700 | 0%
Test Case | ICPIM-35508 | ICPIM-35462 User is not allowed to login Web client when they have no access to any equipment | All |  | Thuy Tran | Khang Nguyen | Web Client | Pass | 2015-03-24 02:45 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-36122
Test Case | ICPIM-35504 | ICPIM-12704 Portfolio - Advanced Navigation: LOB root access | All |  | Tien Pham | Khang Nguyen | Web Client | Pass | 2015-03-24 02:43 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100%
Test Case | ICPIM-35503 | ICPIM-35544 Web client loads Analytic location - repopulation results of all changes in location | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35502 | ICPIM-35544 Web client loads Analytic location - Save settings | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35500 | ICPIM-35544 Web client loads Analytic location - Make change for Analytic location | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35499 | ICPIM-35544 Web client loads Analytic location - Location loaded, location's name | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-35498 | ICPIM-35462 Restrict Web Access - Assign <None> LOB to admin | All |  | Mai Nguyen | Khang Nguyen | Web Client | Pass | 2015-03-24 02:41 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-37768
Test Case | ICPIM-35496 | ICPIM-30957 View Connections dialog - Select all items by default | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2015-03-24 02:41 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-24388
Test Case | ICPIM-35495 | ICPIM-35462 Direct navigate to URL access of an item | All |  | Khang Nguyen | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:40 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-36128
Test Case | ICPIM-35493 | ICPIM-35491 User selects to reset the simulation | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:40
Test Case | ICPIM-35490 | ICPIM-35462 Asset is associated with a LOB that is descendant of the User LOB | All |  | An Vo | Khang Nguyen | Web Client | Pass | 2015-03-24 02:38 |  | 2700 | 900 | 75% |  | 2700 | 900 | 75% |  | ICPIM-38993
Test Case | ICPIM-35488 | ICPIM-35491 User selects to execute the forecast simulation - 2 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:38
Test Case | ICPIM-35487 | ICPIM-35491 User selects to execute the forecast simulation for capacity percentage - 1 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:37
Test Case | ICPIM-35486 | ICPIM-35462 Data Access defined by the User Account line of Business assignment - Asset has descendants | All |  | Khang Nguyen | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:36 | 900 | 2100 | 0 | 100% | 900 | 2100 | 0 | 100%
Test Case | ICPIM-35485 | ICPIM-35491 User modifies the capacity percentages for available and/or reserved-2 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:36
Test Case | ICPIM-35482 | ICPIM-35491 User selects to execute the forecast simulation for growth rate | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:34
Test Case | ICPIM-35481 | ICPIM-35491 User modifies the resource growth rate for the forecast simulation | All |  | Mai Nguyen | Mai Nguyen |  | New | 2015-03-24 02:32
Test Case | ICPIM-35479 | ICPIM-35491 User selects one of the resource growth percentages - 3 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:29
Test Case | ICPIM-35478 | ICPIM-35491 User selects one of the resource growth percentages - 2 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:28
Test Case | ICPIM-35477 | ICPIM-30842 Define Searches - Schedule option | All |  | Tien Pham | Tien Pham | Windows Client | New | 2015-03-24 02:28 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0% |  | ICPIM-13601
Test Case | ICPIM-35476 | ICPIM-35491 User selects one of the resource growth percentages - 1 | All |  | Mai Nguyen | Mai Nguyen | Web Client | New | 2015-03-24 02:27
Test Case | ICPIM-35473 | ICPIM-35491 Web client loads the aggregated resource graphical chart - 4 | All |  | Mai Nguyen | Mai Nguyen |  | New | 2015-03-24 02:22
Test Case | ICPIM-35472 | ICPIM-35491 Web client loads the aggregated resource graphical chart - 3 | All |  | Mai Nguyen | Mai Nguyen |  | New | 2015-03-24 02:22
Test Case | ICPIM-35471 | ICPIM-35491 Web client loads the aggregated resource graphical chart - 2 | All |  | Mai Nguyen | Mai Nguyen |  | New | 2015-03-24 02:21
Test Case | ICPIM-35470 | ICPIM-35491 Web client loads the aggregated resource graphical chart - 1 | All |  | Mai Nguyen | Mai Nguyen |  | New | 2015-03-24 02:20
Test Case | ICPIM-35466 | ICPIM-35464 Reports: HTML5 Schedule Report - Create multiple instances of the same report | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | New | 2015-03-24 02:13
Test Case | ICPIM-35465 | ICPIM-35462 Data Access defined by the User Account line of Business assignment - Asset has no descendants | All |  | Khang Nguyen | Khang Nguyen | Web Client, Web Service | Pass | 2015-03-24 02:13 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-35459 | ICPIM-35457 Web Login - AD Integration - inauthorized credential | All |  | Mai Nguyen | Trinh Nguyen | Business Logic, Web Client, Web Service | Pass | 2015-03-24 01:30 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100% |  | ICPIM-36877, ICPIM-37897
Test Case | ICPIM-35458 | ICPIM-35457 Web Login - AD Integration - authorized credential | All |  | Mai Nguyen | Trinh Nguyen | Business Logic, Web Client, Web Service | Pass | 2015-03-24 01:28 | 300 | 4200 | 0 | 100% | 300 | 4200 | 0 | 100% |  | ICPIM-36877, ICPIM-37897
Test Case | ICPIM-35452 | ICPIM-35432 Commission - Commission Search result: Reserved Assets tooltip | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 11:00 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35451 | ICPIM-35432 Commission - Commission Search result: Outgoing Assets tooltip | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 11:00 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35450 | ICPIM-35432 Commission - Commission Search result: Incoming Assets tooltip | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 11:00 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35446 | ICPIM-35432 Commission - Commission Search: Commission Results restriction for Module | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:59 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35445 | ICPIM-35432 Commission - Commission Search: Commission Results restriction for Equipment | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:59 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-35444 | ICPIM-35432 Commission - Commission Search: Commission Results restriction for Enclosure | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:58 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-35443 | ICPIM-35432 Commission - Commission Search: Drill-in Search results | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:58 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-35441 | ICPIM-35432 Commission - Commission Search: Displaying Hierarchy | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:58 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-35440 | ICPIM-35432 Commission - Commission Search: Quick Search drop down | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:58 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-35439 | ICPIM-35432 Commission - Commission Search result: Color coded overlay for outgoing assets | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:58 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-35438 | ICPIM-35432 Commission - Commission Search result: Color coded overlay for incoming assets | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:57 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-35437 | ICPIM-35432 Commission - Commission Search result: Color coded overlay for reserved space | Ran (4.1) |  | Tien Pham | Rachna Muthanna | Web Client | New | 2015-03-23 10:57 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-35431 | ICPIM-35374 Associating LOB with >1 User Accounts | Ran (4.1) |  | An Vo | Loan Ha | Windows Client | Pass | 2015-03-23 10:06 | 2100 | 900 | 1200 | 42% | 2100 | 900 | 1200 | 42%
Test Case | ICPIM-35430 | ICPIM-35374 Associating LOB with No User Account | Ran (4.1) |  | An Vo | Loan Ha | Windows Client | Pass | 2015-03-23 10:04 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-35428 | ICPIM-35425 Cost data - Cost per IT Circuit | Ran (4.1) |  | Mai Nguyen | Loan Ha | Windows Client | New | 2015-03-20 16:16 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16% |  | ICPIM-35981
Test Case | ICPIM-35427 | ICPIM-35425 Cost data - Cost per Row Position | Ran (4.1) |  | Mai Nguyen | Loan Ha | Windows Client | New | 2015-03-20 16:15 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-35981
Test Case | ICPIM-35426 | ICPIM-35425 Cost data - Cost per kW | Ran (4.1) |  | Mai Nguyen | Loan Ha | Windows Client | New | 2015-03-20 16:14 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33% |  | ICPIM-35981
Test Case | ICPIM-35424 | ICPIM-35421 LOB SLA - Critical Business Service and Secondary | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:56 | 1800 | 780 | 1020 | 43% | 1800 | 780 | 1020 | 43%
Test Case | ICPIM-35423 | ICPIM-35421 LOB SLA - Maintenance Window(s) | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:55 | 1800 | 780 | 1020 | 43% | 1800 | 780 | 1020 | 43%
Test Case | ICPIM-35422 | ICPIM-35421 LOB SLA - Openings Hours Service | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:54 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-35420 | ICPIM-35401 LOB - Escalation | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-35419 | ICPIM-35401 LOB - Email Address | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-35418 | ICPIM-35401 LOB - Telephone | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:26 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-35417 | ICPIM-35401 LOB - Manager | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:24 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-35416 | ICPIM-35401 LOB - Operational Contact Details | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 15:23 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100% |  | ICPIM-35858
Test Case | ICPIM-35410 | ICPIM-35401 LOB - Owner | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 14:34 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-35405 | ICPIM-35401 LOB - Parent | Ran (4.1) |  | Tien Pham | Loan Ha | Windows Client | Pass | 2015-03-20 14:33 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16%
Test Case | ICPIM-35399 | ICPIM-35395 Confirm that there is no full list flicker |  |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-03-20 13:36
Test Case | ICPIM-35398 | ICPIM-35395 Verify ability to change recurrence of a scheduled report |  |  | Donna Daigneault | Donna Daigneault | Web Client | In Progress | 2015-03-20 13:32
Test Case | ICPIM-35397 | ICPIM-35395 Confirm that the multi-select function is still present and functioning |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 13:30
Test Case | ICPIM-35396 | ICPIM-35395 View list of scheduled reports |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 13:28
Test Case | ICPIM-35394 | ICPIM-35377 Associating Report with LOB (w/ descendants) |  |  | Trinh Nguyen | Loan Ha | Web Client | Pass | 2015-03-20 13:26 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50% |  | ICPIM-35986, ICPIM-36122
Test Case | ICPIM-35393 | ICPIM-35377 Associating Report with LOB (No descendant) |  |  | Trinh Nguyen | Loan Ha | Web Client | Pass | 2015-03-20 13:26 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50% |  | ICPIM-35986, ICPIM-36122
Test Case | ICPIM-35392 | ICPIM-35384 View Reports - View scheduled reports | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | New | 2015-03-20 13:21
Test Case | ICPIM-35391 | ICPIM-35384 View Reports - Sort and filter completed reports list | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | New | 2015-03-20 13:17
Test Case | ICPIM-35390 | ICPIM-35384 View Reports - Expand Report | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | New | 2015-03-20 13:17
Test Case | ICPIM-35389 | ICPIM-35384 View Reports - Select Reports | Ran (4.1) |  | An Vo | Donna Daigneault | Web Client | New | 2015-03-20 13:17
Test Case | ICPIM-35386 | ICPIM-35374 Associating User with a LOB (w/ descendants) | Ran (4.1) |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-03-20 12:45 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-35385 | ICPIM-35374 Associating User with a LOB (No descendant) | Ran (4.1) |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-03-20 12:44 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-35383 | ICPIM-35333 Start with LOB -> remove LOB associated with a user | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-03-20 09:53
Test Case | ICPIM-35382 | ICPIM-35333 Start with no LOB -> assign LOB to a user | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-03-20 09:38
Test Case | ICPIM-35381 | ICPIM-35333 Confirm behavior when the permissions are less restrictive than the last time the report was executed | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 09:35
Test Case | ICPIM-35380 | ICPIM-35333 Confirm behavior when the permissions are more restrictive than the last time the report was executed | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 09:34
Test Case | ICPIM-35379 | ICPIM-35333 Confirm that a user with an associated LOB will not have access to reports run for "everyone" | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 09:26
Test Case | ICPIM-35378 | ICPIM-35333 Confirm access of reports for a user based on an associated LOB with descendant LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-03-20 09:17
Test Case | ICPIM-35376 | ICPIM-35333 Confirm access of reports for a user based on no associated LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 09:15
Test Case | ICPIM-35375 | ICPIM-35333 Confirm access of reports for a user based on the associated LOB | Ran (4.1) |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-20 09:14
Test Case | ICPIM-35370 | ICPIM-34750 Ensure That Data Is Being Written to CPIM Data Stores | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:32 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35369 | ICPIM-34750 Aware Asset is Updated with Model - Generic Asset Exists in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:31 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35368 | ICPIM-34750 Removing Cabinets - Cabinet Exists in Aware | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:31 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35367 | ICPIM-34750 Removing Cabinets - Cabinet DOES NOT Exist in Aware | All |  | Garrett S. | Garrett S. |  | Invalid | 2015-03-19 11:31 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35366 | ICPIM-34750 Adding Cabinets - Cabinet DOES NOT Exist in Aware | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:30 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35365 | ICPIM-34750 Adding Cabinets - Cabinet Exists in Aware | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:30 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35364 | ICPIM-34750 Removed Device Does NOT Exist in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:30 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35363 | ICPIM-34750 Create Decommissioning Tickets in CPIM For Removed Devices | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:29 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35362 | ICPIM-34750 Asset No Longer Exists in Aware | All |  | Garrett S. | Garrett S. |  | Blocker | 2015-03-19 11:26 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35361 | ICPIM-34750 Models Match, Location is NOT Provided by Aware | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:24 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35360 | ICPIM-34750 Location Mismatch | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:23 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35359 | ICPIM-34750 Model/SKU Mismatch | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:23 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35358 | ICPIM-34750 Aware Asset is Missing Both Model and Location Data - Asset is Already Mapped | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:23 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35357 | ICPIM-34750 Aware Asset is Missing Model Information - Asset DOES NOT Exist in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:21 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35356 | ICPIM-34750 Aware Asset is Missing Model Information - Asset Exists in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:21 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35355 | ICPIM-34750 Aware Asset Does Not Have Good Location Data - Asset Does NOT Exist in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:21 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35354 | ICPIM-34750 Aware Asset Does Not Have Good Location Data - Asset Exists in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:20 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35353 | ICPIM-34750 Location Conflict - Generic Panel - Module Shall Throw Location Conflict | All |  | Garrett S. | Garrett S. |  | Blocker | 2015-03-19 11:20 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35352 | ICPIM-34750 Generic Assets - Panels | All |  | Garrett S. | Garrett S. |  | Blocker | 2015-03-19 11:15 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35351 | ICPIM-34750 Location Conflict - Location is Missing in CPIM | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:15 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35350 | ICPIM-34750 SKU Conflict - CPIM is Missing A Matching Library Item | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:15 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35349 | ICPIM-34750 Mapping Assets Between CPIM and Aware - Modules | All |  | Garrett S. | Garrett S. |  | New | 2015-03-19 11:14 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35348 | ICPIM-34750 Mapping Assets Between CPIM and Aware - Panels | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:14 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35347 | ICPIM-34750 Mapping Assets Between CPIM and Aware - Cabinets | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:14 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35346 | ICPIM-34750 Mapping Data Attributes to CPIM Data Stores | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:13 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35345 | ICPIM-34750 Polling Data Attributes from Aware System | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:13 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35344 | ICPIM-34750 Configuring the DEA | All |  | Garrett S. | Garrett S. |  | Pass | 2015-03-19 11:13 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-35328 | ICPIM-34090 Verify the View Status of the report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-17 08:48
Test Case | ICPIM-35252 | ICPIM-34154 Confirm that you can cancel a job in the pending state |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-13 13:37 | [9 empty] | ICPIM-34219
Test Case | ICPIM-35245 | ICPIM-34154 Confirm that you can cancel a job in the processing state |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-13 09:58 | [9 empty] | ICPIM-34219
Test Case | ICPIM-35242 | ICPIM-34154 Confirm that you can cancel deletion of a report in job queue using right click |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-03-13 09:19
Test Case | ICPIM-35241 | ICPIM-34154 Cancel deleting a report from the job queue viewer |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-13 09:15
Test Case | ICPIM-35240 | ICPIM-34154 Delete a report from the job queue using remove report button |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-13 09:10
Test Case | ICPIM-35239 | ICPIM-34157 Run report from browser | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-13 07:46
Test Case | ICPIM-35238 | ICPIM-34900 Run a report on the windows Client and verify that you can retrieve the report from the Web client |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-13 07:01
Test Case | ICPIM-35206 | ICPIM-34152 Confirm that custom reports will appear int he Last used reports list | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-03-12 14:57
Test Case | ICPIM-35205 | ICPIM-34152 Run the custom report that was Imported | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 14:54
Test Case | ICPIM-35204 | ICPIM-34152 Import a custom report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 14:53
Test Case | ICPIM-35203 | ICPIM-34152 Export a custom report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 14:53
Test Case | ICPIM-35202 | ICPIM-34152 Add a custom report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 14:52
Test Case | ICPIM-35197 | ICPIM-34258 Try to delete a standard report category | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 13:54
Test Case | ICPIM-35196 | ICPIM-34258 Select No when deleting a report category | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-03-12 13:49
Test Case | ICPIM-35188 | ICPIM-34900 Execute a saved report |  |  | Donna Daigneault | Donna Daigneault | Web Client | New | 2015-03-12 09:55
Test Case | ICPIM-35183 | ICPIM-34900 Save report to favorites |  |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-03-12 09:50 | [9 empty] | ICPIM-35179
Test Case | ICPIM-35172 | ICPIM-34900 Get data from previously run report. Prior to log on. |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-12 07:09
Test Case | ICPIM-35025 | ICPIM-27431 Portfolio - Dashboard Viewer: MapView "Auto-refresh" | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-03-05 18:10 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-35022 | ICPIM-35021 Dashboard ‘Auto-refresh’ –TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2015-03-05 17:54 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-34951 | ICPIM-34900 Download a report to PDF |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 10:25
Test Case | ICPIM-34950 | ICPIM-34900 Download a report to CSV |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 10:25
Test Case | ICPIM-34949 | ICPIM-34900 Display a report |  |  | Donna Daigneault | Donna Daigneault | Web Client | Fail | 2015-03-04 10:23
Test Case | ICPIM-34946 | ICPIM-34900 email a report |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 09:56
Test Case | ICPIM-34945 | ICPIM-34900 Toggle display (CSV, email, PDF) |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 09:55
Test Case | ICPIM-34944 | ICPIM-34900 Perform a search and run a report |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 09:55
Test Case | ICPIM-34942 | ICPIM-40023 Reexecute Reports - Completed Report |  |  | An Vo | Donna Daigneault | Web Client | Pass | 2015-03-04 09:54
Test Case | ICPIM-34941 | ICPIM-34900 Refetch displayed reports from the reports tab |  |  | Donna Daigneault | Donna Daigneault | Web Client | Pass | 2015-03-04 09:53
Test Case | ICPIM-34923 | ICPIM-34922 Copper option within Commission Search results -TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2015-03-03 11:09 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-34845 | ICPIM-34822 Icon and Menu Security Right "Templates - View Template Manager" | Magni |  | Loan Ha | Loan Ha | Windows Client | Fail | 2015-02-27 15:39 | [9 empty] | ICPIM-34902
Test Case | ICPIM-34844 | ICPIM-34822 View object without a Template | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-27 15:26
Test Case | ICPIM-34843 | ICPIM-34822 View object with a Template | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-27 15:21
Test Case | ICPIM-34842 | ICPIM-34822 Security Right "Templates - View Template Manager" | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-27 14:25
Test Case | ICPIM-34805 | ICPIM-34755 Historical Datastore Collection Log Message | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-25 10:53 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-34790 | ICPIM-34755 Manually Delete Log Message | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-24 15:59 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-34789 | ICPIM-34755 Manually Modify Datastore Log Message (Dictionary) | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-24 15:49 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-34788 | ICPIM-29556 Save the Viewer Search Filters | All |  | Thuy Tran | Loan Ha | Windows Client | Pass | 2015-02-24 15:08 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-34784
Test Case | ICPIM-34787 | ICPIM-34755 Manually Modify Datastore Log Message (Browser) | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-24 14:54 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-34780 | ICPIM-34755 Manually Modify Datastore Log Message (CSV File) | Magni |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2015-02-24 12:50 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34762
Test Case | ICPIM-34774 | ICPIM-34755 Manually Modify Datastore Log Message (Properties -> Set Values) | Magni |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2015-02-24 10:33 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34756
Test Case | ICPIM-34636 | ICPIM-34635 Sync Selection within the Rename tab of the Library Item Catalog –TC | Magni |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2015-02-16 17:40 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-34637, ICPIM-30427
Test Case | ICPIM-34595 | ICPIM-34594 64-bit Activator | Magni |  | Garrett S. | Loan Ha | Windows Client | Pass | 2015-02-13 10:46 | 7200 | 3600 | 3600 | 50% | 7200 | 3600 | 3600 | 50%
Test Case | ICPIM-34593 | ICPIM-34582 Remove "Cache Datastores" option | Magni |  | Loan Ha | Loan Ha | Windows Client | Pass | 2015-02-13 10:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-34577 | ICPIM-34576 Report: Switch to End Device Connectivity (Short Circuit) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-02-13 02:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34575 | ICPIM-34574 Report: Switch Connectivity (Short Circuit) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2015-02-13 02:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34534 | ICPIM-34533 Report - Device Connectivity (Short Circuit) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2015-02-11 23:29 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34571
Test Case | ICPIM-34532 | ICPIM-34524 Search by Temperature - Greater Than | All |  | An Vo | An Vo | Windows Client | Fail | 2015-02-11 22:06 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-34538
Test Case | ICPIM-34531 | ICPIM-34530 Report - Switch Connectivity (Full Circuit) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2015-02-11 21:59 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100% |  | ICPIM-34568, ICPIM-34571, ICPIM-29509
Test Case | ICPIM-34529 | ICPIM-34524 Search by Temperature - Less Than | All |  | An Vo | An Vo | Windows Client | Fail | 2015-02-11 21:35 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-34538
Test Case | ICPIM-34527 | ICPIM-34524 Search by Temperature - Over View | All |  | An Vo | An Vo | Windows Client | Pass | 2015-02-11 20:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-34464 | ICPIM-34156 Run report from system category Current Selection search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-10 10:37 | [9 empty] | ICPIM-34210
Test Case | ICPIM-34463 | ICPIM-34156 Stop the current operation | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-10 09:01 | [9 empty] | ICPIM-34462
Test Case | ICPIM-34462 | ICPIM-34333 Stop a report when it is in the process of running by closing the search report window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-10 08:59 | [9 empty] | ICPIM-34463
Test Case | ICPIM-34461 | ICPIM-34156 Run report from system category Query search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-10 08:35
Test Case | ICPIM-34441 | ICPIM-32538 Decommission - Remove multiple Decommission groups |  |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-09 23:45 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-34440 | ICPIM-32538 Decommission - Remove Decommission (remove Change Control entries) |  |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-09 23:38 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-34420 | ICPIM-18689 Power Capping (Placeholder) | All |  | Garrett S. | Garrett S. | All | Fail | 2015-02-09 12:01 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-34421, ICPIM-34422, ICPIM-34427, ICPIM-18677, ICPIM-20121
Test Case | ICPIM-34411 | ICPIM-27477 imVision DEA Supports a "split server" configuration | All |  | Garrett S. | Garrett S. | Windows Client | New | 2015-02-09 09:39 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-34355 | ICPIM-34333 Run 2 instances of the same report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-02-06 13:25 | [9 empty] | ICPIM-34370
Test Case | ICPIM-34354 | ICPIM-34154 View a report from the job queue window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 13:11
Test Case | ICPIM-34353 | ICPIM-34091 Sort Define Reports windows reports list by Category |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 12:43
Test Case | ICPIM-34352 | ICPIM-34091 Sort Define Reports windows reports list byType |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 12:42
Test Case | ICPIM-34351 | ICPIM-34091 Sort Define Reports windows reports list by Name |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 12:42
Test Case | ICPIM-34345 | ICPIM-34333 Choose not to show the library Id's and confirm they are not shown in the reports |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 08:49
Test Case | ICPIM-34340 | ICPIM-34336 Make sure that you are not able to change the table or class drop downs in standard default reports | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 07:59 | [9 empty] | ICPIM-40262
Test Case | ICPIM-34339 | ICPIM-34336 Edit a standard default report that has been cloned | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 07:41
Test Case | ICPIM-34338 | ICPIM-34336 Clone a standard default report and run it | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 07:39
Test Case | ICPIM-34337 | ICPIM-34336 Try to edit a standard default report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 07:38
Test Case | ICPIM-34335 | ICPIM-34333 Confirm behavior of system after deleting files in Windows\Temp directory and then regenerate report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 07:07
Test Case | ICPIM-34334 | ICPIM-34333 Confirm that the report is written to \Windows\Temp directory when run |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-06 06:50
Test Case | ICPIM-34318 | ICPIM-34091 Run a report when the table selected in the drop down is incorrect for the report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-05 21:12
Test Case | ICPIM-34317 | ICPIM-34091 Import a report at the Define Reports Window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-02-05 20:57
Test Case | ICPIM-34312 | ICPIM-34158 Clear entries from the system categories column in the Configure Report Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 18:41
Test Case | ICPIM-34282 | ICPIM-34158 Verify printing a generated report from the Configure Report Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 12:56
Test Case | ICPIM-34281 | ICPIM-34158 Rearrange report columns in the Configure Report Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 12:55
Test Case | ICPIM-34280 | ICPIM-34158 Run from the View->Report menu the report that was created with the Configure Report Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 09:05
Test Case | ICPIM-34279 | ICPIM-34158 Run the report that was created in ICPIM-34160 from the Define Reports Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 09:03
Test Case | ICPIM-34278 | ICPIM-34153 Export the standard report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-05 07:18 | [9 empty] | ICPIM-34143
Test Case | ICPIM-34261 | ICPIM-34258 Try to delete a report category that have reports associted with them. | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 20:11
Test Case | ICPIM-34260 | ICPIM-34258 Remove a report category | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 19:28
Test Case | ICPIM-34259 | ICPIM-34258 Add a report category | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 19:28 | [9 empty] | ICPIM-34134
Test Case | ICPIM-34257 | ICPIM-34153 Add report in Define Reports Window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 19:23 | [9 empty] | ICPIM-34135
Test Case | ICPIM-34229 | ICPIM-34155 Generate Commission Status Report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:18
Test Case | ICPIM-34228 | ICPIM-34155 Generate Commission Resource List | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:17
Test Case | ICPIM-34227 | ICPIM-34155 Generate Commission Parts List | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:17
Test Case | ICPIM-34226 | ICPIM-34154 Clear filters |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:15
Test Case | ICPIM-34225 | ICPIM-34154 Show and hide filters |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:15
Test Case | ICPIM-34224 | ICPIM-34154 Confirm that you can remove a job that is in the pending state |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:14
Test Case | ICPIM-34223 | ICPIM-34154 Confirm that you cannot remove a job that is in the processing state |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:14
Test Case | ICPIM-34222 | ICPIM-34154 Verify timestamps in t_jobqueue database |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-04 14:14
Test Case | ICPIM-34221 | ICPIM-34154 Delete a job in the job queue |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:13
Test Case | ICPIM-34220 | ICPIM-34154 Verify that next job in queue gets executed when job that is processing completes |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:12
Test Case | ICPIM-34219 | ICPIM-34154 Verify that next job in queue gets executed when job that is processing gets canceled. |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:12 | [9 empty] | ICPIM-35245, ICPIM-35252
Test Case | ICPIM-34218 | ICPIM-34154 Verify that report jobs get queued up in the job queue |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 14:11
Test Case | ICPIM-34212 | ICPIM-34156 Run report from system category Basic search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-04 08:34 | [9 empty] | ICPIM-34211
Test Case | ICPIM-34211 | ICPIM-34156 Run report from system category Find search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 08:34 | [9 empty] | ICPIM-34212
Test Case | ICPIM-34210 | ICPIM-34156 Add a search to generate a report from | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 08:33 | [9 empty] | ICPIM-34464
Test Case | ICPIM-34209 | ICPIM-34156 Clear the seed from the Run search window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 08:29
Test Case | ICPIM-34208 | ICPIM-34156 Generate report from browser | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 08:29
Test Case | ICPIM-34207 | ICPIM-34156 Run default Find Dashboard search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-04 08:29
Test Case | ICPIM-34206 | ICPIM-34156 Run default Basic search | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-04 08:28
Test Case | ICPIM-34205 | ICPIM-34166 Job Queue Viewer - The context menu on selected job | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-02-04 03:03 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-34204 | ICPIM-34166 Job Queue Viewer - Filter on Users | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2015-02-04 03:02 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-34266
Test Case | ICPIM-34203 | ICPIM-34166 Job Queue Viewer - Filter on Priorities | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-02-04 03:02 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-34202 | ICPIM-34166 Job Queue Viewer - Filter on Types | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2015-02-04 03:01 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-34272, ICPIM-34275
Test Case | ICPIM-34201 | ICPIM-34166 Job Queue Viewer - Filter on States | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-02-04 03:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-34200 | ICPIM-34166 Job Queue Viewer - Filter overview | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2015-02-04 03:00 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-34275
Test Case | ICPIM-34199 | ICPIM-34166 Job Queue Viewer - Remove Job | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-04 02:58 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-34198 | ICPIM-34166 Job Queue Viewer - View Job | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-04 02:57 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-34197 | ICPIM-34166 Job Queue Viewer - Manual Refresh | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-04 02:56 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-34196 | ICPIM-34166 Job Queue Viewer - Auto Refresh | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-04 02:55 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-34190 | ICPIM-28030 Datastore - Chart Format (Meter Chart) | All |  | An Vo | An Vo | Windows Client | Pass | 2015-02-04 02:21 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-34189 | ICPIM-28030 Datastore - Chart Format (Pie Chart) | All |  | An Vo | An Vo | Windows Client | Pass | 2015-02-04 02:19 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-34188 | ICPIM-28030 Datastore - Chart Format (XY Chart) | All |  | An Vo | An Vo | Windows Client | Pass | 2015-02-04 02:17 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-34185 | ICPIM-28030 Datastore - Chart Format (Chart Colors) | All |  | An Vo | An Vo | Windows Client | Fail | 2015-02-04 01:15 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-34193
Test Case | ICPIM-34180 | ICPIM-34166 Job Queue Viewer - GUI Overview | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2015-02-03 21:35 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-34181
Test Case | ICPIM-34179 | ICPIM-34165 Align report information at the right of the report column |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 21:26
Test Case | ICPIM-34178 | ICPIM-34165 Align report information in the center of the column |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 21:25
Test Case | ICPIM-34177 | ICPIM-34165 Export a report to CSV from the configure reports window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 21:22
Test Case | ICPIM-34176 | ICPIM-34165 Stop a report during execution from the configure reports window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 21:21
Test Case | ICPIM-34175 | ICPIM-34165 Email a report from the configure reports window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-02-03 21:20 | [9 empty] | ICPIM-38760
Test Case | ICPIM-34174 | ICPIM-34165 Print a report from the Configure reports window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Fail | 2015-02-03 21:20 | [9 empty] | ICPIM-38760
Test Case | ICPIM-34173 | ICPIM-34165 Save an HTML file using an invalid window file name. |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 21:13
Test Case | ICPIM-34172 | ICPIM-34165 Cancel saving an HTML report in the Configure Reports window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 21:11 | [9 empty] | ICPIM-34164
Test Case | ICPIM-34171 | ICPIM-34165 Save an HTML report through the configure report window |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 21:09 | [9 empty] | ICPIM-34164
Test Case | ICPIM-34167 | ICPIM-34166 Job Queue Viewer - Opening Job Queue Viewer | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-02-03 20:57 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-34164 | ICPIM-34158 Gather system information from the configured report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 20:07 | [9 empty] | ICPIM-34171, ICPIM-34172
Test Case | ICPIM-34163 | ICPIM-34158 Email report that was generated in Configure Report window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 20:04
Test Case | ICPIM-34162 | ICPIM-34158 Verify configuring a report with the Basic Search system category | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 20:01
Test Case | ICPIM-34161 | ICPIM-34158 Validate the filter System Category when configuring a report | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 19:57
Test Case | ICPIM-34160 | ICPIM-34158 Configure a newly added report in the configure report window | Magni |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 19:50
Test Case | ICPIM-34147 | ICPIM-34091 Verify the help button of the Define New Reports Window will display useful help information |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 15:41
Test Case | ICPIM-34146 | ICPIM-34091 Cancel adding a report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 15:37
Test Case | ICPIM-34145 | ICPIM-34091 Edit a standard report by first cloning it |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 15:19
Test Case | ICPIM-34144 | ICPIM-34091 Verify that you cannot edit a standard report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 15:17
Test Case | ICPIM-34143 | ICPIM-34091 Export a report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 15:14 | [9 empty] | ICPIM-34278
Test Case | ICPIM-34142 | ICPIM-34091 Run a report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 15:07
Test Case | ICPIM-34141 | ICPIM-34091 Cancel the delete report option |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 14:55
Test Case | ICPIM-34140 | ICPIM-34091 Remove a report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 14:52
Test Case | ICPIM-34139 | ICPIM-34091 Clone a report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 14:49
Test Case | ICPIM-34135 | ICPIM-34091 Add a standard report |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 13:48 | [9 empty] | ICPIM-34257
Test Case | ICPIM-34134 | ICPIM-34091 Add a report category |  |  | Donna Daigneault | Donna Daigneault | Windows Client | New | 2015-02-03 13:44 | [9 empty] | ICPIM-34259
Test Case | ICPIM-34131 | ICPIM-34091 Verify the functionality of the Filter by category check box when selected |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 13:37
Test Case | ICPIM-34128 | ICPIM-34090 Verify the functionality of the Filter by category check box |  |  | Donna Daigneault | Donna Daigneault | Windows Client | Pass | 2015-02-03 13:22
Test Case | ICPIM-34127 | ICPIM-34123 Portfolio - Quick Search: Properties | Magni |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2015-02-03 12:38 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-33766, ICPIM-34064
Test Case | ICPIM-34126 | ICPIM-34123 Portfolio - Quick Search: Navigation | Magni |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2015-02-03 12:37 | 1800 | 2100 | 300 | 87% | 1800 | 2100 | 300 | 87% |  | ICPIM-33766, ICPIM-34064
Test Case | ICPIM-34125 | ICPIM-34123 Portfolio - Quick Search: View all Results | Magni |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2015-02-03 12:36 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-33766, ICPIM-34064, ICPIM-34973, ICPIM-35050
Test Case | ICPIM-34124 | ICPIM-34123 Portfolio - Quick Search: Results drop down | Magni |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2015-02-03 12:36 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33766, ICPIM-34064, ICPIM-34973
Test Case | ICPIM-34112 | ICPIM-28127 Ensure Data Is Written Accurately to Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34111 | ICPIM-28127 Ensure Attributes Can Be Mapped To Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34110 | ICPIM-28127 Ensure Assets With Matching UIDs Are Mapped | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34109 | ICPIM-28127 Ensure Assets In The Specified Category(s) Are Retrieved | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34108 | ICPIM-28127 Ensure the DEA Retrieves Attributes From OSI Soft | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34107 | ICPIM-28127 Configure the DEA | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34106 | ICPIM-28127 Add The Same Identifiers to 5 Assets in CPIM | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34105 | ICPIM-28127 Add A Unique Identifier to 5 Assets in OSI Soft | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34104 | ICPIM-28127 Connect Your System To The Demo VM | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:55 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34100 | ICPIM-28127 Install OSI Soft & Pi Explorer | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34099 | ICPIM-28127 Install the DEA | All |  | Garrett S. | Garrett S. |  | Pass | 2015-02-02 16:54 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-34082 | ICPIM-13471 Upgrade from Elli/ Stretch/ Stretch + Hot Fix to Magni (With Jaspersoft) | All |  | An Vo | An Vo | Windows Client | Invalid | 2015-02-02 00:26 | 21600 | 21600 | 0 | 100% | 21600 | 21600 | 0 | 100% |  | ICPIM-33964
Test Case | ICPIM-34081 | ICPIM-13471 Upgrade from Elli/ Stretch/ Stretch + Hot Fix to Magni (Without Jaspersoft) | All |  | An Vo | An Vo | Windows Client | Invalid | 2015-02-02 00:11 | 14400 | 14400 | 0 | 100% | 14400 | 14400 | 0 | 100% |  | ICPIM-33964
Test Case | ICPIM-34041 | ICPIM-34036 Export Tile Grid | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-29 23:33 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-34040 | ICPIM-34035 Import Tile Grid | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-29 23:28 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-34039 | ICPIM-34034 Delete Tile Grid | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-01-29 23:27 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-34038 | ICPIM-34033 Place some items on new tile grid | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-29 23:26 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100%
Test Case | ICPIM-34037 | ICPIM-34033 Create Tile Grid for new Datacenter | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-29 23:25 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-34002 | ICPIM-36605 Portfolio - Asset Attributes: Time Stamp format for Datastore | Magni |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2015-01-28 14:28 | 7200 | 8400 | 0 | 100% | 7200 | 8400 | 0 | 100% |  | ICPIM-34053, ICPIM-34346, ICPIM-34483, ICPIM-34056, ICPIM-34061, ICPIM-35038
Test Case | ICPIM-33997 | ICPIM-27431 Portfolio - Dashboard Viewer: Auto-refresh user settings | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-28 10:23 | 10800 | 3600 | 7200 | 33% | 10800 | 3600 | 7200 | 33% |  | ICPIM-35021
Test Case | ICPIM-33980 | ICPIM-33977 Commission Enclosure to an Row Position that was occupied by another enclosure |  |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-28 03:53 | 1800 | 4500 | 0 | 100% | 1800 | 4500 | 0 | 100%
Test Case | ICPIM-33979 | ICPIM-33977 An Equipment occupies multiple Row Positions. |  |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-28 03:52 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33978 | ICPIM-33977 Commission Enclosure to Row Position with Anywhere option |  |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2015-01-28 03:51 | 1800 | 4500 | 0 | 100% | 1800 | 4500 | 0 | 100%
Test Case | ICPIM-33941 | ICPIM-33912 Circulate Validation Trace | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2015-01-27 13:07 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33915 | ICPIM-33912 Circulate Validation Details Log | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2015-01-26 16:01 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-33883 | ICPIM-28722 Ensure RF Code Assets are Correctly Auto-Mapped to CPIM Assets - Asset Tag | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-23 14:26 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33853 | ICPIM-27431 Portfolio - Dashboard Viewer: Support for Embedded URLs | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2015-01-22 16:12 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33846, ICPIM-33849
Test Case | ICPIM-33819 | ICPIM-13471 Install CPIM-ITRACS and SQL on a new drive other than the C drive | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2015-01-21 14:41 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-33723 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - General (Anchor) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-01-19 02:07 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-33722 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - General (Allow Navigation) | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2015-01-19 02:06 | 600 |  | 600 | 0% | 600 |  | 600 | 0% |  | ICPIM-28059
Test Case | ICPIM-33721 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - General (Allow Connections) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2015-01-19 02:04 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-33715 | ICPIM-29296 CSV - Copy to Server (Connect sub tab - Connecting) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2015-01-18 21:23 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100%
Test Case | ICPIM-33631 | ICPIM-14714 Portfolio - Advanced Search: Disable Search button until Filters applied | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 14:27 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-33629 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters- Attribute” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:37 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33628 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters- Type” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:37 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33627 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters- Make/Model” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:35 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33626 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters- Line Of Business” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:34 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33625 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters-Location” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:33 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33624 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters-Kind” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:31 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33623 | ICPIM-33616 Permissions to control item visibility in the App for ‘‘Search Filters- Name” – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:30 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33622 | ICPIM-33616 Permissions to control item visibility in the App for ‘Tasks’ tab – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:28 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33621 | ICPIM-33616 Permissions to control item visibility in the App for ‘Changes’ tab – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:26 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33620 | ICPIM-33616 Permissions to control item visibility in the App for ‘Portfolio Views - Charts’ - TC | Magni |  | Mai Nguyen | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:23 | 1800 | 4800 | 0 | 100% | 1800 | 4800 | 0 | 100% |  | ICPIM-34618
Test Case | ICPIM-33619 | ICPIM-33616 Permissions to control item visibility in the App for ‘Portfolio Views – List View’ - TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:22 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33618 | ICPIM-33616 Permissions to control item visibility in the App for ‘Portfolio Views - Viewer’ - TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:21 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-33617 | ICPIM-33616 Permissions to control item visibility in the App for ‘Portfolio Views - Map view’ – TC | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2015-01-15 13:19 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-33581 | ICPIM-15839 Trace - Visual Trace: Info Panel & Cable Spacing in Trace Pane | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Blocker | 2015-01-14 14:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33580 | ICPIM-15839 Trace - Visual Trace: Fixed Cables | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Blocker | 2015-01-14 14:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33579 | ICPIM-15839 Trace - Visual Trace: Soft Cables | Magni |  | Rachna Muthanna | Rachna Muthanna | Web Client | Blocker | 2015-01-14 14:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33578 | ICPIM-15839 Trace - Visual Trace: Information On Panels (name, class, model) | Magni |  | Khang Nguyen | Rachna Muthanna | Web Client | Pass | 2015-01-14 14:55 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-33769, ICPIM-33773, ICPIM-34136, ICPIM-34521
Test Case | ICPIM-33521 | ICPIM-33438 Once Assets Are Mapped, The Mappings ARE NOT Modified Without Direct User Interaction | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-13 15:34 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-33432
Test Case | ICPIM-33506 | ICPIM-33438 Configuration - Service/Config File | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-13 09:47 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33456 | ICPIM-33438 This DEA DOES NOT Move, Create, or Otherwise Modify Assets Apart From Writing Values to Specified Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33455 | ICPIM-33438 SQL Queries - Dangerous Queries Are Ignored | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:25 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33454 | ICPIM-33438 SQL Queries - Bad Queries Are Handled Appropriately | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33453 | ICPIM-33438 Large Data Sets Can Be Processed - 64 Bit | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:15 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33452 | ICPIM-33438 Asset Can Be Removed From Source System Without Causing Errors in CPIM | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33451 | ICPIM-33438 Data Mapping - Attributes Mapped to Datastores - Unsupported Data Types | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33450 | ICPIM-33438 Data Mapping - Attributes Mapped to Datastores - String | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33449 | ICPIM-33438 Data Mapping - Attributes Mapped to Datastores - Date/Time | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33448 | ICPIM-33438 Data Mapping - Attributes Mapped to Datastores - Numeric | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:13 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33447 | ICPIM-33438 Asset Mapping - By Datastore - Duplicate Values Exist in Source | All |  | Garrett S. | Garrett S. |  | Invalid | 2015-01-12 16:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33446 | ICPIM-33438 Asset Mapping - By Datastore - Duplicate Values Exist in CPIM | All |  | Garrett S. | Garrett S. |  | Invalid | 2015-01-12 16:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-33609
Test Case | ICPIM-33444 | ICPIM-33438 Asset Mapping - By Datastore | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 16:07 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33443 | ICPIM-33438 Asset Mapping - By Name - Duplicate Names Exist in Source | All |  | Garrett S. | Garrett S. |  | Invalid | 2015-01-12 16:06 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33442 | ICPIM-33438 Asset Mapping - By Name - Duplicate Names Exist in CPIM | All |  | Garrett S. | Garrett S. |  | Invalid | 2015-01-12 16:06 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33441 | ICPIM-33438 Asset Mapping - By Name | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 15:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-33440 | ICPIM-33438 Connectivity to MS SQL Server Source System | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 15:40 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-33254
Test Case | ICPIM-33439 | ICPIM-33438 Configuration - Instance | All |  | Garrett S. | Garrett S. |  | Pass | 2015-01-12 15:39 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-33251
Test Case | ICPIM-33097 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet CUPS) | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2015-01-05 02:29 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32976 | ICPIM-28873 Load Masks - Show Textures |  |  | An Vo | An Vo | Windows Client | Fail | 2014-12-29 03:06 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32985
Test Case | ICPIM-32975 | ICPIM-28873 Load Masks - Show Tile Grid |  |  | An Vo | An Vo | Windows Client | Fail | 2014-12-29 02:58 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-33149
Test Case | ICPIM-32974 | ICPIM-28873 Load Masks - Show Row |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 02:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32958 | ICPIM-28873 Load Masks - Show Enclosures |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 02:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32957 | ICPIM-28873 Load Masks - Show Panels |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 02:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32956 | ICPIM-28873 Load Masks - Show Plugins |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 01:55 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32955 | ICPIM-28873 Load Masks - Show Ports |  |  | An Vo | An Vo | Windows Client | Fail | 2014-12-29 01:36 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32978
Test Case | ICPIM-32954 | ICPIM-28873 Load Masks - Show Foreign |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 01:23 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32953 | ICPIM-28873 Load Masks - Show All |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 01:14 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32952 | ICPIM-28873 Load Masks - View State |  |  | An Vo | An Vo | Windows Client | Pass | 2014-12-29 01:04 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32860 | ICPIM-28847 Manage Favorites - Sort Favorites | All |  | An Vo | An Vo | Windows Client | Fail | 2014-12-23 23:55 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32861
Test Case | ICPIM-32783 | ICPIM-32306 Datastore - Browser (Update Datastore Value) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-22 01:58 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-32774 | ICPIM-32772 Commission - Configure Group - Remove equipment items | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-21 21:56 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32773 | ICPIM-32772 Commission - Create Group - Remove equipment items | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-21 21:55 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32771 | ICPIM-32769 Commission Editor: Equipment tab: Configure Group - Select All | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-21 21:51 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32770 | ICPIM-32769 Commission Editor - Equipment tab: Create Group - Select All equipment | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-21 21:49 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-32712 | ICPIM-32700 Change Management - Change Control Statistics: Selection Details section | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:42 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32711 | ICPIM-32700 Change Management - Change Control Statistics: Filtered section | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:41 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32710 | ICPIM-32700 Change Management - Change Control Statistics: Global section | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:39 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32709 | ICPIM-32699 Change Management - Email Notes: of a Action | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:37 | 900 | 240 | 660 | 26% | 900 | 240 | 660 | 26%
Test Case | ICPIM-32708 | ICPIM-32699 Change Management - Email Notes: of a Order | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:36 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32707 | ICPIM-32699 Change Management - Email Notes: of a Request | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:35 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32706 | ICPIM-32699 Change Management - Email Notes: of a Project | All |  | Tien Pham | Vinh Nguyen | Windows Client | Fail | 2014-12-19 03:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32705 | ICPIM-32698 Change Management - View Notes for Request | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-19 03:32 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32704 | ICPIM-32696 Change Management - Add Notes: for Action | All |  | Mai Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-19 03:29 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-33326, ICPIM-33347, ICPIM-33344
Test Case | ICPIM-32703 | ICPIM-32696 Change Management - Add Notes: for Order | All |  | Mai Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-19 03:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33326, ICPIM-33344
Test Case | ICPIM-32702 | ICPIM-32696 Change Management - Add Notes: for Request | All |  | Mai Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-19 03:28 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33326, ICPIM-33344
Test Case | ICPIM-32701 | ICPIM-32696 Change Management - Add Notes: for project | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-19 03:27 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-33317
Test Case | ICPIM-32697 | ICPIM-28293 Template Management - Add Template (Packages tab: Import Templates) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-12-19 03:20 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-33635
Test Case | ICPIM-32695 | ICPIM-32682 Change Management - Edit Work Actions: Cost | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:16 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-33484
Test Case | ICPIM-32694 | ICPIM-32682 Change Management - Edit Work Actions: Email (Error cases) | All |  | Phuong Phan | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:15 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-33479
Test Case | ICPIM-32693 | ICPIM-32682 Change Management - Edit Work Actions: Notify Technician (Email) for an action | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:14 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33469
Test Case | ICPIM-32692 | ICPIM-32682 Change Management - Edit Work Actions: Reassign | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:14 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-33457
Test Case | ICPIM-32691 | ICPIM-32682 Change Management - Edit Work Actions: Assign | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:12 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-33457
Test Case | ICPIM-32690 | ICPIM-32682 Change Management - Edit Work Actions: Team | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:11 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32689 | ICPIM-32682 Change Management - Edit Work Actions: Action | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:09 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33341
Test Case | ICPIM-32688 | ICPIM-32682 Change Management - Edit Work Actions: Class | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:09 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32687 | ICPIM-32682 Change Management - Edit Work Actions: Move Within | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:08 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32686 | ICPIM-32682 Change Management - Edit Work Actions: Target | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:07 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-33341
Test Case | ICPIM-32685 | ICPIM-32682 Change Management - Edit Work Actions: Source | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-19 03:06 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-33341
Test Case | ICPIM-32684 | ICPIM-32682 Change Management - Edit Work Actions: Name | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:06 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32683 | ICPIM-32682 Change Management - Edit Work Actions: Options for editing | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-19 03:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32634 | ICPIM-32540 Change Management - Filter Display: filter work requests by Created Date | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:57 | 900 | 60 | 840 | 6% | 900 | 60 | 840 | 6%
Test Case | ICPIM-32633 | ICPIM-32540 Change Management - Filter Display: filter work requests by Cost Center | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:56 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32632 | ICPIM-32540 Change Management - Filter Display: filter work requests by Reference | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:55 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-32631 | ICPIM-32540 Change Management - Filter Display: filter work requests by Name | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:53 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-32630 | ICPIM-32540 Change Management - Filter Display: filter work requests by Origin | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:52 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32629 | ICPIM-32613 Change Management - Edit Work Orders: Class | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:52 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-32628 | ICPIM-32540 Change Management - Filter Display: filter work requests by Class type | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:51 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32627 | ICPIM-32613 Change Management - Edit Work Orders: Move Within | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:51 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32626 | ICPIM-32613 Change Management - Edit Work Orders: Finish Date | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-18 02:51 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33366, ICPIM-33369, ICPIM-33372
Test Case | ICPIM-32625 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "TechOk" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:51 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32624 | ICPIM-32613 Change Management - Edit Work Orders: Start Date | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-18 02:50 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100% |  | ICPIM-33366, ICPIM-33369, ICPIM-33372
Test Case | ICPIM-32623 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Rework" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:50 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-32622 | ICPIM-32613 Change Management - Edit Work Orders: Name | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:50 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-32621 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Planned" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:49 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32620 | ICPIM-32613 Change Management - Edit Work Orders: Options for editing | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:49 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32619 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Open" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:48 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-32618 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Flagged" | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Invalid | 2014-12-18 02:47 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-32617 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Flagged" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:46 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32616 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Closed" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:45 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32615 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Cancelled" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:45 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-32614 | ICPIM-32540 Change Management - Filter Display: Filter Requests by Status "Assigned" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:44 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-32612 | ICPIM-32540 Change Management - Filter Display: filter work order by Class type | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:43 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-32611 | ICPIM-32540 Change Management - Filter Display: filter work order by range of Finish date | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:42 | 900 | 60 | 840 | 6% | 900 | 60 | 840 | 6%
Test Case | ICPIM-32610 | ICPIM-32540 Change Management - Filter Display: filter work order by Finish date | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:41 | 1200 | 120 | 1080 | 10% | 1200 | 120 | 1080 | 10%
Test Case | ICPIM-32609 | ICPIM-32540 Change Management - Filter Display: filter work order by range of Start date | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:39 | 900 | 180 | 720 | 20% | 900 | 180 | 720 | 20%
Test Case | ICPIM-32608 | ICPIM-32540 Change Management - Filter Display: filter work order by Start date | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-18 02:36 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-32607 | ICPIM-32597 Change Management - Edit Work Requests: Cost Center | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:36 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32606 | ICPIM-32597 Change Management - Edit Work Requests: Request Item | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:36 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32605 | ICPIM-32597 Change Management - Edit Work Requests: Reference | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:35 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32604 | ICPIM-32597 Change Management - Edit Work Requests: Finish Date | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-18 02:35 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-33366, ICPIM-33369, ICPIM-33372
Test Case | ICPIM-32603 | ICPIM-32597 Change Management - Edit Work Requests: Start Date | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-18 02:34 | 1200 | 2400 | 1500 | 61% | 1200 | 2400 | 1500 | 61% |  | ICPIM-33366, ICPIM-33369, ICPIM-33372
Test Case | ICPIM-32602 | ICPIM-32597 Change Management - Edit Work Requests: Class | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:33 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32601 | ICPIM-32597 Change Management - Edit Work Requests: Move Within | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:32 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100%
Test Case | ICPIM-32600 | ICPIM-32597 Change Management - Edit Work Requests: Status | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:31 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-32599 | ICPIM-32597 Change Management - Edit Work Requests: Name | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32598 | ICPIM-32597 Change Management - Edit Work Requests: Options for editing | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:28 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32596 | ICPIM-32592 Change Management - Edit Work Projects: Class | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:22 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32595 | ICPIM-32592 Change Management - Edit Work Projects: Move Within | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32594 | ICPIM-32592 Change Management - Edit Work Projects: Name | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-18 02:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32593 | ICPIM-32592 Change Management - Edit Work Projects: Options for editing | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-18 02:20 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-33317
Test Case | ICPIM-32558 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Location of object | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 03:03 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32557 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Cost value | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 03:02 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-32556 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Team | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 03:01 | 600 | 180 | 420 | 30% | 600 | 180 | 420 | 30%
Test Case | ICPIM-32555 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by class type "Work Action" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 03:01 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-32554 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Technician | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 03:00 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-32553 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action"Assign Service" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:59 | 600 | 72 | 528 | 12% | 600 | 72 | 528 | 12%
Test Case | ICPIM-32552 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Unassigned" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:58 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-32551 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Request" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:58 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-32550 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Move" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:57 | 600 | 90 | 510 | 15% | 600 | 90 | 510 | 15%
Test Case | ICPIM-32549 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "General" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:56 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-32548 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Disconnect" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:56 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32547 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Dictionary" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:54 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32546 | ICPIM-32540 Change Management - Filter Display: Actions: Filter by Action "Connect" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:54 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32545 | ICPIM-32540 Change Management - Filter Display: Action: Filter by Status "TechOK" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:53 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100% |  | ICPIM-32666
Test Case | ICPIM-32544 | ICPIM-32540 Change Management - Filter Display: Action: Filter by Status "Open" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:52 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-32543 | ICPIM-32540 Change Management - Filter Display: Action: Filter by Status "Flagged" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:51 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-32542 | ICPIM-32540 Change Management - Filter Display: : Action: Filter by Status "Closed" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:50 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100% |  | ICPIM-32654
Test Case | ICPIM-32541 | ICPIM-32540 Change Management - Filter Display: Action: Filter by Status "Assigned" | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-12-17 02:49 | 600 | 840 | 0 | 100% | 600 | 840 | 0 | 100%
Test Case | ICPIM-32539 | ICPIM-32538 Decommission - Remove Decommission (keep Change Control entries) |  |  | Tien Pham | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:25 | 1800 | 2880 | 0 | 100% | 1800 | 2880 | 0 | 100%
Test Case | ICPIM-32537 | ICPIM-32535 Decommission - View Decommission Log (Functionality) | All |  | Tien Pham | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:18 | 1800 | 5400 | 0 | 100% | 1800 | 5400 | 0 | 100% |  | ICPIM-33184
Test Case | ICPIM-32536 | ICPIM-32535 Decommission - View Decommission Log (Overview) | All |  | Tien Pham | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:16 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-32534 | ICPIM-31933 Template Management - Objects Context Menu: Connector Points: Adding a Connected State to a Multi-Connector | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32533 | ICPIM-31933 Template Management - Objects Context Menu: Autospace - Custom (Vertical) | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 02:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32997, ICPIM-33000
Test Case | ICPIM-32532 | ICPIM-31933 Template Management - Objects Context Menu: Autospace - Custom (Horizontal) | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 02:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32997, ICPIM-33000
Test Case | ICPIM-32531 | ICPIM-31933 Template Management - Objects Context Menu: Autospace - Vertical | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 02:06 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-32994, ICPIM-32997
Test Case | ICPIM-32530 | ICPIM-31933 Template Management - Objects Context Menu: Autospace - Horizontal | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 02:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32994, ICPIM-32997
Test Case | ICPIM-32529 | ICPIM-31933 Template Management - Objects Context Menu: Autospace (overview) | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32528 | ICPIM-31933 Template Management - Objects Context Menu: Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 02:03 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32787
Test Case | ICPIM-32527 | ICPIM-31933 Template Management - Objects Context Menu: Refresh | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:02 | 300 | 900 | 0 | 100% | 300 | 900 | 0 | 100%
Test Case | ICPIM-32526 | ICPIM-31933 Template Management - Objects Context Menu: Align Objects Within Parent Objects | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:02 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32525 | ICPIM-31933 Template Management - Objects Context Menu: Align selected Objects on a Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32524 | ICPIM-31933 Template Management - Objects Context Menu: Adjust the Z-order of an object | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 02:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32523 | ICPIM-31933 Template Management - Objects Context Menu: Resize an Object in a Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 01:59 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32988
Test Case | ICPIM-32522 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connected State - Format Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 01:58 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32939
Test Case | ICPIM-32521 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connected State - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-17 01:57 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32520 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connected State - Format Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-17 01:56 | 1800 | 4800 | 0 | 100% | 1800 | 4800 | 0 | 100% |  | ICPIM-33022, ICPIM-33019, ICPIM-34938
Test Case | ICPIM-32516 | ICPIM-28293 Template Management - Add Template (Packages tab: Import Path) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-12-16 14:07 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100% |  | ICPIM-33605
Test Case | ICPIM-32515 | ICPIM-28293 Template Management - Add Template (Packages tab: Open Packages tab) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-16 14:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32429 | ICPIM-32377 Change Management - Configurable Column Display: Project in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:33 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32428 | ICPIM-32377 Change Management - Configurable Column Display: Class in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:31 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32427 | ICPIM-32377 Change Management - Configurable Column Display: Finish in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:30 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32426 | ICPIM-32377 Change Management - Configurable Column Display: Start in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:29 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32425 | ICPIM-32377 Change Management - Configurable Column Display: # of Action(s) in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:29 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32424 | ICPIM-32377 Change Management - Configurable Column Display: # of Order(s) in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:28 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32423 | ICPIM-32377 Change Management - Configurable Column Display: Cost in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:28 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32422 | ICPIM-32377 Change Management - Configurable Column Display: Cost Center in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:27 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32421 | ICPIM-32377 Change Management - Configurable Column Display: Request Item in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:27 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32420 | ICPIM-32377 Change Management - Configurable Column Display: Reference in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:26 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32419 | ICPIM-32377 Change Management - Configurable Column Display: Created in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:25 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32418 | ICPIM-32377 Change Management - Configurable Column Display: Origin in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:25 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32417 | ICPIM-32377 Change Management - Configurable Column Display: Status in Requests pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:25 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32416 | ICPIM-32377 Change Management - Configurable Column Display: Project in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:24 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32415 | ICPIM-32377 Change Management - Configurable Column Display: Request in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:23 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32414 | ICPIM-32377 Change Management - Configurable Column Display: Class in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:23 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32413 | ICPIM-32377 Change Management - Configurable Column Display: Finish in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:22 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32412 | ICPIM-32377 Change Management - Configurable Column Display: Start in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:22 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32411 | ICPIM-32377 Change Management - Configurable Column Display: Created in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:21 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32410 | ICPIM-32377 Change Management - Configurable Column Display: Cost in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:21 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32409 | ICPIM-32377 Change Management - Configurable Column Display: # of Action(s) in Orders pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:20 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32408 | ICPIM-32377 Change Management - Configurable Column Display: Project in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:20 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32407 | ICPIM-32377 Change Management - Configurable Column Display: Request in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:19 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32406 | ICPIM-32377 Change Management - Configurable Column Display: Class in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:19 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32405 | ICPIM-32377 Change Management - Configurable Column Display: First Viewed in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:18 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32404 | ICPIM-32377 Change Management - Configurable Column Display: Physical Link in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:18 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32403 | ICPIM-32377 Change Management - Configurable Column Display: Orientation in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:17 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32402 | ICPIM-32377 Change Management - Configurable Column Display: U Position in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:16 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32401 | ICPIM-32377 Change Management - Configurable Column Display: Technician in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:15 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32400 | ICPIM-32377 Change Management - Configurable Column Display: Team in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:15 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32399 | ICPIM-32377 Change Management - Configurable Column Display: Target in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:14 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32398 | ICPIM-32377 Change Management - Configurable Column Display: Source in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:14 | 300 | 360 | 0 | 100% | 300 | 360 | 0 | 100%
Test Case | ICPIM-32397 | ICPIM-32377 Change Management - Configurable Column Display: Action Type in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:13 | 300 | 420 | 0 | 100% | 300 | 420 | 0 | 100%
Test Case | ICPIM-32396 | ICPIM-32377 Change Management - Configurable Column Display: Cost in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:12 | 300 | 420 | 0 | 100% | 300 | 420 | 0 | 100%
Test Case | ICPIM-32395 | ICPIM-32377 Change Management - Configurable Column Display: Status in Actions pane | All |  | Kim Rodriguez | Vinh Nguyen | Windows Client | Pass | 2014-12-16 02:12 | 300 | 600 | 0 | 100% | 300 | 600 | 0 | 100%
Test Case | ICPIM-32394 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Door - Format Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:59 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32936
Test Case | ICPIM-32393 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Door - Format Border properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-16 01:58 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32392 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Door - Format Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:57 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32933
Test Case | ICPIM-32391 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Door - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:57 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32839, ICPIM-32930
Test Case | ICPIM-32390 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Door - Format Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32784, ICPIM-32873
Test Case | ICPIM-32389 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Datalink - Format Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:55 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32870
Test Case | ICPIM-32388 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Datalink - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:55 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32918
Test Case | ICPIM-32387 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Datalink - Format Location properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:54 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32784, ICPIM-32915
Test Case | ICPIM-32386 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Rectangle - Format Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:53 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32912
Test Case | ICPIM-32385 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Rectangle - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:52 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50% |  | ICPIM-32839
Test Case | ICPIM-32384 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Rectangle - Format Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:52 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32784, ICPIM-32873
Test Case | ICPIM-32383 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Image - Format Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:51 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32903, ICPIM-32906
Test Case | ICPIM-32382 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Image - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:51 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32839
Test Case | ICPIM-32381 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Image - Format Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:50 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32784, ICPIM-32873
Test Case | ICPIM-32380 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Label - Format Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:49 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32870
Test Case | ICPIM-32379 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Label - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:48 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32867
Test Case | ICPIM-32378 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Label - Format Location properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:48 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32784
Test Case | ICPIM-32376 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Slot - Format Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:47 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32864
Test Case | ICPIM-32375 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Slot - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:47 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32839, ICPIM-32851
Test Case | ICPIM-32374 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Slot - Format Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:46 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32784
Test Case | ICPIM-32373 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connector - Format Connector properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-16 01:45 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32372 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connector - Format Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:42 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32839, ICPIM-32851
Test Case | ICPIM-32371 | ICPIM-31933 Template Management - Objects Context Menu: Format '[Object Name]' - Connector - Format Location properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-16 01:42 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83% |  | ICPIM-32784
Test Case | ICPIM-32367 | ICPIM-31716 Slots with more than one module report | All |  | Garrett S. | Garrett S. | Windows Client | Invalid | 2014-12-15 16:38 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0% |  | ICPIM-28396
Test Case | ICPIM-32366 | ICPIM-31716 Blank Datastore Report | All |  | Garrett S. | Garrett S. | Windows Client | Invalid | 2014-12-15 16:37 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0% |  | ICPIM-28397
Test Case | ICPIM-32358 | ICPIM-32357 Configuring IMVision DEA and SQL Database on Separated Servers | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-15 12:49 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-32368, ICPIM-32354
Test Case | ICPIM-32352 | ICPIM-32351 Maintenance - Equipment | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-15 09:29 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32349 | ICPIM-32348 Maintenance - LOB | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-15 09:09 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-32341 | ICPIM-32151 Format 'New Connector' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:09 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32340 | ICPIM-32151 Format 'New CAD Object' - Configure Files properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:07 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-33305
Test Case | ICPIM-32339 | ICPIM-32151 Format 'New CAD Object' - Configure Scale properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:07 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32338 | ICPIM-32151 Format 'New CAD Object' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:06 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32337 | ICPIM-32151 Format 'New 3D Object' - Configure Files properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 03:05 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33282
Test Case | ICPIM-32336 | ICPIM-32151 Format 'New 3D Object' - Configure Scale properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:04 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32335 | ICPIM-32151 Format 'New 3D Object' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:04 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32334 | ICPIM-32151 Format 'New Tile' - Configure Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:03 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32333 | ICPIM-32151 Format 'New Tile' - Configure Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 03:02 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32939
Test Case | ICPIM-32332 | ICPIM-32151 Format 'New Tile' - Configure Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:02 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32331 | ICPIM-32151 Format 'New Tile' - Configure Dimensions properties | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 03:01 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32873
Test Case | ICPIM-32330 | ICPIM-32151 Format 'New Tile' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 03:00 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32329 | ICPIM-32151 Format 'New Plugin' - Configure Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:59 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32328 | ICPIM-32151 Format 'New Plugin' - Configure Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:59 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32939
Test Case | ICPIM-32327 | ICPIM-32151 Format 'New Plugin' - Configure Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:58 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32326 | ICPIM-32151 Format 'New Plugin' - Configure Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:58 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32873
Test Case | ICPIM-32325 | ICPIM-32151 Format 'New Plugin' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:57 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32324 | ICPIM-32151 Format 'New Equipment' - Configure Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:56 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32323 | ICPIM-32151 Format 'New Equipment' - Configure Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:55 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33258
Test Case | ICPIM-32322 | ICPIM-32151 Format 'New Equipment' - Configure Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:55 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32321 | ICPIM-32151 Format 'New Equipment' - Configure Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:54 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33269
Test Case | ICPIM-32320 | ICPIM-32151 Format 'New Equipment' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:53 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-33796
Test Case | ICPIM-32319 | ICPIM-32151 Format 'New Enclosure' - Configure Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:53 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32318 | ICPIM-32151 Format 'New Enclosure' - Configure Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:52 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32939
Test Case | ICPIM-32317 | ICPIM-32151 Format 'New Enclosure' - Configure Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:51 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-32316 | ICPIM-32151 Format 'New Enclosure' - Configure Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:50 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33170
Test Case | ICPIM-32315 | ICPIM-32151 Format 'New Enclosure' - Configure Attributes properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:50 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32314 | ICPIM-32151 Format 'New Connector' - Configure Font properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:48 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32313 | ICPIM-32151 Format 'New Connector' - Configure Image properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:48 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32939
Test Case | ICPIM-32312 | ICPIM-32151 Format 'New Connector' - Configure Fill properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-15 02:47 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-32311 | ICPIM-32151 Format 'New Connector' - Configure Dimensions properties | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-15 02:46 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32873
Test Case | ICPIM-32310 | ICPIM-32306 Datastores - Browser (Deleted datastore disappears on the Browser) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-12 16:18 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32309 | ICPIM-32306 Datastores - Browser (New created datastore displays on the Browser) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-12 16:18 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-32308 | ICPIM-32306 Datastores - Browser (Turn on/off "Show on Browser" options) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-12 16:17 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-32307 | ICPIM-32306 Datastores - Browser (Display datastore information) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-12 16:16 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32305 | ICPIM-32297 Configure Log Archive - Maintenance the log | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-12 15:14 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32304 | ICPIM-32297 Configure Log Archive - Enable Archive Maintenance | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-12 15:08 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32301 | ICPIM-32297 Configure Log Archive - Archive the log | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-12 14:28 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32300 | ICPIM-32297 Configure Log Archive - Do not archive the log | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-12 13:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32295 | ICPIM-31706 Move Attributes - Clear Source Attributes | All |  | Trinh Nguyen | An Vo | Windows Client | Blocker | 2014-12-12 10:58 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-33961, ICPIM-34075, ICPIM-34262, ICPIM-33654
Test Case | ICPIM-32294 | ICPIM-31706 Move Attributes - Move iDiscover | All |  | Trinh Nguyen | An Vo | Windows Client | Blocker | 2014-12-12 10:57 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-33961, ICPIM-34075, ICPIM-34262, ICPIM-33654
Test Case | ICPIM-32290 | ICPIM-31706 Move Attributes - Over Looks | All |  | An Vo | An Vo | Windows Client | Fail | 2014-12-12 10:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33602
Test Case | ICPIM-32289 | ICPIM-31706 Move Attributes - Open Dialog | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-12 10:55 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32287 | ICPIM-32283 Query for Power Circuits | Stretch |  | Loan Ha | Loan Ha | Data Exchange Agent, Web Service | Pass | 2014-12-12 10:12 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-32286 | ICPIM-32283 Query for Rack Contents | Stretch |  | Loan Ha | Loan Ha | Data Exchange Agent, Web Service | Pass | 2014-12-12 10:05 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-32285 | ICPIM-32283 Query for Temperature | Stretch |  | Loan Ha | Loan Ha | Data Exchange Agent, Web Service | Pass | 2014-12-12 10:03 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-32284 | ICPIM-32283 Query for Power | Stretch |  | Loan Ha | Loan Ha | Data Exchange Agent, Web Service | Pass | 2014-12-12 10:02 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-32271 | ICPIM-32151 Template Management - Template Object Tree - CAD Objects - CAD Objects Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 03:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33088
Test Case | ICPIM-32269 | ICPIM-32151 Template Management - Template Object Tree - CAD Objects - CAD Objects Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:08 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32268 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu -Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:07 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32267 | ICPIM-32151 Template Management - Template Object Tree: CAD Objects Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 03:07 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-33082, ICPIM-33098
Test Case | ICPIM-32265 | ICPIM-32151 Template Management - Template Object Tree: CAD Objects Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:06 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32264 | ICPIM-32151 Template Management - Template Object Tree: CAD Objects Folder Context Menu - New CAD Object | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:05 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-33305
Test Case | ICPIM-32262 | ICPIM-32151 Template Management - Template Object Tree: CAD Objects Folder Context Menu - New CAD Object Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:04 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32261 | ICPIM-32151 Template Management - Template Object Tree - 3D Objects - 3D Objects Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 03:04 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33% |  | ICPIM-33088
Test Case | ICPIM-32259 | ICPIM-32151 Template Management - Template Object Tree - 3D Objects - 3D Objects Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:03 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32258 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:02 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32257 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 03:01 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33082, ICPIM-33098
Test Case | ICPIM-32256 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 03:01 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32255 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu - New 3D Object | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32254 | ICPIM-32151 Template Management - Template Object Tree: 3D Objects Folder Context Menu - New 3D Object Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:58 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32253 | ICPIM-32151 Template Management - Template Object Tree - Tiles - Tiles Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:56 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-33088
Test Case | ICPIM-32252 | ICPIM-32151 Template Management - Template Object Tree - Tiles - Tile Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:55 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32251 | ICPIM-32151 Template Management - Template Object Tree: Tiles Folder Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:53 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32250 | ICPIM-32151 Template Management - Template Object Tree: Tiles Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:52 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-33082, ICPIM-33098
Test Case | ICPIM-32249 | ICPIM-32151 Template Management - Template Object Tree: Tiles Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:51 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32248 | ICPIM-32151 Template Management - Template Object Tree: Tiles Folder Context Menu - New Tile | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:51 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32247 | ICPIM-32151 Template Management - Template Object Tree: Tiles Folder Context Menu - New Tile Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:50 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32246 | ICPIM-32151 Template Management - Template Object Tree - Plugins - Plugins Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:49 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-33088
Test Case | ICPIM-32245 | ICPIM-32151 Template Management - Template Object Tree - Plugins - Plugins Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:48 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32244 | ICPIM-32151 Template Management - Template Object Tree: Plugins Folder Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:48 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32243 | ICPIM-32151 Template Management - Template Object Tree: Plugins Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:47 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-33082, ICPIM-33085
Test Case | ICPIM-32242 | ICPIM-32151 Template Management - Template Object Tree: Plugins Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33031
Test Case | ICPIM-32241 | ICPIM-32151 Template Management - Template Object Tree: Plugins Folder Context Menu - New Plugin | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:45 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32240 | ICPIM-32151 Template Management - Template Object Tree: Plugins Folder Context Menu - New Plugin Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:45 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32239 | ICPIM-32151 Template Management - Template Object Tree - Equipment - Equipment Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:44 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-33088
Test Case | ICPIM-32238 | ICPIM-32151 Template Management - Template Object Tree - Equipments - Equipments Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:43 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32237 | ICPIM-32151 Template Management - Template Object Tree: Equipments Folder Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:40 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32236 | ICPIM-32151 Template Management - Template Object Tree: Equipments Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:39 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-33028
Test Case | ICPIM-32235 | ICPIM-32151 Template Management - Template Object Tree: Equipments Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:38 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-33031
Test Case | ICPIM-32234 | ICPIM-32151 Template Management - Template Object Tree: Equipments Folder Context Menu - New Equipment | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:37 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32233 | ICPIM-32151 Template Management - Template Object Tree: Equipments Folder Context Menu - New Equipment Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:36 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32232 | ICPIM-32151 Template Management - Template Object Tree - Enclosures - Enclosures Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:35 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32231 | ICPIM-32151 Template Management - Template Object Tree - Enclosures - Enclosure Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:34 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32230 | ICPIM-32151 Template Management - Template Object Tree: Enclosures Folder Context Menu -Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:33 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32229 | ICPIM-32151 Template Management - Template Object Tree: Enclosures Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:32 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-32228 | ICPIM-32151 Template Management - Template Object Tree: Enclosures Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33031
Test Case | ICPIM-32227 | ICPIM-32151 Template Management - Template Object Tree: Enclosures Folder Context Menu - New Enclosure | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:30 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32226 | ICPIM-32151 Template Management - Template Object Tree: Enclosures Folder Context Menu - New Enclosure Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:29 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32225 | ICPIM-32151 Template Management - Template Object Tree - Connectors - Connectors Context Menu - Export Template | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:28 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32224 | ICPIM-32151 Template Management - Template Object Tree - Connectors - Connectors Context Menu - Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:27 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32223 | ICPIM-32151 Template Management - Template Object Tree: Connectors Folder Context Menu -Delete | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:26 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32222 | ICPIM-32151 Template Management - Template Object Tree: Context Menu - Refresh | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:24 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32221 | ICPIM-32151 Template Management - Template Object Tree: Connectors Folder Context Menu - Export Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:23 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33028
Test Case | ICPIM-32220 | ICPIM-32151 Template Management - Template Object Tree: Connectors Folder Context Menu - Import Template to Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-12 02:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33031
Test Case | ICPIM-32219 | ICPIM-32151 Template Management - Template Object Tree: Connectors Folder Context Menu - New Connector | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:20 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32218 | ICPIM-32151 Template Management - Template Object Tree: Connectors Folder Context Menu - New Connector Folder | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-12 02:15 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-32217 | ICPIM-32214 Navigation - View Dictionary (Update information) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-11 17:02 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32216 | ICPIM-32214 Navigation - View Dictionary (Display information) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-11 17:01 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-32215 | ICPIM-32214 Navigation - View Dictionary (Open View dialog) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-11 17:00 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32213 | ICPIM-31706 Move - Scheduled (Specify Existing Work Project) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-11 16:01 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32212 | ICPIM-31706 Move - Scheduled (Create New Work Project) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-11 16:01 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32197 | ICPIM-32187 Rename Associated Assets - Update asset names to CPIM window | Stretch |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-12-11 10:08 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31973, ICPIM-32848
Test Case | ICPIM-32196 | ICPIM-32187 Rename Associated Assets - Rename assets if exiting commissioning | Stretch |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-12-11 10:06 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-32195 | ICPIM-32187 Rename Associated Assets - Rename assets after completed WAs assignment or completed CR | Stretch |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-12-11 10:06 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-32517
Test Case | ICPIM-32194 | ICPIM-32187 Rename Associated Assets - Auto-Rename multiple assets | Stretch |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-12-11 10:04 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32111
Test Case | ICPIM-32193 | ICPIM-32187 Rename Associated Assets - Rename assets at Single CR page | Stretch |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-12-11 10:03 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31976
Test Case | ICPIM-32192 | ICPIM-32187 Rename Associated Assets - Rename assets at Plan page | Stretch |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-12-11 10:03 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32360, ICPIM-32363
Test Case | ICPIM-32191 | ICPIM-23410 Single CR - Rename Associated Assets |  |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2014-12-11 09:55 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-19819
Test Case | ICPIM-32189 | ICPIM-32187 Rename Work Projects | Stretch |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-12-11 09:48 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32188 | ICPIM-32187 Rename Associated Assets - Unable to rename associated assets at Asset Allocation and Work Project pages | Stretch |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-12-11 09:47 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32165 | ICPIM-32151 Template Management - Template Object Tree - CAD Objects - CAD Objects Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:09 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32164 | ICPIM-32151 Template Management - Template Object Tree - CAD Objects - CAD Objects Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:08 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-32163 | ICPIM-32151 Template Management - Template Object Tree - 3D Objects - 3D Objects Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:07 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32162 | ICPIM-32151 Template Management - Template Object Tree - 3D Objects - 3D Objects Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:06 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32161 | ICPIM-32151 Template Management - Template Object Tree - Tiles - Tiles Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:05 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32160 | ICPIM-32151 Template Management - Template Object Tree - Tiles - Tiles Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:05 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32159 | ICPIM-32151 Template Management - Template Object Tree - Plugins - Plugins Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:04 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32158 | ICPIM-32151 Template Management - Template Object Tree - Plugins - Plugins Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:03 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32157 | ICPIM-32151 Template Management - Template Object Tree - Equipment - Equipment Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:02 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32156 | ICPIM-32151 Template Management - Template Object Tree - Equipment - Equipment Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-11 03:01 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-33010
Test Case | ICPIM-32155 | ICPIM-32151 Template Management - Template Object Tree - Enclosurer - Enclosurer Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 03:00 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32154 | ICPIM-32151 Template Management - Template Object Tree - Enclosurer - Enclosurer Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 02:59 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32153 | ICPIM-32151 Template Management - Template Object Tree - Connectors - Connectors Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 02:58 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32152 | ICPIM-32151 Template Management - Template Object Tree - Connectors - Connectors Folder Context Menu | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-11 02:56 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-32117 | ICPIM-32097 Cabinet Space on Row (Center point is outside the row) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 15:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32116 | ICPIM-32097 Cabinet Space on Row (Center point is inside the row) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 15:38 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32115 | ICPIM-32097 Cabinet Space on Row (Include Future Commission) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-12-10 15:31 | 900 | 3300 | 0 | 100% | 900 | 3300 | 0 | 100% |  | ICPIM-32171
Test Case | ICPIM-32114 | ICPIM-32097 Cabinet Space on Row (Include Future Decommission) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 15:04 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32110 | ICPIM-32097 Cabinet Space on Row (AreaUnit = Feet) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 14:47 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32109 | ICPIM-32097 Cabinet Space on Row (AreaUnit = Inches) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 14:47 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32108 | ICPIM-32097 Cabinet Space on Row (AreaUnit = Meters) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 14:47 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32107 | ICPIM-32097 Cabinet Space on Row (AreaUnit = Millimeters) | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 14:24 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32102 | ICPIM-32097 Creating new datastore with "Available Row Width" syscat | Stretch |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-12-10 13:49 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-32032 | ICPIM-32022 Template Management - Workspace: Accessing the Front, Back, or Top view of the object using Elevation Bar | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:13 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32031 | ICPIM-32022 Template Management - Workspace: Work space context menu - Export All Folders | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:12 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-32030 | ICPIM-32022 Template Management - Workspace: Work space context menu - Import Folders | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:11 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32029 | ICPIM-32022 Template Management - Workspace: Work space context menu - Import Template by Default Location | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:10 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-32028 | ICPIM-32022 Template Management - Workspace: Work space context menu - Zoom to Selection | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:09 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-32027 | ICPIM-32022 Template Management - Workspace: Work space context menu - Fit to Window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:09 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-32026 | ICPIM-32022 Template Management - Workspace: Work space context menu - Settings: Define Decimal Places | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:08 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-32025 | ICPIM-32022 Template Management - Workspace: Work space context menu - Settings: Define Units of Measurement | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:06 | 1800 | 840 | 960 | 46% | 1800 | 840 | 960 | 46%
Test Case | ICPIM-32024 | ICPIM-32022 Template Management - Workspace: Work space context menu - Settings: Manage Equipment Manufacturers | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:05 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-32023 | ICPIM-32022 Template Management - Workspace: Work space context menu - Settings: Configure the Workspace Background | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 03:04 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-32021 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Connection Points | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 02:59 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32020 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Door | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 02:59 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32019 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Datalink | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 02:58 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32018 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Rectangle | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-10 02:57 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-32017 | ICPIM-32007 Template Management - Toolbar: Import Status | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-10 02:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32045
Test Case | ICPIM-32016 | ICPIM-32007 Template Management - Toolbar: Unload Templates | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-10 02:03 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32044
Test Case | ICPIM-32015 | ICPIM-32007 Template Management - Toolbar: Import Templates | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-10 02:02 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32043
Test Case | ICPIM-32014 | ICPIM-32007 Template Management - Toolbar: Clear All | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-10 02:01 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32013 | ICPIM-32007 Template Management - Toolbar: Select None | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-10 02:00 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32012 | ICPIM-32007 Template Management - Toolbar: Select All | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-10 01:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-32011 | ICPIM-32006 Template Management - List Folder: List Folder button | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-10 01:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-32010 | ICPIM-32005 Template Management - Search for Templates in Package | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-10 01:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32040, ICPIM-32041
Test Case | ICPIM-32009 | ICPIM-32004 Template Management - Search For Packages in Folder: search folder | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-12-10 01:52 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32039
Test Case | ICPIM-32008 | ICPIM-32004 Template Management - Search For Packages in Folder: folder lists | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-10 01:51 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31994 | ICPIM-31791 Configure Standard Report - Dialog Options (Type) | All |  | An Vo | An Vo | Windows Client | New | 2014-12-09 16:04 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31993 | ICPIM-31791 Configure Standard Report - Dialog Options (Return as Text) | All |  | An Vo | An Vo | Windows Client | New | 2014-12-09 15:36 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31992 | ICPIM-31791 Configure Standard Report - Dialog Options (Minimize and Maximize) | All |  | An Vo | An Vo | Windows Client | New | 2014-12-09 15:14 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31989 | ICPIM-31791 Configure Standard Report - Dialog Options (Hide Column) | All |  | An Vo | An Vo | Windows Client | New | 2014-12-09 14:55 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31981 | ICPIM-31791 Configure Custom Report | All |  | An Vo | An Vo | Windows Client | New | 2014-12-09 14:10 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31945 | ICPIM-31944 General Reports - Disconnected Network Equipment (By Location) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-09 10:04
Test Case | ICPIM-31943 | ICPIM-31942 General Reports - Device Connectivity (By Location) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-09 10:01
Test Case | ICPIM-31941 | ICPIM-31940 General Reports - Device Connectivity (By Enclosure) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-09 09:50
Test Case | ICPIM-31939 | ICPIM-31938 Auto Report - One Level | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-09 09:18
Test Case | ICPIM-31937 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Image | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-09 03:39 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-31936 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Label | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-09 03:37 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-31935 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Slot | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-09 03:37 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-32775
Test Case | ICPIM-31934 | ICPIM-31933 Template Management - Designer - Tool Bar: Add Connector | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-09 03:35 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-31932 | ICPIM-31929 Template Management - Designer - Search Templates: Select template on the Template Manager Search dialog | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-09 03:30 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-31931 | ICPIM-31929 Template Management - Designer - Search Templates by clicking Search Templates button | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-12-09 03:29 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31930 | ICPIM-31929 Template Management - Designer - Search Templates by pressing Enter key | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-12-09 03:28 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-32033
Test Case | ICPIM-31928 | ICPIM-31927 Server Stats | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:13
Test Case | ICPIM-31926 | ICPIM-31925 Server Space | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:12
Test Case | ICPIM-31924 | ICPIM-31923 Server Power | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:11
Test Case | ICPIM-31922 | ICPIM-31921 Server Network | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:11
Test Case | ICPIM-31920 | ICPIM-31919 Server Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:10
Test Case | ICPIM-31918 | ICPIM-31917 Server Cooling | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:09
Test Case | ICPIM-31916 | ICPIM-31915 Row Stats | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:08
Test Case | ICPIM-31914 | ICPIM-31913 Row Space | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:07
Test Case | ICPIM-31912 | ICPIM-31911 Row Power | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:07
Test Case | ICPIM-31910 | ICPIM-31909 Row Network | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:06
Test Case | ICPIM-31908 | ICPIM-31907 Row Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:05
Test Case | ICPIM-31906 | ICPIM-31905 Row Cooling | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:04
Test Case | ICPIM-31904 | ICPIM-31903 PDU Space | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:03
Test Case | ICPIM-31902 | ICPIM-31901 PDU Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:02
Test Case | ICPIM-31900 | ICPIM-31899 PDU Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 01:00
Test Case | ICPIM-31898 | ICPIM-31897 HVAC Power | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:57
Test Case | ICPIM-31896 | ICPIM-31895 HVAC Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:56
Test Case | ICPIM-31894 | ICPIM-31893 HVAC Cooling | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:55
Test Case | ICPIM-31892 | ICPIM-31891 Enclosure Stats | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:53
Test Case | ICPIM-31890 | ICPIM-31889 Enclosure Space | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:52
Test Case | ICPIM-31888 | ICPIM-31887 Enclosure Power | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:51
Test Case | ICPIM-31886 | ICPIM-31885 Enclosure Network | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:50
Test Case | ICPIM-31884 | ICPIM-31883 Enclosure Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:48
Test Case | ICPIM-31882 | ICPIM-31881 Enclosure Cooling | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:48
Test Case | ICPIM-31880 | ICPIM-31879 Data Center Stats | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:47
Test Case | ICPIM-31878 | ICPIM-31877 Data Center Space | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:46
Test Case | ICPIM-31876 | ICPIM-31875 Data Center Power | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:45
Test Case | ICPIM-31874 | ICPIM-31873 Data Center Data | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:44
Test Case | ICPIM-31872 | ICPIM-31871 Data Center Cooling | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:43
Test Case | ICPIM-31870 | ICPIM-31869 Simulated Power Failure Report (By Device) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:40
Test Case | ICPIM-31868 | ICPIM-31867 Power Strip Connectivity (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:39
Test Case | ICPIM-31866 | ICPIM-31865 Power Strip Connectivity (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:38
Test Case | ICPIM-31864 | ICPIM-31863 PDU Breaker Draw (By PDU) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:37
Test Case | ICPIM-31862 | ICPIM-31861 PDU Breaker Draw (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:36
Test Case | ICPIM-31860 | ICPIM-31859 PDU Breaker Connectivity And Draw (By PDU) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:32
Test Case | ICPIM-31858 | ICPIM-31857 PDU Breaker Connectivity And Draw (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:31
Test Case | ICPIM-31856 | ICPIM-31855 PDU Breaker Connectivity (By PDU) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:30
Test Case | ICPIM-31854 | ICPIM-31853 PDU Breaker Connectivity (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:29
Test Case | ICPIM-31852 | ICPIM-31851 Enclosure Future Drawing Past 80% (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:28
Test Case | ICPIM-31850 | ICPIM-31849 Enclosure Future Drawing Past 80% (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:27
Test Case | ICPIM-31848 | ICPIM-31847 Enclosure Drawing Past 80% (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:25
Test Case | ICPIM-31846 | ICPIM-31845 Enclosure Drawing Past 80% (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:24
Test Case | ICPIM-31844 | ICPIM-31843 Enclosure Draw (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:22
Test Case | ICPIM-31842 | ICPIM-31841 Enclosure Draw (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:21
Test Case | ICPIM-31840 | ICPIM-31839 Device Power Connectivity (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:20
Test Case | ICPIM-31838 | ICPIM-31837 Device Power Connectivity (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:19
Test Case | ICPIM-31836 | ICPIM-31835 Device Draw (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:18
Test Case | ICPIM-31834 | ICPIM-31833 Device Draw (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:17
Test Case | ICPIM-31832 | ICPIM-31831 Device Draw (By Device) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:14
Test Case | ICPIM-31830 | ICPIM-31829 Available Power (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-09 00:12
Test Case | ICPIM-31828 | ICPIM-31827 Report - Save Report to HTML | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-09 00:10
Test Case | ICPIM-31826 | ICPIM-31825 Report - Regenerate Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-09 00:08
Test Case | ICPIM-31824 | ICPIM-31823 Report - Run Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Invalid | 2014-12-09 00:05
Test Case | ICPIM-31822 | ICPIM-31821 Report - Print Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-09 00:04
Test Case | ICPIM-31820 | ICPIM-31819 Report - Cancel Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Invalid | 2014-12-09 00:02
Test Case | ICPIM-31818 | ICPIM-31817 Report - Remove Categories that is used by reports | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-09
Test Case | ICPIM-31816 | ICPIM-31815 Report - Add System Categories | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:59
Test Case | ICPIM-31814 | ICPIM-31813 Report - Configure System Category Parameters | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:58
Test Case | ICPIM-31812 | ICPIM-31811 Report - Chaining System Categories | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:57
Test Case | ICPIM-31810 | ICPIM-31809 Report - Add Category | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:56
Test Case | ICPIM-31808 | ICPIM-31807 Available Power (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:55
Test Case | ICPIM-31806 | ICPIM-31805 Report - Set Category/Table/Class | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:54
Test Case | ICPIM-31804 | ICPIM-31803 Report - Run Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:53 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-31802 | ICPIM-31801 PE Search | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:52
Test Case | ICPIM-31800 | ICPIM-31799 Report - Remove Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:52
Test Case | ICPIM-31798 | ICPIM-31797 PE Optimization | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:51
Test Case | ICPIM-31796 | ICPIM-31795 Report - Import Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:51
Test Case | ICPIM-31794 | ICPIM-31793 Report - Export Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:50 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31792 | ICPIM-31791 Configure Report - Open Configure Report dialog | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:48 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31790 | ICPIM-31789 Report - Clone Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:45 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31788 | ICPIM-31787 Report - Weight Reports - Enclosure Loaded Past 80% (By Row) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:40
Test Case | ICPIM-31786 | ICPIM-31785 Report - Weight Reports - Enclosure Loaded Past 80% (By Location) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:39
Test Case | ICPIM-31784 | ICPIM-31783 Report - Virtual Machine Reports - Virtual Machine (By Entire Database) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:34
Test Case | ICPIM-31782 | ICPIM-31781 Report - Space Report - Space Utilization (By Row) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:31
Test Case | ICPIM-31780 | ICPIM-31779 Report - Space Report - Space Utilization (By Location) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:31
Test Case | ICPIM-31778 | ICPIM-31777 Report - Space Report - Space Utilization (By Enclosure) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:29
Test Case | ICPIM-31776 | ICPIM-31775 Report - Space Report - Space Layout Summary (By Row) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:27
Test Case | ICPIM-31774 | ICPIM-31773 Report - Space Report - Space Layout Summary (By Location) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:26
Test Case | ICPIM-31772 | ICPIM-31771 Weight Utilization (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:26
Test Case | ICPIM-31770 | ICPIM-31769 Report - Space Report - Space Layout Summary (By Enclosure) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:25
Test Case | ICPIM-31768 | ICPIM-31767 Weight Utilization (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:25
Test Case | ICPIM-31766 | ICPIM-31765 Weight Utilization (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:24
Test Case | ICPIM-31764 | ICPIM-31763 Report - Space Report - Space Future Layout Summary (By Row) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:23
Test Case | ICPIM-31762 | ICPIM-31761 Weight Distribution (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:23
Test Case | ICPIM-31760 | ICPIM-31759 Report - Space Report - Space Future Layout Summary (By Location) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:23
Test Case | ICPIM-31758 | ICPIM-31757 Weight Distribution (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:22
Test Case | ICPIM-31756 | ICPIM-31755 Report - Space Report - Space Future Layout Summary (By Enclosure) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 23:21
Test Case | ICPIM-31754 | ICPIM-31753 Weight Distribution (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:20
Test Case | ICPIM-31752 | ICPIM-31751 Future Weight Distribution (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:19
Test Case | ICPIM-31750 | ICPIM-31749 Future Weight Distribution (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:19
Test Case | ICPIM-31748 | ICPIM-31747 Future Weight Distribution (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:17
Test Case | ICPIM-31746 | ICPIM-31745 Future Enclosures Loaded Past 80% (By Row) report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:15
Test Case | ICPIM-31744 | ICPIM-31743 Future Enclosures Loaded Past 80% (By Location) report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 23:13
Test Case | ICPIM-31742 | ICPIM-31735 Commission Search | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 21:45
Test Case | ICPIM-31741 | ICPIM-31740 Report - Space Report - Contiguous Space (By Row) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 21:42
Test Case | ICPIM-31739 | ICPIM-31738 Report - Space Report - Contiguous Space (By Location) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 21:40
Test Case | ICPIM-31737 | ICPIM-31736 Report - Space Report - Contiguous Space (By Enclosure) | All |  | Mai Nguyen | Mai Nguyen | Windows Client | New | 2014-12-08 21:37
Test Case | ICPIM-31734 | ICPIM-31733 Blade Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 21:35
Test Case | ICPIM-31732 | ICPIM-31731 Optimization Reports - PE (By Device) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 19:28
Test Case | ICPIM-31730 | ICPIM-31729 Log - CPIM Log Details | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 19:25
Test Case | ICPIM-31728 | ICPIM-31727 Report - Lease Report | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 19:21
Test Case | ICPIM-31726 | ICPIM-31725 Report - Lease - Lease End (6 Months) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 19:14
Test Case | ICPIM-31724 | ICPIM-31723 Report - Lease - Lease End (3 Months) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 18:06
Test Case | ICPIM-31722 | ICPIM-31721 Report - Lease - Lease End (12 Months) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 18:04
Test Case | ICPIM-31720 | ICPIM-31719 Commissioning Reports - Commission Resource List | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 17:56
Test Case | ICPIM-31718 | ICPIM-30711 Commission - Configure Commission Work Flow: Configure Group functionality | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-12-08 17:30 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31717 | ICPIM-31716 System Category Report | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 16:49
Test Case | ICPIM-31715 | ICPIM-31714 Commissioning Reports - Commission Parts List | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 16:47
Test Case | ICPIM-31713 | ICPIM-31078 Report - Auto Reports: One Level | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | New | 2014-12-08 16:38 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31711 | ICPIM-31706 Move - Below | All |  | An Vo | An Vo | Windows Client | Blocker | 2014-12-08 15:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31710 | ICPIM-31706 Move - Above | All |  | An Vo | An Vo | Windows Client | Blocker | 2014-12-08 15:41 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-29345
Test Case | ICPIM-31709 | ICPIM-31706 Move - Within | All |  | Rachna Muthanna | An Vo | Windows Client | Pass | 2014-12-08 15:40 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31708 | ICPIM-31706 Move - Select Source Item | All |  | Rachna Muthanna | An Vo | Windows Client | Pass | 2014-12-08 15:38 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31707 | ICPIM-31706 Move Connection | All |  | An Vo | An Vo | Windows Client | Fail | 2014-12-08 15:37 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-33334
Test Case | ICPIM-31703 | ICPIM-31653 Commission - Commission Swap (Functionality) | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-12-08 13:39 | 1500 | 3420 | 0 | 100% | 1500 | 3420 | 0 | 100% |  | ICPIM-31702
Test Case | ICPIM-31694 | ICPIM-31692 Auto Create (Edit Dictionary) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-08 11:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31693 | ICPIM-31692 Auto Create (Create) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-08 11:20 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31687 | ICPIM-31685 Cable Coloring - Specify | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-08 10:32 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31686 | ICPIM-31685 Cable Coloring - By IT Service | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-08 10:31 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31679 | ICPIM-31360 Report - General: Device Connectivity (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 03:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31678 | ICPIM-31360 Report - General: Device Connectivity (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 03:27 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31677 | ICPIM-31360 Report - General: Device Connectivity (By Enclosure): multiple selected enclosures | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 03:25 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31676 | ICPIM-31360 Report - General: Device Connectivity (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-08 03:24 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31658 | ICPIM-31653 Commission - Commission Swap (Overview of the Commission Editor window for Commission Swap) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-05 16:32 | 1200 | 1740 | 0 | 100% | 1200 | 1740 | 0 | 100%
Test Case | ICPIM-31657 | ICPIM-31653 Commission - Commission Swap (Open Commission Editor window from the Trace dialog) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-05 16:31 | 900 | 2040 | 0 | 100% | 900 | 2040 | 0 | 100%
Test Case | ICPIM-31656 | ICPIM-31653 Commission - Commission Swap (Open Commission Editor window from the Browser dialog) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-05 16:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31655 | ICPIM-31653 Commission - Commission Swap (Open Commission Editor window from the ancestry bar) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-05 16:31 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100%
Test Case | ICPIM-31654 | ICPIM-31653 Commission - Commission Swap (Open Commission Editor window from the Navigator) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-05 16:30 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31639 | ICPIM-31629 Circulating Instance Configuration (Location based - Enclosure) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-05 13:24 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-33176
Test Case | ICPIM-31638 | ICPIM-31629 Circulating Instance Configuration (Location based - Row) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-05 13:18 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-33176
Test Case | ICPIM-31637 | ICPIM-31629 Circulating Instance Configuration (Location based - Datacenter) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-05 12:55 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-33176
Test Case | ICPIM-31636 | ICPIM-31629 Circulating Instance Configuration (Location based - Site) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-05 12:53 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-33729
Test Case | ICPIM-31635 | ICPIM-31632 Asset Management - CSV (Create) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-05 11:26 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31634 | ICPIM-31632 Asset Management - CSV (Configuration) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-12-05 11:24 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-33212
Test Case | ICPIM-31633 | ICPIM-31632 Asset Management - CSV (Browse For File) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-05 11:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31622 | ICPIM-31360 Report - General: Template GUID List | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:54 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31621 | ICPIM-31360 Report - General: Switch Utilization (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31620 | ICPIM-31360 Report - General: Switch Utilization (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31619 | ICPIM-31360 Report - General: Switch Utilization (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:52 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31618 | ICPIM-31360 Report - General: Switch Utilization (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:51 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31617 | ICPIM-31360 Report - General: Switch Port Circuit Trace (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:50 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31616 | ICPIM-31360 Report - General: Switch Port Circuit Trace (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-05 02:49 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31615 | ICPIM-31536 Commission - Commission Within (Commission equipment items to a location that has no available space) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-04 17:23 | 2100 | 2580 | 0 | 100% | 2100 | 2580 | 0 | 100%
Test Case | ICPIM-31614 | ICPIM-31536 Commission - Commission Within (Commission multiple equipment items to a location that has available space) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-04 17:22 | 2100 | 1860 | 240 | 88% | 2100 | 1860 | 240 | 88%
Test Case | ICPIM-31613 | ICPIM-31536 Commission - Commission Within (Commission an incorrect equipment item to the selected location that has available space) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-04 17:21 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-33016
Test Case | ICPIM-31612 | ICPIM-31536 Commission - Commission Within (Commission a correct equipment item to the selected location that has available space) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-04 17:19 | 1800 | 2100 | 0 | 100% | 1800 | 2100 | 0 | 100%
Test Case | ICPIM-31611 | ICPIM-31536 Commission - Commission Within (Open Commission Editor window from the ancestry bar) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-04 17:18 | 900 | 1140 | 0 | 100% | 900 | 1140 | 0 | 100%
Test Case | ICPIM-31608 | ICPIM-31610 Template Instance Editor - Viewer Toolbar | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 16:14 | 10800 | 10800 | 0 | 100% | 10800 | 10800 | 0 | 100%
Test Case | ICPIM-31604 | ICPIM-31610 Template Instance Editor - Viewer | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-12-04 15:46 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-32984
Test Case | ICPIM-31603 | ICPIM-31609 Template Instance Editor - Remove Connectors | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 15:02 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31602 | ICPIM-31601 Asset Management - Autonumber (Simple with Number) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-04 14:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31600 | ICPIM-31599 Asset Management - Autonumber (Simple) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-04 14:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31598 | ICPIM-31597 Asset Management - Autonumber (IP) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-12-04 14:52 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-33225
Test Case | ICPIM-31596 | ICPIM-31595 Asset Management - Autonumber (Auto Label Scheme) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-04 14:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31592 | ICPIM-31609 Template Instance Editor - Configure Instance | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 13:26 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31590 | ICPIM-31609 Template Instance Editor - Results Display | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 12:33 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31575 | ICPIM-31518 Template Instance Editor - Search within Enclosure | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 09:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31574 | ICPIM-31518 Template Instance Editor - Search within Row | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-04 09:24 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31563 | ICPIM-31360 Report - General: Switch Information (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31562 | ICPIM-31360 Report - General: Switch Information (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:52 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31561 | ICPIM-31360 Report - General: Switch Information (By Location): many selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:51 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31560 | ICPIM-31360 Report - General: Switch Information (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:51 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31559 | ICPIM-31360 Report - General: Switch Details – Network Interface (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:49 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31558 | ICPIM-31360 Report - General: Switch Details – Network Interface (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:48 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31557 | ICPIM-31360 Report - General: Switch Details – Network Interface (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:47 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31556 | ICPIM-31360 Report - General: Switch Details – Network Interface (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:47 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31555 | ICPIM-31360 Report - General: Switch Connectivity (Entire Database) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:46 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31554 | ICPIM-31360 Report - General: Switch Connectivity (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:44 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31553 | ICPIM-31360 Report - General: Switch Connectivity (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31552 | ICPIM-31360 Report - General: Switch Connectivity (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:42 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31551 | ICPIM-31360 Report - General: Switch Connectivity (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:41 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31550 | ICPIM-31360 Report - General: Switch Connectivity (By Enclosure): multiple selected enclosures | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:39 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31549 | ICPIM-31360 Report - General: Switch Connectivity (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-04 02:38 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31542 | ICPIM-31536 Commission - Commission Within (Open Commission Editor window from the Trace) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 17:24 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31541 | ICPIM-31536 Commission - Commission Within (Open Commission Editor window from the Browser) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 17:23 | 600 | 840 | 0 | 100% | 600 | 840 | 0 | 100%
Test Case | ICPIM-31540 | ICPIM-31536 Commission - Commission Within (Open Commission Editor window from the Navigator) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 17:23 | 1200 | 1560 | 0 | 100% | 1200 | 1560 | 0 | 100%
Test Case | ICPIM-31539 | ICPIM-31518 Template Instance Editor - Search within Datacenter | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 16:54 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31538 | ICPIM-31518 Template Instance Editor - Search within Site | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 16:47 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31537 | ICPIM-31518 Template Instance Editor - Search by Template | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 16:40 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31535 | ICPIM-31518 Template Instance Editor - Search by Manufacturer | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 16:31 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31534 | ICPIM-30276 Design - Color Cables - Set Color for multiple cables | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-12-03 16:29 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31533 | ICPIM-31518 Template Instance Editor - Search by Class | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 16:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31532 | ICPIM-30276 Design - Color Cables - Set Color for a single cable | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-12-03 15:59 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31531 | ICPIM-31238 Manual Naming - Logging | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31530 | ICPIM-31525 Commission - Commission Mirror (Clone and commission multiple equipment items) | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-12-03 15:46 | 1800 | 2160 | 0 | 100% | 1800 | 2160 | 0 | 100%
Test Case | ICPIM-31529 | ICPIM-31525 Commission - Commission Mirror (Clone and commission a single equipment item) | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-12-03 15:45 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100%
Test Case | ICPIM-31528 | ICPIM-31525 Commission - Commission Mirror (Open Commission Editor window from the ancestry bar) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 15:42 | 1800 | 1740 | 60 | 96% | 1800 | 1740 | 60 | 96%
Test Case | ICPIM-31527 | ICPIM-31525 Commission - Commission Mirror (Open Commission Editor window from the Browser) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 15:42 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-31526 | ICPIM-31525 Commission - Commission Mirror (Open Commission Editor window from the Navigator) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-03 15:41 | 1500 | 2220 | 0 | 100% | 1500 | 2220 | 0 | 100%
Test Case | ICPIM-31524 | ICPIM-30276 Design - Color Cables - Filter Connections | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-12-03 15:34 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31523 | ICPIM-31238 Manual Naming - Use existing names | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:26 | 900 | 900 | 900 | 50% | 900 | 900 | 900 | 50%
Test Case | ICPIM-31522 | ICPIM-31238 Manual Naming - Copy Connection | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:25 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31605
Test Case | ICPIM-31521 | ICPIM-31238 Manual Naming - Create from Library Item | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:24 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31520 | ICPIM-31238 Manual Naming - Scheme | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:23 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31519 | ICPIM-31238 Manual Naming - Class | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:23 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31517 | ICPIM-31238 Manual Naming - Drop Zone, Select All, Remove Selection | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:22 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31516 | ICPIM-31238 Manual Naming - Create items | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:21 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31515 | ICPIM-31238 Manual Naming - Launch Create window | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-03 15:20 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31511 | ICPIM-31508 Export Rows to .csv file | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 13:47 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31512
Test Case | ICPIM-31510 | ICPIM-31508 Export a Row to .csv file | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-12-03 13:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31512
Test Case | ICPIM-31494 | ICPIM-31360 Report - General: Switch Card Utilization (By Switch): multiple selected switches | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:58 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31493 | ICPIM-31360 Report - General: Switch Card Utilization (By Switch) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:57 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31492 | ICPIM-31360 Report - General: Switch Card Utilization (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:57 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31491 | ICPIM-31360 Report - General: Switch Card Utilization (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:56 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31490 | ICPIM-31360 Report - General: Patch Panel Utilization (By Patch Panel): multiple selected panels | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:55 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31489 | ICPIM-31360 Report - General: Patch Panel Utilization (By Patch Panel) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:54 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31488 | ICPIM-31360 Report - General: Patch Panel Utilization (By Enclosure): multiple selected enclosures | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:54 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31487 | ICPIM-31360 Report - General: Patch Panel Utilization (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-03 03:53 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31486 | ICPIM-31456 Commission - Commission Move (Moving Module item(s) by dragging) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:30 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-31485 | ICPIM-31456 Commission - Commission Move (Moving Module item(s) without dragging) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:29 | 2100 | 1380 | 720 | 65% | 2100 | 1380 | 720 | 65%
Test Case | ICPIM-31484 | ICPIM-31456 Commission - Commission Move (Moving Equipment item(s) by dragging) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:29 | 1500 | 1260 | 240 | 84% | 1500 | 1260 | 240 | 84%
Test Case | ICPIM-31483 | ICPIM-31456 Commission - Commission Move (Moving Equipment item(s) without dragging) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:28 | 1800 | 1440 | 360 | 80% | 1800 | 1440 | 360 | 80%
Test Case | ICPIM-31482 | ICPIM-31456 Commission - Commission Move (Open Commission Editor window from Trace) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:28 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31481 | ICPIM-31456 Commission - Commission Move (Open Commission Editor window from Browser) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:27 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31480 | ICPIM-31456 Commission - Commission Move (Open Commission Editor window from Navigator) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-02 16:27 | 1200 | 1320 | 0 | 100% | 1200 | 1320 | 0 | 100%
Test Case | ICPIM-31476 | ICPIM-31464 Maintenance - Filter (Clear Filter) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:06 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-31475 | ICPIM-31464 Maintenance - Filter (Combine filters) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:06 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-31474 | ICPIM-31464 Maintenance - Filter (Filter by Site) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-12-02 15:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32922
Test Case | ICPIM-31473 | ICPIM-31464 Maintenance - Filter (Filter by Keyword) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-12-02 15:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32921
Test Case | ICPIM-31472 | ICPIM-31464 Maintenance - Filter (Filter by Projected End) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:03 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31471 | ICPIM-31464 Maintenance - Filter (Filter by Projected Start) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:02 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31470 | ICPIM-31464 Maintenance - Filter (Filter by Completed state) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:02 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-31469 | ICPIM-31464 Maintenance - Filter (Filter by In Progress state) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:01 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31468 | ICPIM-31464 Maintenance - Filter (Filter by Approved state) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 15:00 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31467 | ICPIM-31464 Maintenance - Filter (Filter by Scheduled state) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 14:58 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-31466 | ICPIM-31464 Maintenance - Filter (Filter by Unplanned type) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 14:57 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31465 | ICPIM-31464 Maintenance - Filter (Filter by Planned type) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 14:56 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31461 | ICPIM-31271 Maintenance - Display (Restore) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-02 14:50 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31460 | ICPIM-31271 Maintenance - Display (Trace) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-02 14:49 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31459 | ICPIM-31271 Maintenance - Display (Root) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-02 14:48 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31458 | ICPIM-31271 Maintenance - Display (Failover) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-12-02 14:48 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31457 | ICPIM-31271 Maintenance - Display (Hide - Restore Options) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-02 14:42 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31440 | ICPIM-31360 Report - General: Parts List (By Row): multiple selected row | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:29 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31439 | ICPIM-31360 Report - General: Parts List (By Row) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31438 | ICPIM-31360 Report - General: Parts List (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:28 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31437 | ICPIM-31360 Report - General: Parts List (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:27 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31436 | ICPIM-31360 Report - General: Parts List (By Equipment): multiple selected equipment items | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:26 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31435 | ICPIM-31360 Report - General: Parts List (By Equipment) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:26 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31434 | ICPIM-31360 Report - General: Parts List (By Enclosure): multiple selected items | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:25 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31433 | ICPIM-31360 Report - General: Parts List (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:24 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31432 | ICPIM-31360 Report - General: Disconnected Network Equipment (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:23 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31431 | ICPIM-31360 Report - General: Disconnected Network Equipment (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:21 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-31430 | ICPIM-31428 Report - Diagnostic: System Category Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:16 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31429 | ICPIM-31428 Report - Diagnostic: Class Schema Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-02 03:15 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31421 | ICPIM-30923 Commission - Configure Commission group - Clone Commission Items (with Configuration) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-01 16:19 | 1200 | 2520 | 0 | 100% | 1200 | 2520 | 0 | 100%
Test Case | ICPIM-31420 | ICPIM-30923 Commission - Configure Commission group - Clone Commission Items (without Configuration) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-01 16:17 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100%
Test Case | ICPIM-31406 | ICPIM-31041 Commission - Configure Commission Item (Network - Configure Commission Group with Equipment item that has no connectivity part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-01 14:42 | 1200 | 1260 | 0 | 100% | 1200 | 1260 | 0 | 100%
Test Case | ICPIM-31405 | ICPIM-31041 Commission - Configure Commission Item (Network - Configure Commission Group with Equipment item that has connectivity part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-01 14:41 | 1200 | 1140 | 60 | 95% | 1200 | 1140 | 60 | 95%
Test Case | ICPIM-31404 | ICPIM-31038 Commission - Configure Commission Item (Power - Configure Commission group with Equipment item that has power part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-01 14:36 | 1320 | 1140 | 180 | 86% | 1320 | 1140 | 180 | 86%
Test Case | ICPIM-31403 | ICPIM-31038 Commission - Configure Commission Item (Power - Configure Commission group with Equipment item that has no power part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-01 14:35 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31402 | ICPIM-31401 Schema - Set System Category Scriptlets | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 14:27 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31400 | ICPIM-31034 Commission - Configure Commission Item (Space - Configure Module Commission group) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-12-01 14:26 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-34460
Test Case | ICPIM-31399 | ICPIM-31034 Commission - Configure Commission Item (Space - Configure Equipment Commission group) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-12-01 14:25 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-31398 | ICPIM-31034 Commission - Configure Commission Item (Space - Configure Enclosure Commission group) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-12-01 14:24 | 1500 | 1860 | 0 | 100% | 1500 | 1860 | 0 | 100%
Test Case | ICPIM-31397 | ICPIM-31385 Configure Parameter - Dependencies (Dependent Parameter) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 12:24 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31396 | ICPIM-31385 Configure Parameter - Dependencies (Independent Parameter) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 12:22 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31393 | ICPIM-31385 Configure Parameter - General (Default Value) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:48 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31392 | ICPIM-31385 Configure Parameter - General (Description) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:46 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31391 | ICPIM-31385 Configure Parameter - General (Code) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:45 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31390 | ICPIM-31385 Configure Parameter - General (Edit type) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:44 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31389 | ICPIM-31385 Configure Parameter - General (Sub type) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:44 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31388 | ICPIM-31385 Configure Parameter - General (Data type) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:43 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31387 | ICPIM-31385 Configure Parameter - General (Name) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:42 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31386 | ICPIM-31385 Configure Parameter - General (Optional) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 11:42 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-31384 | ICPIM-11221 Create New Assets in CPIM | All |  | Garrett S. | Garrett S. | Business Logic | Invalid | 2014-12-01 10:55
Test Case | ICPIM-31371 | ICPIM-31368 Configure System Category (Export Script) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 09:26 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31370 | ICPIM-31368 Configure System Category (Import Script) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 09:25 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31369 | ICPIM-31368 Configure System Category (Edit Script) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-12-01 09:23 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31367 | ICPIM-31360 Report - General: Enclosure Contents Summary (By Location): multiple selected locations | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-01 04:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31366 | ICPIM-31360 Report - General: Enclosure Contents Summary (By Location) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-12-01 04:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31365 | ICPIM-31360 Report - General: Enclosure Contents Summary (By Enclosure): multiple selected items | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-01 04:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31364 | ICPIM-31360 Report - General: Enclosure Contents Summary (By Enclosure) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-01 04:20 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31363 | ICPIM-31360 Report - General: Commission Search | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-01 04:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31362 | ICPIM-31360 Report - General: Blade Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-01 04:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31361 | ICPIM-31360 Report - General: Asset Count (Entire Database) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-12-01 04:17 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31353 | ICPIM-31324 Platform - Dialogs Import Folder | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31352 | ICPIM-31324 Platform - Dialogs Import File | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31351 | ICPIM-31323 Platform - Dialogs Filter: Filter by Name | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:27 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31350 | ICPIM-31323 Platform - Dialogs Filter: Filter by Category | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-11-28 04:26 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-33311
Test Case | ICPIM-31349 | ICPIM-31323 Platform - Dialogs Filter: Filter by Library | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:25 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31348 | ICPIM-31320 Platform - Include Files Export | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:24 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-31347 | ICPIM-31318 Platform - Dialogs Import Folder | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:20 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31346 | ICPIM-31318 Platform - Dialogs Import File | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:19 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31345 | ICPIM-31325 System Administration - Maintenance - Events: Send Email Settings | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:18 | 1800 | 960 | 840 | 53% | 1800 | 960 | 840 | 53%
Test Case | ICPIM-31344 | ICPIM-31325 System Administration - Maintenance - Events: Send Email and auto close "Send Email" window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:18 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-31343 | ICPIM-31325 System Administration - Maintenance - Events: Send Email but errors triggered | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:17 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31342 | ICPIM-31325 System Administration - Maintenance - Events: Send Email with attachments | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:16 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32886
Test Case | ICPIM-31341 | ICPIM-31317 Platform - Dialogs Filter: Filter by Tab Count | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:15 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31340 | ICPIM-31325 System Administration - Maintenance - Events: Send Email to multiple recipients | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:15 | 1800 | 720 | 1080 | 40% | 1800 | 720 | 1080 | 40%
Test Case | ICPIM-31339 | ICPIM-31325 System Administration - Maintenance - Events: Send Email to single recipient | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:15 | 1200 | 480 | 720 | 40% | 1200 | 480 | 720 | 40%
Test Case | ICPIM-31338 | ICPIM-31317 Platform - Dialogs Filter: Filter by Name | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:15 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31337 | ICPIM-31317 Platform - Dialogs Filter: Filter by Category | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:14 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31336 | ICPIM-31317 Platform - Dialogs Filter: Filter by Library | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31335 | ICPIM-31325 System Administration - Maintenance - Events: Remove Maintenance Entry | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32885
Test Case | ICPIM-31334 | ICPIM-31325 System Administration - Maintenance - Events: Recalculate Affected Equipment | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:12 | 1200 | 300 | 900 | 25% | 1200 | 300 | 900 | 25%
Test Case | ICPIM-31333 | ICPIM-31316 Platform - Dialogs Export | All |  | Trinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-28 04:12 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31332 | ICPIM-31325 System Administration - Maintenance - Events: Modify Maintenance Entry | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:11 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32884
Test Case | ICPIM-31331 | ICPIM-31325 System Administration - Maintenance - Events: Modify Maintenance Entry: Validate input info on "Maintenance Edit" window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:10 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32881, ICPIM-32882, ICPIM-32883
Test Case | ICPIM-31330 | ICPIM-31325 System Administration - Maintenance - Events: Modify Maintenance Entry: Verify the "Maintenance Edit" window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:09 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-32880
Test Case | ICPIM-31329 | ICPIM-31325 System Administration - Maintenance - Events: Schedule Maintenance | All |  | Trinh Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-28 04:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31135, ICPIM-32879
Test Case | ICPIM-31328 | ICPIM-31325 System Administration - Maintenance - Events: Schedule Maintenance: Validate input info on "Maintenance Creation" window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:08 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-31327 | ICPIM-31325 System Administration - Maintenance - Events: Schedule Maintenance: Verify the "Maintenance Creation" window | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:05 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-31326 | ICPIM-31325 System Administration - Maintenance - Events: UI elements and sorting events | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-28 04:04 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-31312 | ICPIM-31307 Asset Management - Delete: Remove multiple items from within the database (with or without descendants) | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:57 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31311 | ICPIM-31307 Asset Management - Delete: Remove a selected item and all of its descendants | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:56 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31310 | ICPIM-31307 Asset Management - Delete: Remove a single item from the database | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31309 | ICPIM-31307 Asset Management - Delete: Verify elements on the Delete dialog | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:54 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31308 | ICPIM-31307 Asset Management - Delete: Open the Delete dialog | All |  | Vinh Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:53 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31285 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove multiple types of items in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-27 03:44 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-31267
Test Case | ICPIM-31284 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the cables in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:43 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31282 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the IT Assets in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:42 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31281 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the cooling equipment in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:41 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31280 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the power components in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:40 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31279 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the Enclosures in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:40 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31277 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the Rows in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:38 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31276 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the Tile grids in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:38 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31274 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the roof in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-27 03:37 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-31267
Test Case | ICPIM-31273 | ICPIM-31271 System Administration - Maintenance - Display: Display or remove the building structure in the viewer | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-27 03:36 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31253 | ICPIM-31245 Platform - Tabs: Add as Common tab |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-11-27 02:28 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31286
Test Case | ICPIM-31252 | ICPIM-31245 Platform - Tabs: Security Rights |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:27 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31251 | ICPIM-31245 Platform - Tabs: Assign system dialog |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-11-27 02:25 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31283
Test Case | ICPIM-31250 | ICPIM-31245 Platform - Tabs: Clear Values |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:24 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31249 | ICPIM-31245 Platform - Tabs: Order Virtual Tab Item |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:21 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31248 | ICPIM-31245 Platform - Tabs: Remove Virtual Tab Item |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:20 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31247 | ICPIM-31245 Platform - Tabs: Add Virtual Tab Item |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:17 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31246 | ICPIM-31245 Platform - Tabs: pre-configured dialogs |  |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-27 02:16 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31244 | ICPIM-30637 Commission - Add Library Items to Commission (Configure Equipment items) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-26 17:25 | 900 | 840 | 60 | 93% | 900 | 840 | 60 | 93%
Test Case | ICPIM-31243 | ICPIM-30630 Commission - Configure Group - Advanced Options (Virtual/Physical) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-26 16:48 | 600 | 1080 | 0 | 100% | 600 | 1080 | 0 | 100%
Test Case | ICPIM-31242 | ICPIM-30630 Commission - Configure Group - Advanced Options (Validate PDU Breaker/Validate Power Circuit) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-26 16:45 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31241 | ICPIM-31238 Asset Management - Manual Naming | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-26 16:37 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31240 | ICPIM-31236 Set System Category Groups - Set Groups | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:37 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31239 | ICPIM-31236 Set System Category Groups - Remove User-Defined Groups | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:36 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31237 | ICPIM-31236 Set System Category Groups - Add Groups | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:35 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31235 | ICPIM-31233 Reorder Parameters - Move Paremeter Down | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:32 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31234 | ICPIM-31233 Reorder Parameters - Move Parameter Up | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:31 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31232 | ICPIM-31231 Schema - Remove System Category | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:29 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31230 | ICPIM-31229 Schema - Remove Parameter | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:26 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31228 | ICPIM-31226 Schema - Import System Category | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:22 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31227 | ICPIM-31226 Schema - Import System Category (Over Write Existing System Category) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:21 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31225 | ICPIM-31224 Schema - Filter by Group | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:19 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31223 | ICPIM-31222 Schema - Export System Category | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:17 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31221 | ICPIM-31218 Clone System Category (Details - Return Translate) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:13 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31220 | ICPIM-31218 Clone System Category (Details - Run on Server) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:11 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-31219 | ICPIM-31218 Schema - Clone System Category | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:09 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31217 | ICPIM-31215 Add System Category (Details - Name, Description) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:06 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31216 | ICPIM-31215 Add System Category | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 16:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31214 | ICPIM-31213 Schema - Add Parameter |  |  | An Vo | An Vo | Windows Client | Pass | 2014-11-26 15:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31212 | ICPIM-30866 Commission - Configure Group - Preview Library Items (Visuals and Text) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-26 15:28 | 1500 | 1920 | 0 | 100% | 1500 | 1920 | 0 | 100%
Test Case | ICPIM-31207 | ICPIM-31119 PDU Breaker Rule (Power Policy) - Disconnect immediate power circuit connections | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-26 11:57 | 900 | 6600 | 0 | 100% | 900 | 6600 | 0 | 100% |  | ICPIM-33323
Test Case | ICPIM-31206 | ICPIM-31119 PDU Breaker Rule (Power Policy) - Disconnect direct power circuit and decommission PDU Breaker | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:57 | 1500 | 6300 | 0 | 100% | 1500 | 6300 | 0 | 100%
Test Case | ICPIM-31205 | ICPIM-31119 PDU Breaker Rule (Power Policy) - Disconnect direct Power Circuit | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:56 | 3600 | 9180 | 0 | 100% | 3600 | 9180 | 0 | 100%
Test Case | ICPIM-31204 | ICPIM-31119 Move Work Action Rule - Only for equipment listed | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:41 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100%
Test Case | ICPIM-31203 | ICPIM-31119 Move Work Action Rule - For the equipment listed and any descendant panels | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:41 | 900 | 3300 | 0 | 100% | 900 | 3300 | 0 | 100%
Test Case | ICPIM-31202 | ICPIM-31119 Move Work Action Rule - For the equipment listed and any descendant panels/modules | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:40 | 900 | 4500 | 0 | 100% | 900 | 4500 | 0 | 100%
Test Case | ICPIM-31201 | ICPIM-31119 Circuit Rule - Disconnect Full Circuit (Network Policy) | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-26 11:31 | 900 | 2400 | 0 | 100% | 900 | 2400 | 0 | 100% |  | ICPIM-33641
Test Case | ICPIM-31200 | ICPIM-31119 Circuit Rule - Disconnect Immediate Links Only | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:31 | 900 | 3900 | 0 | 100% | 900 | 3900 | 0 | 100%
Test Case | ICPIM-31199 | ICPIM-31119 Circuit Rule - Disconnect Soft Links Only | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-26 11:31 | 900 | 9600 | 0 | 100% | 900 | 9600 | 0 | 100%
Test Case | ICPIM-31198 | ICPIM-30895 Commission - Configure Group - Set Replication Destinations for Infrastructure/Network Run Commission group | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-26 11:18 | 1500 | 1020 | 480 | 68% | 1500 | 1020 | 480 | 68%
Test Case | ICPIM-31197 | ICPIM-30895 Commission - Configure Group - Set Replication Destinations for Enclosure/Equipment/Module/Row Commission group | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-26 11:17 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-34717
Test Case | ICPIM-31196 | ICPIM-30895 Commission - Create Group - Set Replication Destinations for Infrastructure/Network Run Commission group | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-26 11:16 | 2100 | 1200 | 900 | 57% | 2100 | 1200 | 900 | 57%
Test Case | ICPIM-31195 | ICPIM-31188 Cache - Viewer (Keep For) | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-11-26 09:03 | 3600 | 600 | 3000 | 16% | 3600 | 600 | 3000 | 16% |  | ICPIM-31208, ICPIM-33805
Test Case | ICPIM-31194 | ICPIM-31188 Cache - Viewer (Resolution) | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-11-26 09:03 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-31208, ICPIM-32652
Test Case | ICPIM-31193 | ICPIM-31188 Cache - Viewer (Enabled) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-26 09:03 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31208
Test Case | ICPIM-31192 | ICPIM-31188 Cache - Viewer (Search) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-26 09:03 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31191 | ICPIM-31188 Cache - Viewer (Clear Cache) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-26 09:03 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-31208
Test Case | ICPIM-31190 | ICPIM-31188 Cache - Viewer (Select None) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-26 09:03 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31189 | ICPIM-31188 Cache - Viewer (Select All) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-26 09:03 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31173 | ICPIM-31159 Platform - Categories: Remove Category | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:23 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31172 | ICPIM-31159 Platform - Categories: Add New Category | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31171 | ICPIM-31159 Platform - Categories: pre-configured categories | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-11-26 04:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31257
Test Case | ICPIM-31170 | ICPIM-31158 Platform - Display: Dialog Minimums | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Fail | 2014-11-26 04:18 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-31278
Test Case | ICPIM-31169 | ICPIM-31158 Platform - Display: Buttons | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31168 | ICPIM-31158 Platform - Display: Dictionary Flags | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:17 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31167 | ICPIM-31158 Platform - Display: Windows Styles | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31166 | ICPIM-31158 Platform - Display: display options | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:11 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31165 | ICPIM-31157 Platform - Dialogs: Move Dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:10 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31164 | ICPIM-31157 Platform - Dialogs: Launch Dialog | All |  | Tien Pham | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:09 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-31270, ICPIM-31258, ICPIM-31262, ICPIM-31264, ICPIM-31272, ICPIM-31275
Test Case | ICPIM-31163 | ICPIM-31157 Platform - Dialogs: Clone Dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:08 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31162 | ICPIM-31157 Platform - Dialogs: Remove Dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:07 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31161 | ICPIM-31157 Platform - Dialogs: Add Dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:06 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31160 | ICPIM-31157 Platform -Dialogs: pre-configured dialogs | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | Pass | 2014-11-26 04:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31156 | ICPIM-31149 Scheme - Data Collection - Methods: Edit Collection Method: Leave configuration without saving the change |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:37 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31155 | ICPIM-31149 Scheme - Data Collection - Methods: Edit Collection Method - WMI |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:36 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31154 | ICPIM-31149 Scheme - Data Collection - Methods: Edit Collection Method - SNMP |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:35 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31153 | ICPIM-31149 Scheme - Data Collection - Methods: Edit Collection Method - FileSystem |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31152 | ICPIM-31149 Scheme - Data Collection - Methods: Clear Script |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:31 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31151 | ICPIM-31149 Scheme - Data Collection - Methods: Edit Script |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31150 | ICPIM-31149 Scheme - Data Collection - Methods: Verify the Methods Listing and buttons |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:30 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31148 | ICPIM-31145 Scheme - Data Collection - General: Leave configuration without saving the change |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:23 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31147 | ICPIM-31145 Scheme - Data Collection - General: Edit parameters for a cloned data collection value |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:22 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31146 | ICPIM-31145 Scheme - Data Collection - General: Configure parameters for a new data collection value |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:20 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31144 | ICPIM-31143 Scheme - Data Collection - Clone data collection value |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 03:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31142 | ICPIM-31141 Scheme - Data Collection - Clone data collection value |  |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 02:59 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31140 | ICPIM-31138 Scheme - Data Collection - Add data collection value: Sort the Collection Values list | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 02:51 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31139 | ICPIM-31138 Scheme - Data Collection - Add data collection value | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-26 02:50 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31134 | ICPIM-30891 Commission - Configure Group: Set Destination for Commission Group Type Infrastructure/Network Run | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-25 15:38 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-31133 | ICPIM-30891 Commission - Configure Group: Set Destination for Commission Group Type Enclosure/Equipment/Module/Row | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-25 15:35 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-31132 | ICPIM-30891 Commission - Create Group: Set Destination for Commission Group Type Infrastructure/Network Run | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-25 15:33 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31131 | ICPIM-31119 Configuring The Decommission Editor - View Notes | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:30 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31130 | ICPIM-31119 Configuring The Decommission Editor - Selecting The Decommission Button | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:20 | 900 | 2100 | 0 | 100% | 900 | 2100 | 0 | 100% |  | ICPIM-33129
Test Case | ICPIM-31129 | ICPIM-31119 Configuring The Decommission Editor - Auto Complete | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:19 | 900 | 2400 | 0 | 100% | 900 | 2400 | 0 | 100%
Test Case | ICPIM-31128 | ICPIM-31119 Configuring The Decommission Editor - Override Verification | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-25 15:18 | 900 | 2400 | 0 | 100% | 900 | 2400 | 0 | 100% |  | ICPIM-27308
Test Case | ICPIM-31127 | ICPIM-31119 Configuring The Decommission Editor - PDU Breaker Rule | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:18 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100%
Test Case | ICPIM-31126 | ICPIM-31119 Configuring The Decommission Editor - Move Work Action Rule | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:17 | 900 | 1080 | 0 | 100% | 900 | 1080 | 0 | 100%
Test Case | ICPIM-31125 | ICPIM-31119 Configuring The Decommission Editor - Circuit Rule | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:17 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100%
Test Case | ICPIM-31124 | ICPIM-31119 Configuring The Decommission Editor - Cable Bin | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:17 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100%
Test Case | ICPIM-31123 | ICPIM-31119 Configuring The Decommission Editor - Grave Yard | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:16 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100%
Test Case | ICPIM-31122 | ICPIM-31119 Configuring The Decommission Editor - Finish date | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-25 15:16 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-31121 | ICPIM-31119 Configuring The Decommission Editor - Start date | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:15 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31120 | ICPIM-31119 Configuring The Decommission Editor - Browser Pane | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-25 15:15 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-31118 | ICPIM-31044 Cache - Dashboard (Keep For) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-25 15:06 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-31117 | ICPIM-31113 Add Decommission Group via Commission Search |  |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-25 14:21 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31116 | ICPIM-31113 Add Decommission Group via the Toolbar |  |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-25 14:21 | 600 | 960 | 0 | 100% | 600 | 960 | 0 | 100%
Test Case | ICPIM-31115 | ICPIM-31113 Add Decommission Group via the Standard Context menu |  |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-25 14:20 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31114 | ICPIM-31113 Add Decommission Group via the Planner window |  |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-25 14:19 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-31112 | ICPIM-31044 Cache - Dashboard (Resolution) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-25 13:57 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31100 | ICPIM-31098 Commission - General Configuration Options - Name | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-25 11:26 | 1500 | 1620 | 0 | 100% | 1500 | 1620 | 0 | 100%
Test Case | ICPIM-31099 | ICPIM-31098 Commission - General Configuration Options - State | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-25 11:25 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-31096 | ICPIM-31044 Cache - Dashboard (Enabled) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-25 10:23 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31095 | ICPIM-31044 Cache - Dashboard (Search) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-25 09:57 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-31094 | ICPIM-31044 Cache - Dashboard (Clear Cache) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-25 09:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31092 | ICPIM-31078 Report - Auto Reports: NGA (multiple items selected) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:36 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31091 | ICPIM-31078 Report - Auto Reports: NGA | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:35 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31090 | ICPIM-31078 Report - Auto Reports: Multi-level (multiple items selected) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:34 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31089 | ICPIM-31078 Report - Auto Reports: Multi-level | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31088 | ICPIM-31078 Report - Auto Reports: Dashboard (multiple items selected) | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:32 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31087 | ICPIM-31078 Report - Auto Reports: Dashboard | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:32 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31086 | ICPIM-31078 Report - Last Used Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-31085 | ICPIM-31077 Report - Regenerate Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:29 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31084 | ICPIM-31077 Report - Refresh Report View | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:28 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31083 | ICPIM-31077 Report - Stop Processing Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:27 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31082 | ICPIM-31077 Report - Email Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:26 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31081 | ICPIM-31077 Report - Print Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:25 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31080 | ICPIM-31077 Report - Save Report | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:24 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31079 | ICPIM-31076 Report - Report Job Viewer dialog | All |  | Vinh Nguyen | Vinh Nguyen | Windows Client | New | 2014-11-25 04:23 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-31075 | ICPIM-31063 Report - Add Report: Verify element UI of the "Choose Wizard" dialog | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-25 03:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31054
Test Case | ICPIM-31074 | ICPIM-31063 Report - Add Report: Creating a Power Blank Custom Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:21 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31073 | ICPIM-31063 Report - Add Report: Creating a Log Blank Custom Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:20 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31072 | ICPIM-31063 Report - Add Report: Creating a Diagnostic Blank Custom Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31071 | ICPIM-31063 Report - Add Report: Creating a General Blank Custom Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31070 | ICPIM-31063 Report - Add Report: Creating a Power Custom Report Using a Wizard | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-25 03:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31053
Test Case | ICPIM-31069 | ICPIM-31063 Report - Add Report: Creating a Log Custom Report Using a Wizard | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:17 | 900 | 900 | 900 | 50% | 900 | 900 | 900 | 50%
Test Case | ICPIM-31068 | ICPIM-31063 Report - Add Report: Creating a Diagnostic Custom Report Using a Wizard | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:16 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31067 | ICPIM-31063 Report - Add Report: Creating a General Custom Report Using a Wizard | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:15 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31066 | ICPIM-31063 Report - Add Report: Verify status of the Custom Report radio button | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-25 03:14 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-31052
Test Case | ICPIM-31065 | ICPIM-31063 Report - Add Report: Add a Standard Report | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Pass | 2014-11-25 03:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31064 | ICPIM-31063 Report - Add Report: Verify "Define New Report" dialog's UI | All |  | Mai Nguyen | Mai Nguyen | Windows Client | Fail | 2014-11-25 03:10 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31051
Test Case | ICPIM-31050 | ICPIM-31044 Cache - Dashboard (Select None) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 17:03 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31045 | ICPIM-31044 Cache - Dashboard (Select All) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 15:28 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-31043 | ICPIM-31041 Commission - Configure Commission Item (Network - Creating Commission Group with Equipment item that has no connectivity part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-11-24 14:24 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-31042 | ICPIM-31041 Commission - Configure Commission Item (Network - Creating Commission Group with Equipment item that has connectivity part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-11-24 14:24 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-31040 | ICPIM-31038 Commission - Configure Commission Item (Power - Creating Commission group with Equipment item has power part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-11-24 14:21 | 1200 | 2220 | 0 | 100% | 1200 | 2220 | 0 | 100%
Test Case | ICPIM-31039 | ICPIM-31038 Commission - Configure Commission Item (Power - Creating Commission group with Equipment item has no power part) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-11-24 14:20 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-31037 | ICPIM-31034 Commission - Configure Commission Item (Space - Creating Module Commission group) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-24 14:09 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31036 | ICPIM-31034 Commission - Configure Commission Item (Space - Creating Equipment Commission group) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-11-24 14:08 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-31035 | ICPIM-31034 Commission - Configure Commission Item (Space - Creating Enclosure Commission group) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-24 14:08 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-31033 | ICPIM-31017 Cache - Globals (Defaults) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 13:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31031 | ICPIM-31028 Create a scheduled virtual connection (Specify Existing Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 13:30 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31030 | ICPIM-31017 Cache - Globals (Clear) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 13:29 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-31029 | ICPIM-31028 Create a scheduled virtual connection (Create New Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 13:29 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31026 | ICPIM-31017 Cache - Globals (Location) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 13:20 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31025 | ICPIM-31017 Cache - Globals (Log Location) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 13:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-31024 | ICPIM-31017 Cache - Globals (Size) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 12:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-31023 | ICPIM-31017 Cache - Globals (Log level) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-24 12:44 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-31021 | ICPIM-31019 Create a scheduled physical connection (Specify Existing Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 11:53 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31020 | ICPIM-31019 Create a scheduled physical connection (Create New Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 11:52 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31016 | ICPIM-31014 Create a scheduled physical from existing cable (Specify Existing Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 11:17 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-30997
Test Case | ICPIM-31015 | ICPIM-31014 Create a scheduled physical from existing cable (Create New Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-24 11:16 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-31005 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Edit Size Settings | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:27 | 1500 | 4200 | 0 | 100% | 1500 | 4200 | 0 | 100% |  | ICPIM-39588
Test Case | ICPIM-31004 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose Type - Text | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:27 | 900 | 3000 | 0 | 100% | 900 | 3000 | 0 | 100% |  | ICPIM-29473, ICPIM-33395
Test Case | ICPIM-31003 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose Type - Numeric Counter | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:25 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33386
Test Case | ICPIM-31002 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose Type - Alpha Counter | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:25 | 900 | 3000 | 0 | 100% | 900 | 3000 | 0 | 100% |  | ICPIM-33386
Test Case | ICPIM-31001 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose the first Part Type | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-21 16:17 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-30998 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose Number of Parts | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:17 | 900 | 3600 | 0 | 100% | 900 | 3600 | 0 | 100% |  | ICPIM-33383
Test Case | ICPIM-30996 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Wizard - Choose Parameters | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 16:15 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-39507
Test Case | ICPIM-30995 | ICPIM-30994 Manual Connect - Logging | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 15:59 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30990 | ICPIM-30989 Trace - Internal Routing | All |  | Vinh Nguyen | Loan Ha | Windows Client | In Progress | 2014-11-21 15:19 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33%
Test Case | ICPIM-30986 | ICPIM-30982 Schedule Disconnect (Specify Existing Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 14:35 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-30985 | ICPIM-30982 Schedule Disconnect (Create New Work Project) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 14:33 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30984 | ICPIM-30983 Commission - Auto Complete | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-21 14:31 | 1800 | 5520 | 0 | 100% | 1800 | 5520 | 0 | 100% |  | ICPIM-34390
Test Case | ICPIM-30973 | ICPIM-30972 Trace - Fit To Window | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 14:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30971 | ICPIM-30969 Trace - Print W/ Fit To Window (Save) | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 13:37 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30970 | ICPIM-30969 Trace - Print W/ Fit To Window (Print) | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 13:37 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30968 | ICPIM-30966 Trace - Save | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 13:17 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30967 | ICPIM-30966 Trace - Print | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 13:07 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30961 | ICPIM-30960 Manual Disconnect - Logging | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 11:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30959 | ICPIM-30248 CSV Import Full Datastore Update | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-21 11:23 | 1200 | 10800 | 0 | 100% | 1200 | 10800 | 0 | 100% |  | ICPIM-33958
Test Case | ICPIM-30958 | ICPIM-30957 Connectivity - Launch Disconnect Dialog | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 11:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30956 | ICPIM-30955 Trace - Show Connection Points | All |  | An Vo | Loan Ha | Windows Client | Fail | 2014-11-21 10:50 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66% |  | ICPIM-33076, ICPIM-34325
Test Case | ICPIM-30952 | ICPIM-30951 Trace - Show Future | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 10:12 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-30949 | ICPIM-30945 Trace - Visual Trace | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-21 09:53 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-30948 | ICPIM-30946 Labeling preview (Name) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 09:45 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30947 | ICPIM-30946 Labeling preview (Template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-21 09:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30941 | ICPIM-27594 Update/Create Test Plan | Ran (4.1) |  | Alok Ghodke | Dan Fry | Web Client | Pass | 2014-11-21 06:27
Test Case | ICPIM-30925 | ICPIM-30923 Commission - Create Commission group - Clone Commission Items (with Configuration) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-20 17:13 | 1500 | 2820 | 0 | 100% | 1500 | 2820 | 0 | 100%
Test Case | ICPIM-30924 | ICPIM-30923 Commission - Create Commission group - Clone Commission Items (without Configuration) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-20 17:13 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-32971
Test Case | ICPIM-30922 | ICPIM-30918 Auto Number Rename (Auto Label Scheme) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-20 16:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30921 | ICPIM-30918 Auto Number Rename (IP) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-20 16:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33225
Test Case | ICPIM-30920 | ICPIM-30918 Auto Number Rename (Simple with Number) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-20 16:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30919 | ICPIM-30918 Auto Number Rename (Simple) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-20 16:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30914 | ICPIM-30912 Commission - Auto Naming of Cloned Item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-20 16:03 | 1500 | 1860 | 0 | 100% | 1500 | 1860 | 0 | 100%
Test Case | ICPIM-30913 | ICPIM-30912 Commission - Auto Naming of Added Item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-20 16:03 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100%
Test Case | ICPIM-30911 | ICPIM-30637 Commission - Add Library Items to Commission (Create Equipment items) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-20 15:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30910 | ICPIM-30906 Assignment of Data Store Values (File) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-20 14:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30909 | ICPIM-30906 Assignment of Data Store Values (Auto Number) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-20 14:55 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-30903, ICPIM-33225
Test Case | ICPIM-30908 | ICPIM-30906 Assignment of Data Store Values (Manual) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-20 14:54 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-30903, ICPIM-33380, ICPIM-34399
Test Case | ICPIM-30907 | ICPIM-30906 Assignment of Data Store Values (Parameters) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-20 14:53 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30867 | ICPIM-30866 Commission - Create Group - Preview Library Items (Visuals and Text) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-19 17:27 | 1200 | 1320 | 0 | 100% | 1200 | 1320 | 0 | 100%
Test Case | ICPIM-30859 | ICPIM-30858 Asset Management - Class Assignment (descendant classes only) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 15:26 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30857 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Context Object | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 14:57 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-30856 | ICPIM-30854 Asset Management - Renaming from file | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 14:33 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30855 | ICPIM-30850 Commission - View Commission Change Control ("Unable to Commission" group) | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-11-19 14:32 | 1500 | 2520 | 0 | 100% | 1500 | 2520 | 0 | 100%
Test Case | ICPIM-30853 | ICPIM-30850 Commission - View Commission Change Control ("Commissioned" group) | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-11-19 14:31 | 1500 | 2520 | 0 | 100% | 1500 | 2520 | 0 | 100%
Test Case | ICPIM-30852 | ICPIM-30851 Search - Search Reports (Run a Report Post the Search) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 14:31 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-30849 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Save Changes message | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 14:13 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-30848 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Scripts | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 14:13 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-30847 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Details - Refresh | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 14:11 | 300 | 1200 | 0 | 100% | 300 | 1200 | 0 | 100%
Test Case | ICPIM-30846 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Details - Remove | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 14:10 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-30845 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Details - Add Checkbox | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-19 14:08 | 600 | 2100 | 0 | 100% | 600 | 2100 | 0 | 100% |  | ICPIM-39504
Test Case | ICPIM-30844 | ICPIM-30841 Asset Management - Configure Autonumbering Definitions - Details - Add Text | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-19 14:06 | 600 | 2100 | 0 | 100% | 600 | 2100 | 0 | 100% |  | ICPIM-39504
Test Case | ICPIM-30843 | ICPIM-30842 Search - System Category Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 14:03 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-30838 | ICPIM-30837 Search - System Category Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 13:35 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30836 | ICPIM-30835 Search - Set Default | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 13:15 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30833 | ICPIM-30832 Search - Run Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 12:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30831 | ICPIM-30830 Asset Management - Set as Uplink | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 11:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30829 | ICPIM-30828 Search - Remove Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 11:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30826 | ICPIM-30825 Search - Drag and Drop Seeds | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 10:42 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30824 | ICPIM-30822 Commission - View Commission Log (Functionality) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-19 10:42 | 1500 | 1080 | 420 | 72% | 1500 | 1080 | 420 | 72%
Test Case | ICPIM-30823 | ICPIM-30822 Commission - View Commission Log (Overview) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-19 10:35 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-30821 | ICPIM-30820 Asset Management - Set Line of Business | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 10:23 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30819 | ICPIM-30813 Assignment of Template - Change Template | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-19 10:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-30786, ICPIM-30792, ICPIM-33712
Test Case | ICPIM-30818 | ICPIM-30813 Assignment of Template - Assign Template | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 09:59 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-30770, ICPIM-30773
Test Case | ICPIM-30817 | ICPIM-30816 Search - Dialog Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 09:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30815 | ICPIM-30813 Assignment of Template - View Template | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-19 09:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30773
Test Case | ICPIM-30814 | ICPIM-30813 Assignment of Template (Drop Zone, Select All, Remove Selection From List) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-19 09:57 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30776, ICPIM-33329
Test Case | ICPIM-30812 | ICPIM-30811 Search - Create Search | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-11-19 09:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30810 | ICPIM-30693 Search - Clone Search | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-11-19 09:35 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30890
Test Case | ICPIM-30809 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Remove | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-19 09:33 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100%
Test Case | ICPIM-30799 | ICPIM-30796 Commission - Remove Commission Group | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-11-18 17:46 | 1200 | 540 | 660 | 45% | 1200 | 540 | 660 | 45%
Test Case | ICPIM-30798 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Clone | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 17:46 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100%
Test Case | ICPIM-30797 | ICPIM-30795 Asset Management - Manage Autonumbering Definitions - Add and Edit | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 17:45 | 600 | 2400 | 0 | 100% | 600 | 2400 | 0 | 100%
Test Case | ICPIM-30785 | ICPIM-30782 Commission - Results tab (Commissioned item) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-18 16:54 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-30784 | ICPIM-30782 Commission - Results tab (Unable to commission item) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-18 16:54 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30783 | ICPIM-30782 Commission - Results tab (Overview) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-18 16:53 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-30769 | ICPIM-30716 Data Manager - Data Categories - Available Categories - Associates | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 15:16 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30764 | ICPIM-30716 Data Manager - Data Categories - Export User Category | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 14:39 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30763 | ICPIM-30716 Data Manager - Data Categories - Import User Category | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 14:38 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30762 | ICPIM-30716 Data Manager - Data Categories - Remove | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-18 14:37 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30761 | ICPIM-30760 Asset Management - Unassignment of Template | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-18 13:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30779
Test Case | ICPIM-30758 | ICPIM-30547 Audit - Manually Remove Connectivity | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-18 11:19 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30757 | ICPIM-30756 Open Basic Search window via menu File > Shortcuts | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-11-18 10:46 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30755 | ICPIM-30751 User Management - Toolbars (Configure Display Style) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-18 10:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30754 | ICPIM-30751 User Management - Toolbars (Remove Display Style) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-18 10:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30753 | ICPIM-30751 User Management - Toolbars (Active Display Style) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-18 10:40 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30752 | ICPIM-30751 User Management - Toolbars (Add Display Style) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-18 10:39 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30750 | ICPIM-30749 Asset Management - Scheme Assignment | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-18 10:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30719 | ICPIM-30716 Data Manager - Data Categories - Add Image | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-17 17:57 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-34935
Test Case | ICPIM-30718 | ICPIM-30716 Data Manager - Data Categories - Add Pickoff | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-17 17:57 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100% |  | ICPIM-32857, ICPIM-34083
Test Case | ICPIM-30717 | ICPIM-30716 Data Manager - Data Categories - Add Object, Date, Text, Double, Yes/No, Memo or Long | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-17 17:56 | 300 | 600 | 0 | 100% | 300 | 600 | 0 | 100%
Test Case | ICPIM-30715 | ICPIM-30714 Asset Management - Sub Class Assignment | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-17 16:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30713 | ICPIM-30711 Commission - Configure Commission Work Flow: Create Group functionality | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-17 16:34 | 1500 | 1560 | 0 | 100% | 1500 | 1560 | 0 | 100%
Test Case | ICPIM-30712 | ICPIM-30711 Commission - Configure Commission Work Flow: Work Flow tab overview | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-17 16:33 | 900 | 420 | 480 | 46% | 900 | 420 | 480 | 46%
Test Case | ICPIM-30710 | ICPIM-30709 Asset Management - Set as Library Item | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-17 16:07 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30708 | ICPIM-30707 Asset Management - Manual Rename | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-17 16:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30706 | ICPIM-30705 Asset Management - IT Service Assignment | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-17 16:03 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30704 | ICPIM-30703 Asset Management - Drag and Drop Objects | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-17 16:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30702 | ICPIM-30701 Schema - Library Management - Password | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-17 15:51 | 60 | 60 | 0 | 100% | 60 | 60 | 0 | 100%
Test Case | ICPIM-30700 | ICPIM-30699 Schema - Library Management - Info | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-17 15:40 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30692 | ICPIM-30689 3DViewer - View State Selection Simple | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-17 13:14 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-30691 | ICPIM-30690 Commission - Filters (State,Type,User) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-17 13:13 | 1500 | 2700 | 0 | 100% | 1500 | 2700 | 0 | 100% |  | ICPIM-34449
Test Case | ICPIM-30688 | ICPIM-30686 3DViewer - Export View States (Multiple) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-17 12:30 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30687 | ICPIM-30686 3DViewer - Export View State (Single) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-17 12:30 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30685 | ICPIM-30683 3DViewer - Import View States (Multiple) | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-11-17 12:25 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31672
Test Case | ICPIM-30684 | ICPIM-30683 3DViewer - Import View State (Single) | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-11-17 12:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31672
Test Case | ICPIM-30667 | ICPIM-30535 3DViewer - View State Configuration (Goto Parent) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-17 10:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30666 | ICPIM-30535 3DViewer - View State Configuration (Goto Selected) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-17 10:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30665 | ICPIM-29555 DEA - Flat FIle - Parent Mapping - Asset Creation - Device is not created if parent is not mapped. | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-17 09:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30664 | ICPIM-29555 DEA - Flat FIle - Parent Mapping - Front and Back Oritientation | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-17 09:46 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30663 | ICPIM-30535 3DViewer - View State Configuration (Display Style Options) | All |  | Tien Pham | Loan Ha | Windows Client | Fail | 2014-11-17 09:09 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-33183, ICPIM-35034
Test Case | ICPIM-30641 | ICPIM-30504 Commission - Add commission from Commission context menu | All |  | Thuy Tran | Tien Pham | Windows Client | Pass | 2014-11-14 17:04 | 2100 | 1800 | 300 | 85% | 2100 | 1800 | 300 | 85%
Test Case | ICPIM-30640 | ICPIM-30895 Commission - Create Group - Set Replication Destinations for Enclosure/Equipment/Module/Row Commission group | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-14 17:03 | 2100 | 1200 | 900 | 57% | 2100 | 1200 | 900 | 57% |  | ICPIM-34717
Test Case | ICPIM-30639 | ICPIM-30891 Commission - Create Group: Set Destination for Commission Group Type Enclosure/Equipment/Module/Row | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-14 17:02 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-30638 | ICPIM-30891 Commission - Set Destination - Create Group (The Browser) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-14 17:01 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30636 | ICPIM-30630 Commission - Create Group - Advanced Options (Physical type) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-14 16:55 | 600 | 780 | 0 | 100% | 600 | 780 | 0 | 100%
Test Case | ICPIM-30635 | ICPIM-30630 Commission - Create Group - Advanced Options (Virtual type) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-14 16:54 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-30634 | ICPIM-30630 Commission - Create Group - Advanced Options (Validate Power Circuit) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-14 16:54 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-30633 | ICPIM-30631 Role Management - Remove Security Right | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:54 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100%
Test Case | ICPIM-30632 | ICPIM-30630 Commission - Create Group - Advanced Options (Validate PDU Breaker) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-14 16:53 | 1500 | 2700 | 0 | 100% | 1500 | 2700 | 0 | 100% |  | ICPIM-32909
Test Case | ICPIM-30629 | ICPIM-30627 Commission - Manual Refresh | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-14 16:51 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30628 | ICPIM-30626 Role Management - Move Security Right | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:51 | 300 | 1200 | 0 | 100% | 300 | 1200 | 0 | 100%
Test Case | ICPIM-30625 | ICPIM-30622 Role Management - Find By Category | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:48 | 300 | 900 | 0 | 100% | 300 | 900 | 0 | 100%
Test Case | ICPIM-30624 | ICPIM-30623 Commission - Add/Clear Notes | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-14 16:48 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30621 | ICPIM-30620 Role Management - Find By Menu Item | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:44 | 120 | 720 | 0 | 100% | 120 | 720 | 0 | 100%
Test Case | ICPIM-30619 | ICPIM-30618 Role Management - Configure Security Item | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:41 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100%
Test Case | ICPIM-30617 | ICPIM-30616 Role Management - Add Security Right | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-14 16:36 | 300 | 900 | 0 | 100% | 300 | 900 | 0 | 100%
Test Case | ICPIM-30615 | ICPIM-30535 3DViewer - View State Configuration (Remove Style) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-14 15:13 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30613 | ICPIM-30612 Administration - Clean | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-14 13:55 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30606 | ICPIM-30535 3DViewer - View State Configuration (Add Display Style) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-14 13:05 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30602 | ICPIM-30600 Scheme Based Power Connectivity (Connect Primary/Redundant) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-14 11:06 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-31642, ICPIM-31650
Test Case | ICPIM-30601 | ICPIM-30600 Scheme Based Power Connectivity (One to Each) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-14 11:06 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31650
Test Case | ICPIM-30599 | ICPIM-30597 Audit - Horizontal Alignment (With Selected) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-14 11:02 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-30929, ICPIM-30932
Test Case | ICPIM-30598 | ICPIM-30597 Audit - Horizontal Alignment (Within Row) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-14 11:02 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30596 | ICPIM-30592 Audit - Vertical Alignment (With Selected) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-14 11:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30595 | ICPIM-30592 Audit - Vertical Alignment (Within Row) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-14 10:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30590 | ICPIM-30533 Audit - Horizontal, Vertical and Rotation combination | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-14 10:54 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-30929, ICPIM-30932
Test Case | ICPIM-30580 | ICPIM-30535 3DViewer - View State Configuration (Animate) | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-11-14 10:28 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31666
Test Case | ICPIM-30563 | ICPIM-30535 3DViewer - View State Configuration (Fit) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-14 09:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30558 | ICPIM-30556 Drag and Drop/Multi-select Network Connectivity (Different Enclosure) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-13 15:46 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-31006
Test Case | ICPIM-30557 | ICPIM-30556 Drag and Drop/Multi-select Network Connectivity (Same Enclosure) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-13 15:45 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-31006
Test Case | ICPIM-30555 | ICPIM-30552 Drag and Drop/Multi-select Manual Connectivity - Different Enclosure | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 15:40 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30554 | ICPIM-30552 Drag and Drop/Multi-select Manual Connectivity - Same Enclosure | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 15:39 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30553 | ICPIM-30552 Drag and Drop/Multi-select Manual Connectivity - Select to Connect | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 15:38 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30550 | ICPIM-30535 3DViewer - View State Configuration (Camera) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 14:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30549 | ICPIM-30535 3DViewer - View State Configuration (Styles) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 14:19 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30548 | ICPIM-30547 Audit - Remove Network Connectivity | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 14:00 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33006
Test Case | ICPIM-30546 | ICPIM-30535 3DViewer - View State Configuration (Save Viewstate) | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-11-13 13:57 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-31669
Test Case | ICPIM-30545 | ICPIM-30535 3DViewer - View State Configuration (Delete Viewstate) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 13:37 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30544 | ICPIM-30535 3DViewer - View State Configuration (Viewstates) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 13:03 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30540 | ICPIM-30547 Audit - Remove Power Cables | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-13 11:57 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-31009
Test Case | ICPIM-30534 | ICPIM-30533 Audit - Rotation | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 10:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30525 | ICPIM-30520 Audit - Rotation Undo | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 10:00 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30522 | ICPIM-30521 Audit - Alignment/Rotation Undo | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-13 09:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30519 | ICPIM-30349 3D Viewer - Viewer Toolbar (Load Masks) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 09:35 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30518 | ICPIM-30349 3D Viewer - Viewer Toolbar (View States) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-13 09:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30506 | ICPIM-30504 Commission - Add commission from Commission tab | All |  | Thuy Tran | Tien Pham | Windows Client | Fail | 2014-11-12 18:00 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-32845
Test Case | ICPIM-30505 | ICPIM-30504 Commission - Add commission (Commission tab overview) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-12 17:58 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30503 | ICPIM-30502 Standard 3D Viewer Capabilities - General Display | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-12 17:20 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30501 | ICPIM-30495 Audit - Rack Mounted Device Stacking (Stack and Add Blanking Panel) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30500 | ICPIM-30495 Audit - Rack Mounted Device Stacking (Back) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:12 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30499 | ICPIM-30495 Audit - Rack Mounted Device Stacking (From Bottom) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:11 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30498 | ICPIM-30495 Audit - Rack Mounted Device Stacking (Mounted Rear Devices) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:10 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30497 | ICPIM-30495 Audit - Rack Mounted Device Stacking (Mounted Front Devices) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:10 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30496 | ICPIM-30495 Audit - Rack Mounted Device Stacking (All Devices) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 17:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30494 | ICPIM-30493 Audit - Dynamic Blanking Panel Creation | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-12 16:25 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-30874, ICPIM-30877
Test Case | ICPIM-30492 | ICPIM-30349 3D Viewer - Viewer Toolbar (Show Settings) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 14:48 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100% |  | ICPIM-31422, ICPIM-30084
Test Case | ICPIM-30489 | ICPIM-30349 3D Viewer - Viewer Toolbar (Trace) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 14:12 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50% |  | ICPIM-31413
Test Case | ICPIM-30488 | ICPIM-30484 Create from Existing Instance - Add Instance Library Item (Module) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 13:48 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30487 | ICPIM-30484 Create from Existing Instance - Add Instance Library Item (Equipment) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 13:47 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30486 | ICPIM-30484 Create from Existing Instance - Add Instance Library Item (Enclosure) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-12 13:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30871
Test Case | ICPIM-30485 | ICPIM-30484 Create from Existing Instance - Select Instance Item | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 13:45 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-30483 | ICPIM-30349 3D Viewer - Viewer Toolbar (Unhide All) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 13:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30482 | ICPIM-30349 3D Viewer - Viewer Toolbar (Unhide Last) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 13:26 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30481 | ICPIM-30349 3D Viewer - Viewer Toolbar (Hide All Except Selection) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 13:09 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30480 | ICPIM-30349 3D Viewer - Viewer Toolbar (Hide Selection and Children) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 12:59 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30469 | ICPIM-30349 3D Viewer - Viewer Toolbar (Hide Selection) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 10:55 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-31407
Test Case | ICPIM-30468 | ICPIM-30349 3D Viewer - Viewer Toolbar (Zoom Out) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 10:35 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30467 | ICPIM-30349 3D Viewer - Viewer Toolbar (Zoom In) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 10:25 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30466 | ICPIM-30349 3D Viewer - Viewer Toolbar (Rotate Mode) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 10:10 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30465 | ICPIM-30349 3D Viewer - Viewer Toolbar (Pan Mode) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 10:02 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30464 | ICPIM-30421 Audit - Create by Library Item (Add Module) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-12 10:01 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30463 | ICPIM-30349 3D Viewer - Viewer Toolbar (Select Mode) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 09:36 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30462 | ICPIM-30349 3D Viewer - Viewer Toolbar (Zoom To Fit) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 09:32 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30460 | ICPIM-30349 3D Viewer - Viewer Toolbar (Toggle Perspective Mode) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 08:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30458 | ICPIM-30349 3D Viewer - Viewer Toolbar (Show Top) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-12 08:43 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30425 | ICPIM-30421 Audit - Create by Library Item (Add Equipment) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 17:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30424 | ICPIM-30421 Audit - Create by Library Item (Add Enclosure) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 17:07 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-30423 | ICPIM-30421 Audit - Create by Library Item (Library Item Position) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 17:06 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30422 | ICPIM-30421 Audit - Create by Library Item (Select Library Item) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 17:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30420 | ICPIM-30419 Audit - Simple Auto Naming | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-11 17:00 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-30868
Test Case | ICPIM-30415 | ICPIM-29555 DEA - Flat File - Data Integrity - Order of Assets in File Shall Not Cause Errant Location Conflicts | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30414 | ICPIM-29555 DEA - Flat File - Data Integrity - Re-Running File Shall Not Cause Errant Location Conflicts | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-31101, ICPIM-32642
Test Case | ICPIM-30413 | ICPIM-29555 DEA - Flat File - Data Integrity - Delete All Mappings and Re-import File | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30412 | ICPIM-29555 DEA - Flat File - Data Integrity - Importing a Large Number of Assets | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-31101
Test Case | ICPIM-30411 | ICPIM-29555 DEA - Flat File - File Export - All Data is Present and Accurate | All |  | Garrett S. | Garrett S. |  | Fail | 2014-11-11 16:21 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-32586
Test Case | ICPIM-30410 | ICPIM-29555 DEA - Flat File - File Export - All Exported Columns Have Headers | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:21 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30409 | ICPIM-29555 DEA - Flat File - File Export - Schedule is Followed | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:21 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30408 | ICPIM-29555 DEA - Flat File - Data Integration - Unmapped Attributes Do Not Write Data to Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:10 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30407 | ICPIM-29555 DEA - Flat File - Data Integration - Data is Written To Appropriate Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:09 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30406 | ICPIM-29555 DEA - Flat File - Data Integration - Ensure Attributes Can be Mapped To Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:09 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30405 | ICPIM-29555 DEA - Flat File - Data Integration - Ensure Column Headers Are Listed As Attributes | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:09 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30404 | ICPIM-29555 DEA - Flat File - Assets In Commissioning - Mapping Shall Be Retained Once Commissioning Is Complete | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 16:08 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30403 | ICPIM-29555 DEA - Flat File - Assets In Commissioning - Assets Shall Not Be Moved Out of Commissioning Store | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 16:08 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30402 | ICPIM-29555 DEA - Flat File - Assets In Commissioning - Assets Shall Be Mapped to Assets in Commissioning | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 16:07 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30401 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Cabinets - Move to Different Row Into Occupied Position | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 16:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30400 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Cabinets - Move To Different Row Into Empty Position | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 16:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30399 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Cabinets - Move to Occupied Row Position | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 16:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30398 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Cabinets - Move to Empty Row Position | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 16:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30397 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Panels - Move to Different Parent Into Occupied U Position | All |  | Garrett S. | Garrett S. |  | Fail | 2014-11-11 16:05 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-31576, ICPIM-32583
Test Case | ICPIM-30396 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Panels - Move To Different Parent With Empty U Position | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:05 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30395 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Panels - Swap Positions with Another Panel | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:04 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30394 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Panels - Move To Empty U Position | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:04 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30393 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Modules - Move to Other Parent Into Occupied Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:01 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30392 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Modules - Move to Different Parent Into Empty Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:01 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30391 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Modules - Swap Slots with Other Module | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:00 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30390 | ICPIM-29555 DEA - Flat File - Parent Mapping - Moving Assets - Modules - Empty Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 16:00 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30389 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Asset Which Is Forced Out Throws Conflict | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:59 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30388 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Location Can Be Forced | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30387 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Location Can Be Changed | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30386 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Missing Data Can Be Added | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 15:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30385 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Cabinets in the Same Row Position | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30384 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Panels in the Same U Position | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:57 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-30860
Test Case | ICPIM-30383 | ICPIM-29555 DEA - Flat File - Parent Mapping - Location Conflicts - Modules in the Same Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:57 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30382 | ICPIM-29555 DEA - Flat File - Parent Mapping - Asset Type Rules - Module/Slot Numbering Order | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:56 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30381 | ICPIM-29555 DEA - Flat File - Parent Mapping - Asset Type Rules - Power in Power Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30380 | ICPIM-29555 DEA - Flat File - Parent Mapping - Asset Type Rules - Card in Card Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30379 | ICPIM-29555 DEA - Flat File - Parent Mapping - Asset Type Rules - Blade in Blade Slot | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:55 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30378 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Any to Store - Cabinet | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30377 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Panel to Store | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-30900
Test Case | ICPIM-30376 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Module to Store | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-30900
Test Case | ICPIM-30375 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Cabinet to Other | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30374 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Cabinet to Row | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30373 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Panel to Other | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:52 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30372 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Panel to Cabinet | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:52 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30371 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Module to Other | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:52 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30370 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Container Rules are Followed - Module to Panel | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30369 | ICPIM-30349 3D Viewer - Viewer Toolbar (Show Back) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 15:51 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30368 | ICPIM-29555 DEA - Flat File - Parent Mapping - Missing Parent Device in File Does Not Cause Location Conflict | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-31101
Test Case | ICPIM-30367 | ICPIM-29555 DEA - Flat File - Parent Mapping - Ensure Specified Datastore is Used | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30366 | ICPIM-29555 DEA - Flat File - UID Mapping - CPIM Assets with Duplicated UID | All |  | Garrett S. | Garrett S. |  | Fail | 2014-11-11 15:50 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-32573
Test Case | ICPIM-30365 | ICPIM-29555 DEA - Flat File - UID Mapping - Ensure Existing Assets Missing a UID But With Matching SKU Are Mapped and UID is Added - Cabinet | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30364 | ICPIM-29555 DEA - Flat File - UID Mapping - Ensure Existing Assets Missing a UID But With Matching SKU Are Mapped and UID is Added - Panel | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 15:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30363 | ICPIM-29555 DEA - Flat File - UID Mapping - Ensure Existing Assets Missing a UID But With Matching SKU Are Mapped and UID is Added - Module | All |  | Garrett S. | Garrett S. |  | New | 2014-11-11 15:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30362 | ICPIM-30349 3D Viewer - Viewer Toolbar (Show Front) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 15:49 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30361 | ICPIM-29555 DEA - Flat File - UID Mapping - Ensure New Assets Are Created With UID - Modules | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:48 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30360 | ICPIM-29555 DEA - Flat File - UID Mapping - Ensure Specified Data Store Is Used | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-11 15:48 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30359 | ICPIM-29555 DEA - Flat File - SKU Mapping - Conflict Resolution - Duplicate SKUs Found in CPIM | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-11-11 15:47 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30358 | ICPIM-29555 DEA - Flat File - SKU Mapping - Conflict Resolution - Missing SKU With Asset Mapped | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-11 15:47 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30357 | ICPIM-29555 DEA - Flat File - SKU Mapping - Conflict Resolution - Missing SKU With No Asset Mapped | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-11 15:46 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30356 | ICPIM-29555 DEA - Flat File - SKU Mapping - Ensure Missing SKU Causes SKU Conflict | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-11 15:45 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30355 | ICPIM-29555 DEA - Flat File - SKU Mapping - Ensure Assets Are Created From The Correct Library Item | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-11 15:45 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-31101
Test Case | ICPIM-30354 | ICPIM-29555 DEA - Flat File - SKU Mapping - Ensure Specified Datastore Is Used | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:44 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30353 | ICPIM-29555 DEA - Flat File - Service Configuration | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:44 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30352 | ICPIM-29555 DEA - Flat File - Cabinet Creation (Configuration Step) | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-11 15:42 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-30351 | ICPIM-30350 Audit - Blanking Panel Deletion | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 15:41 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-30303
Test Case | ICPIM-30348 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Line Of Business) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-11 15:30 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-33079
Test Case | ICPIM-30347 | ICPIM-30346 Languages tab | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-11 15:26 | 1200 | 360 | 840 | 30% | 1200 | 360 | 840 | 30%
Test Case | ICPIM-30345 | ICPIM-30327 Search - Commission Search - Details | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:12 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-30344 | ICPIM-30327 Search - Commission Search - Results tab (Contents and user actions) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:11 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30343 | ICPIM-30327 Search - Commission Search - Viewer | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30342 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Mix criteria) | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-11 15:08 | 2400 | 2700 | 0 | 100% | 2400 | 2700 | 0 | 100% |  | ICPIM-33079
Test Case | ICPIM-30341 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Advanced) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:06 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30340 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Copper) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:06 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-30339 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Power) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:04 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-30338 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Fiber) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:03 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30337 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Space) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 15:03 | 900 | 1260 | 0 | 100% | 900 | 1260 | 0 | 100%
Test Case | ICPIM-30336 | ICPIM-30333 Globals tab |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-11 14:58 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-30335 | ICPIM-30327 Search - Commission Search - Search tab - Search criteria (Library Item) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 14:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30334 | ICPIM-30327 Search - Commission Search - Search tab - “Library item” | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 14:55 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-30332 | ICPIM-30327 Search - Commission Search - Search tab (Save Search, Save-Add) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 14:54 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30331 | ICPIM-30325 3DViewer - Trim Tile Grid | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 14:51 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-30330 | ICPIM-30327 Search - Commission Search (Search Within) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-11 14:29 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-30329 | ICPIM-30326 Workflow - Commission Search Settings - Saved Search | All |  | Tien Pham | Trinh Nguyen | Windows Client | Pass | 2014-11-11 14:20 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83% |  | ICPIM-30122, ICPIM-30137
Test Case | ICPIM-30328 | ICPIM-30326 Workflow - Commission Search Settings - Configurations | All |  | Tien Pham | Trinh Nguyen | Windows Client | Fail | 2014-11-11 14:18 | 1500 | 5400 | 0 | 100% | 1500 | 5400 | 0 | 100% |  | ICPIM-30100, ICPIM-30125, ICPIM-32823, ICPIM-32831, ICPIM-33653
Test Case | ICPIM-30324 | ICPIM-30314 Workflow - Technician - Action - Update | All |  | Tien Pham | Trinh Nguyen | Windows Client | Pass | 2014-11-11 13:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30323 | ICPIM-30318 3DViewer - Trace (T hot key) - Multiple Items | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 13:38 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30319 | ICPIM-30318 3DViewer - Trace (T hot key) - Single Item | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 12:49 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30317 | ICPIM-30314 Workflow - Technician - Action - Assign | All |  | Tien Pham | Trinh Nguyen | Windows Client | Fail | 2014-11-11 12:08 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30316 | ICPIM-30314 Workflow - Technician - View | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-11 12:08 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30315 | ICPIM-30314 Workflow - Technician - Utilities section - Details tab | All |  | Tien Pham | Trinh Nguyen | Windows Client | Pass | 2014-11-11 12:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30313 | ICPIM-28847 Manage Favorites-interaction between application and web interface | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-11 11:50 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30312 | ICPIM-28847 Manage Favorites - Navigate To | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-11 11:48 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30311 | ICPIM-30310 3DViewer - Print | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 10:57 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31425
Test Case | ICPIM-30309 | ICPIM-30306 3DViewer - M key (Move Here) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 10:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30308 | ICPIM-30307 Audit - Top/Front/Rear Quick Links | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-11 10:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30302 | ICPIM-30300 3DViewer - Tilegrid - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 09:24 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30301 | ICPIM-30300 3DViewer - Tilegrid - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 09:24 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30295 | ICPIM-30293 3DViewer - Tilegrid - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 08:55 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30294 | ICPIM-30293 3DViewer - Tilegrid - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-11 08:55 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30277 | ICPIM-30276 Design - Color Cables - View Connections infomation | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:38 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100% |  | ICPIM-32981
Test Case | ICPIM-30275 | ICPIM-30269 CSV Removal Enclosures | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:25 | 3300 | 3600 | 0 | 100% | 3300 | 3600 | 0 | 100%
Test Case | ICPIM-30274 | ICPIM-30269 CSV Removal Data Connections | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:24 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100%
Test Case | ICPIM-30273 | ICPIM-30269 CSV Removal Panel | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:24 | 1200 | 10800 | 0 | 100% | 1200 | 10800 | 0 | 100% |  | ICPIM-33970
Test Case | ICPIM-30272 | ICPIM-30269 CSV Removal Modules | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:23 | 3000 | 3600 | 0 | 100% | 3000 | 3600 | 0 | 100%
Test Case | ICPIM-30271 | ICPIM-30269 CSV Removal Row | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:22 | 2100 | 2100 | 0 | 100% | 2100 | 2100 | 0 | 100%
Test Case | ICPIM-30270 | ICPIM-30269 CSV Removal Basic | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:21 | 1800 | 10800 | 0 | 100% | 1800 | 10800 | 0 | 100% |  | ICPIM-33357
Test Case | ICPIM-30268 | ICPIM-30248 CSV Import Data Connections | All |  | An Vo | Trinh Nguyen | Windows Client | Blocker | 2014-11-10 18:14 | 3000 | 7200 | 0 | 100% | 3000 | 7200 | 0 | 100% |  | ICPIM-39158, ICPIM-33363, ICPIM-33919
Test Case | ICPIM-30267 | ICPIM-30248 CSV Import Power Connections | All |  | An Vo | Trinh Nguyen | Windows Client | Blocker | 2014-11-10 18:13 | 1500 | 10800 | 0 | 100% | 1500 | 10800 | 0 | 100% |  | ICPIM-39155, ICPIM-33897, ICPIM-33898
Test Case | ICPIM-30266 | ICPIM-30248 CSV Import Library Item | All |  | Mai Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:12 | 1500 | 3600 | 0 | 100% | 1500 | 3600 | 0 | 100% |  | ICPIM-33973
Test Case | ICPIM-30265 | ICPIM-30248 CSV Import Rename | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 18:11 | 1200 | 6660 | 0 | 100% | 1200 | 6660 | 0 | 100% |  | ICPIM-33357
Test Case | ICPIM-30264 | ICPIM-30248 CSV Import Datastore Values | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:10 | 1200 | 12600 | 0 | 100% | 1200 | 12600 | 0 | 100% |  | ICPIM-39152, ICPIM-39557, ICPIM-39690, ICPIM-39684, ICPIM-39685
Test Case | ICPIM-30263 | ICPIM-30248 CSV Import Panel (Update existing Panel) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:08 | 1500 | 7200 | 0 | 100% | 1500 | 7200 | 0 | 100% |  | ICPIM-32266
Test Case | ICPIM-30262 | ICPIM-30248 CSV Import Panel (Create Cable Management Bars) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:06 | 1800 | 7200 | 0 | 100% | 1800 | 7200 | 0 | 100% |  | ICPIM-32266
Test Case | ICPIM-30261 | ICPIM-30248 CSV Import Module | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:05 | 3000 | 16200 | 0 | 100% | 3000 | 16200 | 0 | 100% |  | ICPIM-33967
Test Case | ICPIM-30260 | ICPIM-30248 CSV Import Panel (import rack-mounted asset) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:04 | 1500 | 10800 | 0 | 100% | 1500 | 10800 | 0 | 100% |  | ICPIM-32260, ICPIM-32342, ICPIM-32343, ICPIM-32266
Test Case | ICPIM-30259 | ICPIM-30248 CSV Import Enclosure | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 18:01 | 1500 | 11520 | 0 | 100% | 1500 | 11520 | 0 | 100% |  | ICPIM-32260, ICPIM-32342, ICPIM-32343, ICPIM-39595, ICPIM-32266, ICPIM-34827
Test Case | ICPIM-30258 | ICPIM-30248 CSV Import Row | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-10 17:58 | 1200 | 13200 | 0 | 100% | 1200 | 13200 | 0 | 100% |  | ICPIM-37032, ICPIM-32260, ICPIM-32342, ICPIM-32343, ICPIM-32266, ICPIM-34827
Test Case | ICPIM-30257 | ICPIM-30256 Change Management - Remove Work Actions | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 17:37 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30255 | ICPIM-30254 Change Management - Add Work Actions | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 17:34 | 1200 | 660 | 540 | 55% | 1200 | 660 | 540 | 55%
Test Case | ICPIM-30253 | ICPIM-30233 View State Displays - Datacenter Connectivity | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 17:26 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30252 | ICPIM-30233 View State Displays - Row Connectivity | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 17:25 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100% |  | ICPIM-30806
Test Case | ICPIM-30251 | ICPIM-30233 View State Displays - Blanking Panels | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 17:24 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30250 | ICPIM-30233 View State Displays - Panels | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 17:23 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30249 | ICPIM-30248 CSV Import Basic | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2014-11-10 17:18 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100% |  | ICPIM-33357, ICPIM-37032, ICPIM-32260, ICPIM-32263, ICPIM-32266
Test Case | ICPIM-30247 | ICPIM-30246 Change Management - Remove Work Orders | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 16:51 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-30245 | ICPIM-30244 Change Management - Add Work Orders | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 16:49 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-30243 | ICPIM-30241 3DViewer - Power - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 16:45 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30242 | ICPIM-30241 3DViewer - Power - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 16:45 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30240 | ICPIM-30238 3DViewer - Power - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 16:35 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30239 | ICPIM-30238 3DViewer - Power - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 16:35 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30237 | ICPIM-30233 View State Displays - Cooling | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 16:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30236 | ICPIM-30233 View State Displays - Power | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 16:25 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30235 | ICPIM-30233 View State Displays - Enclosures | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 16:15 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30234 | ICPIM-30233 View State Displays - Tile Grid | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 16:14 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30232 | ICPIM-30230 3DViewer - Horizontal Cables - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 15:51 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30231 | ICPIM-30230 3DViewer - Horizontal Cables - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 15:51 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30229 | ICPIM-30227 Audit - Tree Based Navigation | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 15:40 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30803
Test Case | ICPIM-30228 | ICPIM-30216 CSV Populate tab (Execute sub-tab) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 15:40 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30226 | ICPIM-30216 CSV Populate tab (Configure sub-tab) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 15:38 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-30225 | ICPIM-30216 CSV Populate tab - Manage CSV Populate | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-10 15:37 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30224 | ICPIM-30222 Audit - View Row | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 15:36 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30223 | ICPIM-30216 CSV Populate tab - General | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-10 15:36 | 2400 | 900 | 1500 | 37% | 2400 | 900 | 1500 | 37%
Test Case | ICPIM-30221 | ICPIM-30220 Audit - Reloadable 3D Viewer Navigation | All |  | An Vo | An Vo | Windows Client | Pass | 2014-11-10 15:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30219 | ICPIM-30217 3DViewer - Horizontal Cables - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 15:17 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30218 | ICPIM-30217 3DViewer - Horizontal Cables - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 15:17 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30215 | ICPIM-30214 Change Management - Remove Work Requests | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 14:43 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30213 | ICPIM-30212 Change Management - Add Work Requests | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 14:41 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30211 | ICPIM-30210 Change Management - Remove Work Projects | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-11-10 14:29 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-32780
Test Case | ICPIM-30209 | ICPIM-30208 Change Management - Add Work Projects | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 14:23 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30207 | ICPIM-30143 Change Management - Workflow (Work Requests Overview) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 14:16 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-30206 | ICPIM-30143 Change Management - Workflow (Work Project Overview) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-10 14:15 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-30205 | ICPIM-30203 3DViewer - Enclosures - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 13:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30204 | ICPIM-30203 3DViewer - Enclosures - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 13:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30201 | ICPIM-30199 3DViewer - Enclosures - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 13:06 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30200 | ICPIM-30199 3DViewer - Enclosures - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 13:06 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30198 | ICPIM-30196 3DViewer - Doors - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 12:56 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30197 | ICPIM-30196 3DViewer - Doors- Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 12:55 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30192 | ICPIM-30190 3DViewer - Door - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 12:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30191 | ICPIM-30190 3DViewer - Doors - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 12:41 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30189 | ICPIM-30186 Create from Library Item - Create Plug-in Device | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 11:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30800
Test Case | ICPIM-30188 | ICPIM-30186 Create from Library Item - Create Panel Device | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 11:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30187 | ICPIM-30186 Create from Library Item - Add Enclosure | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 11:40 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30184 | ICPIM-30182 3DViewer - Data Cables - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 10:48 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30183 | ICPIM-30182 3DViewer - Data Cables - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 10:48 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30181 | ICPIM-30180 TC - File-Advanced-Report Repositories-Reports | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-10 10:32 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-33820
Test Case | ICPIM-30179 | ICPIM-30173 Create by Template - Change, Remove Plug-in Device | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 10:30 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-30729
Test Case | ICPIM-30178 | ICPIM-30173 Create by Template - Add Plug-in Device | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 10:29 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-38550, ICPIM-30720
Test Case | ICPIM-30177 | ICPIM-30173 Create by Template - Change, Remove Pane Device | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 10:28 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-30729
Test Case | ICPIM-30176 | ICPIM-30173 Create by Template - Add Pane Device | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 10:28 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-30175 | ICPIM-30173 Create by Template - Set Enclosure | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-10 10:26 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100% |  | ICPIM-30720
Test Case | ICPIM-30174 | ICPIM-30173 Create by Template - Add Enclosure | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-10 10:25 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100%
Test Case | ICPIM-30172 | ICPIM-30171 TC - File-Advanced-Report Repositories-Connections | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Invalid | 2014-11-10 10:21 | 2100 | 2100 | 0 | 100% | 2100 | 2100 | 0 | 100% |  | ICPIM-33793, ICPIM-33790, ICPIM-33799
Test Case | ICPIM-30170 | ICPIM-30168 3DViewer - Data Cables - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 09:53 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30169 | ICPIM-30168 3DViewer - Data Cables - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-10 09:53 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30155 | ICPIM-30153 3DViewer - Cable Routes - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 15:25 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30154 | ICPIM-30153 3DViewer - Cable Routes - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 15:25 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30149 | ICPIM-30147 3DViewer - Cable Routes - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 15:02 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30148 | ICPIM-30147 3DViewer - Cable Routes - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 15:02 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30145 | ICPIM-30144 Audit - 1mm Rack Spacing | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-07 14:59 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-30741
Test Case | ICPIM-30142 | ICPIM-30140 3DViewer - Cabinet - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:46 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30141 | ICPIM-30140 3DViewer - Cabinet - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:46 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30133 | ICPIM-30131 3DViewer - Cabinet - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:34 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30132 | ICPIM-30131 3DViewer - Cabinet - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:34 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30121 | ICPIM-30119 3DViewer - Fixed Power - Hide (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:09 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33% |  | ICPIM-23972
Test Case | ICPIM-30120 | ICPIM-30119 3DViewer - Fixed Power - Hide (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 14:09 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30118 | ICPIM-30112 Single Port Connect - Disconnect | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:04 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30117 | ICPIM-30112 Single Port Connect - Disconnect Information | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:03 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30116 | ICPIM-30112 Single Port Connect - Create | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:03 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30115 | ICPIM-30112 Single Port Connect - Existing | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:02 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30114 | ICPIM-30112 Single Port Connect - Virtual | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:01 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-30113 | ICPIM-30112 Single Port Connect - Connect Information | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 14:00 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30111 | ICPIM-30108 Properties- Set Line Of Business | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-07 13:57 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-30099 | ICPIM-30084 3DViewer - Interactive Visualization (Options tab overview) | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-11-07 11:19 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-30098 | ICPIM-30084 3DViewer - Interactive Visualization (Global tab functionality) | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-11-07 11:13 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-30097 | ICPIM-30084 3DViewer - Interactive Visualization (Global tab overview) | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-11-07 11:13 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30096 | ICPIM-30063 Tree Based Navigation - View Trace | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-07 11:12 | 1200 | 3300 | 0 | 100% | 1200 | 3300 | 0 | 100% |  | ICPIM-30645, ICPIM-33206
Test Case | ICPIM-30086 | ICPIM-30085 Navigation- View Dictionary - Launch the Dictionary Dialog: | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-07 10:36 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-30083 | ICPIM-30048 3DViewer - Delete Tile Grid (Viewer RMM) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 09:06 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30082 | ICPIM-30048 3DViewer - Delete Tile Grid (Root Navigator RMM) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-07 08:57 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30068 | ICPIM-30061 TC - File-Shortcuts-Define Dictionary (Dictionary Editor) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 17:00 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100%
Test Case | ICPIM-30067 | ICPIM-30063 Tree Based Navigation - Navigator Selection | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-06 16:47 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-30648
Test Case | ICPIM-30066 | ICPIM-30063 Tree Based Navigation - Errors | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-06 16:47 | 1800 | 5400 | 0 | 100% | 1800 | 5400 | 0 | 100% |  | ICPIM-30645, ICPIM-33206, ICPIM-34385
Test Case | ICPIM-30065 | ICPIM-30063 Tree Based Navigation - Animate and Zoom to Selected Equipment | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-06 16:46 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-30454
Test Case | ICPIM-30064 | ICPIM-30061 TC - File - Shortcuts - Define Dictionary (Delete this dictionary) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:45 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100%
Test Case | ICPIM-30062 | ICPIM-30061 TC - File-Shortcuts-Define Dictionary (Define Dictionary Wizard) | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:43 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30060 | ICPIM-30049 Connect dialog - Connect item(s) added from context menu on Root Navigator with "Existing" type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-06 16:35 | 1200 | 4920 | 0 | 100% | 1200 | 4920 | 0 | 100% |  | ICPIM-31046, ICPIM-35812, ICPIM-33668, ICPIM-34402
Test Case | ICPIM-30059 | ICPIM-30049 Connect dialog - Connect item(s) added from context menu on Root Navigator with "Create" type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:34 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-30058 | ICPIM-30049 Connect dialog - Connect item(s) added from context menu on Root Navigator with "Virtual" type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-06 16:34 | 1200 | 1140 | 60 | 95% | 1200 | 1140 | 60 | 95% |  | ICPIM-33659
Test Case | ICPIM-30057 | ICPIM-30049 Connect dialog - Context menu's options | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:32 | 1500 | 1080 | 420 | 72% | 1500 | 1080 | 420 | 72%
Test Case | ICPIM-30056 | ICPIM-30049 Connect dialog - Schedule tab | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-06 16:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33638
Test Case | ICPIM-30055 | ICPIM-30049 Connect dialog - Connect items with Existing type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:30 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-33665
Test Case | ICPIM-30054 | ICPIM-30049 Connect dialog - Set Next Link Item when create connection with "Existing" type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:25 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30053 | ICPIM-30049 Connect dialog - Connect items with Create type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:24 | 2100 | 2100 | 0 | 100% | 2100 | 2100 | 0 | 100%
Test Case | ICPIM-30052 | ICPIM-30049 Connec dialog - Set Store Location when create connection with "Create" type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:22 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-30051 | ICPIM-30049 Connect dialog - Connect items with Virtual type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:22 | 1800 | 1260 | 540 | 70% | 1800 | 1260 | 540 | 70% |  | ICPIM-33644, ICPIM-33650
Test Case | ICPIM-30050 | ICPIM-30049 Connect dialog - Filling / removing item from browsers | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:20 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-33674
Test Case | ICPIM-30047 | ICPIM-30032 Templates: Set Index - Multiple Classes | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:13 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-30046 | ICPIM-30032 Templates: Set Index - Index | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-06 16:13 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100% |  | ICPIM-33534
Test Case | ICPIM-30045 | ICPIM-30032 Templates: Set Index - Additional | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30044 | ICPIM-30032 Templates: Set Index - Part No | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30043 | ICPIM-30032 Templates: Set Index - Depth | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30042 | ICPIM-30032 Templates: Set Index - Width | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30041 | ICPIM-30032 Templates: Set Index - Height | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30040 | ICPIM-30032 Templates: Set Index - Model | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:12 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30039 | ICPIM-30032 Templates: Set Index - Manufacturer | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30038 | ICPIM-30032 Templates: Set Index - Template Name | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30037 | ICPIM-30032 Templates: Set Index - Items Drop Zone | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:11 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30036 | ICPIM-30032 Templates: Set Index - Remove Selection From List | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:11 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30035 | ICPIM-30032 Templates: Set Index - Select All | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 16:11 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30034 | ICPIM-30032 Launch the Set Index dialog | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-06 16:10 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-33487
Test Case | ICPIM-30033 | ICPIM-30021 Disconnect dialog - View Connections - Filter Tab – Connections – Soft - Type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2014-11-06 16:09 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-33808, ICPIM-33961, ICPIM-34075, ICPIM-34262, ICPIM-33654
Test Case | ICPIM-30031 | ICPIM-30021 Disconnect dialog - View Connections - Filter Tab – Connections – Circuit - Type | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2014-11-06 16:06 | 900 | 3600 | 0 | 100% | 900 | 3600 | 0 | 100% |  | ICPIM-33808, ICPIM-33961, ICPIM-34262, ICPIM-33654
Test Case | ICPIM-30030 | ICPIM-30028 Mapview - View | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 16:04 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-30029 | ICPIM-30021 Disconnect dialog - View Connections - Filter Tab - Connections – Circuit (Classes, Select All, Select None) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 16:02 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-30027 | ICPIM-30021 Disconnect dialog - View Connections - Filter Tab – Connections - Immediate | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2014-11-06 16:01 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-33808, ICPIM-33961, ICPIM-34075, ICPIM-34262, ICPIM-33654
Test Case | ICPIM-30026 | ICPIM-30021 Disconnect dialog - View Connections - Filter Tab UI (Display Links, Connections, Types) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 15:59 | 900 | 900 | 900 | 50% | 900 | 900 | 900 | 50%
Test Case | ICPIM-30025 | ICPIM-30021 Disconnect dialog - View Connections - Source Tab | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 15:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30024 | ICPIM-30021 Disconnect dialog - View Connections - Links to Disconnect (Auto Close) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 15:57 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-30023 | ICPIM-30021 Disconnect dialog - View Connections - Links to Disconnect (Select All, Select None, Disconnect) | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 15:55 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-30022 | ICPIM-30021 Disconnect dialog - View Connections - Links to Disconnect | All |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-06 15:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30020 | ICPIM-30018 Search for Templates | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 15:52 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-30017 | ICPIM-30007 3DViewer - Viewer Refresh (RMM) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 15:24 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30016 | ICPIM-30007 3DViewer - Viewer Refresh (F5) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 15:22 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-30015 | ICPIM-30007 3DViewer - Viewer Refresh (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 15:19 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-30014 | ICPIM-30009 Rotate Image | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 15:09 | 900 | 960 | 840 | 53% | 900 | 960 | 840 | 53%
Test Case | ICPIM-30013 | ICPIM-30009 New Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 15:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30012 | ICPIM-30009 Current Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 15:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-30011 | ICPIM-30010 Mapview - Configure | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 15:08 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-30001 | ICPIM-29957 3DViewer - Fixed Power - Show (Icon) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 14:28 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33% |  | ICPIM-23972
Test Case | ICPIM-30000 | ICPIM-29957 3DViewer - Fixed Power - Show (Display) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 14:02 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29999 | ICPIM-30106 3DViewer - Viewer Filter - Show Cables | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 13:41 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29998 | ICPIM-29979 Assign Template - Assign | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29997 | ICPIM-29979 Assign Template - Clear all but size | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-06 13:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-33590
Test Case | ICPIM-29996 | ICPIM-29979 Assign Template - Clear All | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29995 | ICPIM-30018 Assign Template - Search button | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:13 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29994 | ICPIM-29979 Assign Template - Depth | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:13 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29993 | ICPIM-29979 Assign Template - Width | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29992 | ICPIM-29979 Assign Template - Height | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29991 | ICPIM-29979 Assign Template - Type | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-06 13:12 | 600 | 1800 | 0 | 100% | 600 | 1800 | 0 | 100% |  | ICPIM-33593
Test Case | ICPIM-29990 | ICPIM-29979 Assign Template - Part | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29989 | ICPIM-29979 Assign Template - Unique | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29988 | ICPIM-29979 Assign Template - Additional | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:12 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29987 | ICPIM-29979 Assign Template - Model | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29986 | ICPIM-29979 Assign Template - Manufacturer | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29985 | ICPIM-29979 Assign Template - Items Drop Zone | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100% |  | ICPIM-30792
Test Case | ICPIM-29984 | ICPIM-29979 Assign Template - Clear Selected Items | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29983 | ICPIM-29979 Assign Template - Select All | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29982 | ICPIM-29979 Assign Template - Auto Close | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-29981 | ICPIM-29979 Assign Template - Auto Fill | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:11 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-29980 | ICPIM-29979 Launch the Assign Template dialog | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-06 13:10 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100% |  | ICPIM-30792
Test Case | ICPIM-29973 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Power, Tilegrid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29972 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Horizontal Cable, Overhead Power) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:41 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29971 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Fixed Cables, Fix Power) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:41 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29970 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Doors, Enclosures) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:40 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29969 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Cage, Data Cables) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:39 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29968 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Cable Routes, Cable Trays) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29967 | ICPIM-29963 View State Displays - Display Styles (Hide and Show Aisle Containment, Cabinet) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:38 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29966 | ICPIM-29963 View State Displays - Camera | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:35 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29965 | ICPIM-29963 View State Displays - View States | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:34 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29964 | ICPIM-29963 Launch Audit Item Window | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-06 11:32 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29962 | ICPIM-29961 Mapview - Reload View | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 11:04 | 1500 | 960 | 540 | 64% | 1500 | 960 | 540 | 64%
Test Case | ICPIM-29956 | ICPIM-29954 Mapview - Print (Save Image As) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 10:12 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29955 | ICPIM-29954 Mapview - Print | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 10:11 | 2100 | 1440 | 660 | 68% | 2100 | 1440 | 660 | 68%
Test Case | ICPIM-29953 | ICPIM-29534 3DViewer - Hide list (RMM) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-06 09:40 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29952 | ICPIM-29887 3DViewer - Future View (Icon) | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-06 09:27 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-29951 | ICPIM-29949 Mapview - Clear All Connections | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 09:05 | 1200 | 780 | 420 | 65% | 1200 | 780 | 420 | 65%
Test Case | ICPIM-29950 | ICPIM-29887 3DViewer - Future View (RMM) | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-06 09:04 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-29948 | ICPIM-29947 Mapview - Update All Connections | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-06 09:02 | 1500 | 960 | 540 | 64% | 1500 | 960 | 540 | 64%
Test Case | ICPIM-29931 | ICPIM-29910 Poly Line - Format (Information) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:54 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29930 | ICPIM-29910 Poly Line - Format (Aspect Ratio) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-05 16:53 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70% |  | ICPIM-30449
Test Case | ICPIM-29929 | ICPIM-29910 Poly Line - Format (Fill - Gradient) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:53 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29928 | ICPIM-29910 Poly Line - Format (Fill - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:52 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29927 | ICPIM-29910 Poly Line - Format (Fill - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:51 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29926 | ICPIM-29910 Poly Line - Format (Poly Line - Rounded Corners) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:51 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29925 | ICPIM-29910 Poly Line - Format (Poly Line - Dotted) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:50 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29924 | ICPIM-29910 Poly Line - Format (Poly Line - Dashed) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:49 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29923 | ICPIM-29910 Poly Line - Format (Poly Line - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:48 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29922 | ICPIM-29910 Poly Line - Format (Poly Line - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:47 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29921 | ICPIM-29910 Poly Line - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:45 | 900 | 480 | 420 | 53% | 900 | 480 | 420 | 53%
Test Case | ICPIM-29920 | ICPIM-29915 SLA’s –Clear All Tasks or LOB’s | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-11-05 16:43 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29919 | ICPIM-29915 SLA’s –Select All option Tasks or LOB’s | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-11-05 16:43 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29918 | ICPIM-29915 SLA’s – Set Duration for Line of Business | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-11-05 16:42 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29917 | ICPIM-29915 SLA’s – Set Duration for Task | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-11-05 16:42 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29916 | ICPIM-29915 Access the SLA’s tab | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-11-05 16:42 | 900 | 180 | 720 | 20% | 900 | 180 | 720 | 20%
Test Case | ICPIM-29914 | ICPIM-29910 Poly Line - Zoom Selected | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:32 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29913 | ICPIM-29910 Poly Line - Anchor, Unanchor Poly Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:31 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29912 | ICPIM-29910 Poly Line - Copy and Paste Poly Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:30 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29911 | ICPIM-29910 Poly Line - Add, Delete Poly Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 16:29 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29907 | ICPIM-29902 MapView - Sync Selection (with Trace) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 16:00 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29906 | ICPIM-29902 MapView - Sync Selection (with Browser) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 15:59 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29905 | ICPIM-29904 Filtering the Viewer Display by Line of Business | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:59 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-29903 | ICPIM-29902 MapView - Sync Selection (with Navigator) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 15:57 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29901 | ICPIM-29900 Remove Line of Business. | All |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:55 | 300 | 900 | 0 | 100% | 300 | 900 | 0 | 100%
Test Case | ICPIM-29899 | ICPIM-29897 Conducting a Basic Search by Line of Business | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:42 | 900 | 960 | 0 | 100% | 900 | 960 | 0 | 100%
Test Case | ICPIM-29898 | ICPIM-29897 Assigning a Line of Business to an Item | All |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:41 | 1200 | 4620 | 0 | 100% | 1200 | 4620 | 0 | 100% |  | ICPIM-36204
Test Case | ICPIM-29896 | ICPIM-29887 3DViewer - Future View (F key) | All |  | An Vo | Loan Ha | Windows Client | Pass | 2014-11-05 15:40 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-29895 | ICPIM-29891 Search for LOB | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Invalid | 2014-11-05 15:36 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-29894 | ICPIM-29891 Assigning Color for Line of Business | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:35 | 300 | 900 | 0 | 100% | 300 | 900 | 0 | 100% |  | ICPIM-32961, ICPIM-32960, ICPIM-32962
Test Case | ICPIM-29893 | ICPIM-29891 Adding Code value to Line of Business | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Invalid | 2014-11-05 15:35 | 300 | 600 | 0 | 100% | 300 | 600 | 0 | 100%
Test Case | ICPIM-29892 | ICPIM-29891 Adding a Name to Line of Business | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:35 | 300 | 600 | 600 | 50% | 300 | 600 | 600 | 50% |  | ICPIM-32959
Test Case | ICPIM-29890 | ICPIM-29888 Adding a new Line of Business | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-05 15:30 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-33475
Test Case | ICPIM-29889 | ICPIM-29888 Launch the Line of Business dialog | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-05 15:30 | 300 | 480 | 0 | 100% | 300 | 480 | 0 | 100% |  | ICPIM-36827
Test Case | ICPIM-29881 | ICPIM-29880 MapView - Erase All | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 13:41 | 1200 | 780 | 420 | 65% | 1200 | 780 | 420 | 65%
Test Case | ICPIM-29879 | ICPIM-29878 MapView - Remove From Class | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 13:14 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-29877 | ICPIM-29739 Mapview - Unanchor Item (Unanchor Items dialog) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-05 12:56 | 1500 | 840 | 660 | 56% | 1500 | 840 | 660 | 56%
Test Case | ICPIM-29872 | ICPIM-29858 Ellipse - Format (Information) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:47 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29871 | ICPIM-29858 Ellipse - Format (Aspect Ratio) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:46 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29870 | ICPIM-29858 Ellipse - Format (Fill - Gradient) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-05 09:45 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50% |  | ICPIM-30448
Test Case | ICPIM-29869 | ICPIM-29858 Ellipse - Format (Fill - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:44 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29868 | ICPIM-29858 Ellipse - Format (Fill - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:43 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29867 | ICPIM-29858 Ellipse - Format (Ellipse - Dotted) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:42 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29866 | ICPIM-29858 Ellipse - Format (Ellipse - Dashed) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:42 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29865 | ICPIM-29858 Ellipse - Format (Ellipse - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:41 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29864 | ICPIM-29858 Ellipse - Format (Ellipse - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:40 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29863 | ICPIM-29858 Ellipse - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:39 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29862 | ICPIM-29858 Ellipse - Zoom Selected | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:38 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29861 | ICPIM-29858 Ellipse - Anchor, Unanchor Ellipse | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:38 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29860 | ICPIM-29858 Ellipse - Copy and Paste Ellipse | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:37 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29859 | ICPIM-29858 Ellipse - Add, Delete Ellipse | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-05 09:36 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29797 | ICPIM-29786 Mapview - Edit (Change View) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 16:40 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-29795 | ICPIM-29786 Mapview - Edit (Drag and Drop) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 16:39 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-29789 | ICPIM-29787 MapView - Zoom Default | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 16:25 | 1200 | 480 | 720 | 40% | 1200 | 480 | 720 | 40%
Test Case | ICPIM-29779 | ICPIM-29717 Box - Format (Information) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 16:00 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29778 | ICPIM-29717 Box - Format (Aspect Ratio) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 16:00 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29777 | ICPIM-29717 Box - Format (Fill - Gradient) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-11-04 15:59 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50% |  | ICPIM-30448
Test Case | ICPIM-29776 | ICPIM-29717 Box - Format (Fill - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:58 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29775 | ICPIM-29717 Box - Format (Fill - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:57 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29771 | ICPIM-29770 Mapview - Reload Dashboard | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 15:44 | 900 | 420 | 480 | 46% | 900 | 420 | 480 | 46%
Test Case | ICPIM-29769 | ICPIM-29710 3DViewer - Filters - Trace (Power Redundancy) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-04 15:18 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-29768 | ICPIM-29766 Sort Status for Datastore Ascending | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:14 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-29767 | ICPIM-29766 Sort by Data Store options | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:14 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29764 | ICPIM-29761 Sort By NumConnectionsAscending |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:07 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-29763 | ICPIM-29761 Sort By NumConnection |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:06 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-29762 | ICPIM-29717 Box - Format (Box - Dotted) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:06 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29760 | ICPIM-29717 Box - Format (Box - Dashed) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:04 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29758 | ICPIM-29717 Box - Format (Box - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:03 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29757 | ICPIM-29717 Box - Format (Box - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 15:02 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29756 | ICPIM-29754 Sort By ClassNameAscending | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:02 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29755 | ICPIM-29754 Sort By ClassName | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 15:01 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29750 | ICPIM-29747 Sort By NameAscending | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 14:48 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29749 | ICPIM-29747 Sort By Name | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 14:47 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29748 | ICPIM-29747 Sort Descendants | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-04 14:47 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29742 | ICPIM-29739 Mapview - Unanchor Item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 14:35 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-29737 | ICPIM-29557 Sort - Clear Drop Zone |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-11-04 14:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-33647
Test Case | ICPIM-29736 | ICPIM-29717 Box - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 14:21 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29735 | ICPIM-29710 3DViewer - Filters - Trace (Circuit Intersection) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-04 14:20 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-29734 | ICPIM-29717 Box - Zoom Selected | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 14:20 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29733 | ICPIM-29717 Box - Anchor, Unanchor Box | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 14:19 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29729 | ICPIM-29717 Box - Copy and Paste Box | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 14:19 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29728 | ICPIM-29726 Mapview - Unanchor All Items (Edit, Copy) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 14:17 | 1200 | 660 | 540 | 55% | 1200 | 660 | 540 | 55%
Test Case | ICPIM-29727 | ICPIM-29726 Mapview - Unanchor All Items | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 14:16 | 1200 | 780 | 420 | 65% | 1200 | 780 | 420 | 65%
Test Case | ICPIM-29725 | ICPIM-29710 3DViewer - Filters - Trace (Circuit) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-04 14:13 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29721 | ICPIM-29717 Box - Add, Delete Box | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:59 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29716 | ICPIM-29714 Mapview - Anchor All Items (Edit, Copy) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-11-04 13:51 | 600 | 720 | 0 | 100% | 600 | 720 | 0 | 100% |  | ICPIM-30660
Test Case | ICPIM-29715 | ICPIM-29714 Mapview - Anchor All Items (Move) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 13:50 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29706 | ICPIM-29681 Line - Format (Information) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:34 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29705 | ICPIM-29681 Line - Format (Line - Color) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:33 | 900 | 480 | 420 | 53% | 900 | 480 | 420 | 53%
Test Case | ICPIM-29703 | ICPIM-29681 Line - Format (Line - Dotted) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:20 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29702 | ICPIM-29681 Line - Format (Line - Dashed) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:15 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29700 | ICPIM-29681 Line - Format (Line - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 13:02 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29693 | ICPIM-29692 MapView - Create From Class | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 11:57 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-29691 | ICPIM-29690 Mapview - Save For Class | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 11:49 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-29689 | ICPIM-29681 Line - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 11:30 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29685 | ICPIM-29681 Line - Zoom Selected | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 11:26 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29684 | ICPIM-29681 Line - Anchor, Unanchor Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 11:17 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29683 | ICPIM-29681 Line - Copy and Paste Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 11:08 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29682 | ICPIM-29681 Line - Add, Delete Line | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 11:00 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29680 | ICPIM-29580 Image - Format (Information) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 10:39 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29675 | ICPIM-29665 Paste - Copy and paste hot keys | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:31 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29674 | ICPIM-29665 Paste - Poly Line item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:30 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29673 | ICPIM-29580 Image - Format (Aspect Ratio) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 10:30 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29672 | ICPIM-29556 3DViewer - Filters - Search (Visual Virtual Machines) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-04 10:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29671 | ICPIM-29665 Paste - Ellipse item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:29 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29670 | ICPIM-29665 Paste - Box item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:27 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29669 | ICPIM-29665 Paste - Bitmap item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:26 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29668 | ICPIM-29665 Paste - Text item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:25 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29667 | ICPIM-29665 Paste - Line item | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 10:24 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29666 | ICPIM-29580 Image - Format (Image) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 10:20 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29664 | ICPIM-29580 Image - Format (Border - Dotted) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 10:10 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29663 | ICPIM-29556 3DViewer - Filters - Search (Server Pools) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-04 10:06 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29662 | ICPIM-29580 Image - Format (Border - Dashed) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 10:03 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29661 | ICPIM-29556 3DViewer - Filters - Search (Power Search) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-04 10:00 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29660 | ICPIM-29555 DEA - Flat File - File Import/Consumption - Only .CSV Files Are Consumed | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-04 09:59 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-29659 | ICPIM-29555 DEA - Flat File - File Import/Consumption - File Moved to Backups Directory | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-04 09:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-29658 | ICPIM-29555 DEA - Flat File - File Import/Consumption - File "Scraped" Within 10 Seconds | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-04 09:58 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-29657 | ICPIM-29555 DEA - Flat File - Instance Configuration | All |  | Thuy Tran | Garrett S. |  | Fail | 2014-11-04 09:57 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-34494
Test Case | ICPIM-29656 | ICPIM-29555 DEA - Flat File - CSV File Creation (Configuration Step) | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-04 09:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-29655 | ICPIM-29555 DEA - Flat File - Library Item/SKU Creation (Configuration Step) | All |  | Thuy Tran | Garrett S. |  | Pass | 2014-11-04 09:57 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-29654 | ICPIM-29555 DEA - Flat File - Datastore Creation (Configuration Step) | All |  | Garrett S. | Garrett S. |  | Pass | 2014-11-04 09:56 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-29653 | ICPIM-29580 Image - Format (Border - Solid) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 09:55 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29652 | ICPIM-29580 Image - Format (Border - None) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 09:46 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29651 | ICPIM-29556 3DViewer - Filters - Search (Power Configuration) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-04 09:45 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33314, ICPIM-33320
Test Case | ICPIM-29646 | ICPIM-29556 3DViewer - Filters - Search (PE Search) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-11-04 09:32 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-29642 | ICPIM-29580 Image - Format (Border) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 09:29 | 600 | 180 | 420 | 30% | 600 | 180 | 420 | 30%
Test Case | ICPIM-29640 | ICPIM-29556 3DViewer - Filters - Search (Line of Business) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-04 09:19 | 3600 | 4800 | 0 | 100% | 3600 | 4800 | 0 | 100% |  | ICPIM-33273, ICPIM-33276, ICPIM-33279
Test Case | ICPIM-29638 | ICPIM-29556 3DViewer - Filters - Search (Lease Search) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-04 09:03 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33263
Test Case | ICPIM-29637 | ICPIM-29580 Image - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 09:03 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29636 | ICPIM-29626 Dashboard Settings - Information | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:59 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-29635 | ICPIM-29626 Dashboard Settings - Interfaces | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:58 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-29634 | ICPIM-29626 Dashboard Settings - Performance (Performance mode) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-04 08:57 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-29633 | ICPIM-29626 Dashboard Settings - Performance (Overview) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-04 08:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29632 | ICPIM-29580 Image - Zoom Selected | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-04 08:54 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29631 | ICPIM-29626 Dashboard Settings - Background (Gradient) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:53 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-29630 | ICPIM-29626 Dashboard Settings - Background (Color) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:52 | 1200 | 660 | 540 | 55% | 1200 | 660 | 540 | 55%
Test Case | ICPIM-29629 | ICPIM-29626 Dashboard Settings - Background (Solid) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:51 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29628 | ICPIM-29626 Dashboard Settings - Background (None) | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-11-04 08:50 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29627 | ICPIM-29626 Dashboard Settings (Overview) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-11-04 08:47 | 600 | 780 | 0 | 100% | 600 | 780 | 0 | 100%
Test Case | ICPIM-29601 | ICPIM-29580 Image - Anchor, Unanchor Image | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 17:25 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29600 | ICPIM-29580 Image - Copy and Paste Image | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 17:14 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29599 | ICPIM-29000 TC File-Configure-Users: Interfaces -Security-System Tray (Load Interface, Reload Interface, Restore) | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 17:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29598 | ICPIM-29000 TC File-Configure-Users: Interfaces -Security-System Tray (Close All Window, Exit, Help) | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 17:06 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29597 | ICPIM-29000 TC-File-Configure-Users-Interfaces tab-Security tab-Configure security rights (from Users to User View All) | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 17:05 | 5400 | 3600 | 1800 | 66% | 5400 | 3600 | 1800 | 66%
Test Case | ICPIM-29596 | ICPIM-29000 TC-File-Configure-Users-Interfaces tab-Security tab-Configure security rights (from Routing Zones to System Support) | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-03 17:03 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-33858
Test Case | ICPIM-29595 | ICPIM-29000 TC-File-Configure-Users-Interfaces tab-Security tab-Configure security rights (from Interface to Right Remove) | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-03 17:01 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-34006
Test Case | ICPIM-29594 | ICPIM-29000 TC-File-Configure-Users-Interfaces tab-Security tab-Configure security rights (from Events to Remove Event Handler) | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 17:00 | 5400 | 4500 | 900 | 83% | 5400 | 4500 | 900 | 83%
Test Case | ICPIM-29593 | ICPIM-29000 TC-File-Configure-Users-Interfaces tab-Security tab-Configure security rights (from Active Sessions to Device Type) | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 16:57 | 3600 | 4500 | 0 | 100% | 3600 | 4500 | 0 | 100%
Test Case | ICPIM-29592 | ICPIM-29000 TC File-Configure-Users: Interfaces -Security -Application (From "Application - Restart Service" to "Application - Windows Layout") | All |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-11-03 16:56 | 2700 | 1800 | 900 | 66% | 2700 | 1800 | 900 | 66%
Test Case | ICPIM-29591 | ICPIM-29000 TC File-Configure-Users: Interfaces -Security -Application (From "Application - Help" to "Application - Requestor Connection") | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-03 16:55 | 2700 | 2700 | 0 | 100% | 2700 | 2700 | 0 | 100%
Test Case | ICPIM-29590 | ICPIM-29000 TC File-Configure-Users: Interfaces -Security -Application (From "Application - Cascade Windows" to "Application - Favorites") | All |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-11-03 16:53 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33338
Test Case | ICPIM-29589 | ICPIM-28984 Rename an interface. | All |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 16:43 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-29588 | ICPIM-29580 Image - Add Image (Store Internally) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 16:42 | 600 | 540 | 60 | 90% | 600 | 540 | 60 | 90%
Test Case | ICPIM-29587 | ICPIM-29580 Image - Add, Delete Image | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 16:41 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29586 | ICPIM-29556 3DViewer - Filters - Search (CPU Utilization) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:32 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29585 | ICPIM-29556 3DViewer - Filters - Search (End of Lease) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:30 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29584 | ICPIM-29556 3DViewer - Filters - Search (FindAdvanced) | All |  | Trinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:27 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33257
Test Case | ICPIM-29583 | ICPIM-29556 3DViewer - Filters - Search (EnergyStar) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:18 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29582 | ICPIM-29556 3DViewer - Filters - Search (Basic Search Extended) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:14 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33228, ICPIM-33155, ICPIM-33158, ICPIM-33161, ICPIM-33164, ICPIM-33173
Test Case | ICPIM-29581 | ICPIM-29556 3DViewer - Filters - Search (Alarms) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:10 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29579 | ICPIM-29556 3DViewer - Filters - Search (Basic Search) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-11-03 16:02 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-33152, ICPIM-33155, ICPIM-33158
Test Case | ICPIM-29578 | ICPIM-29561 Schemes - Current Scheme |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 15:36 | 900 | 780 | 120 | 86% | 900 | 780 | 120 | 86%
Test Case | ICPIM-29577 | ICPIM-29561 Schemes - Clear Scheme |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 15:35 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-29576 | ICPIM-29533 Text - Order | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 15:29 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29575 | ICPIM-29561 Schemes - Set Scheme |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-03 15:28 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-32796
Test Case | ICPIM-29574 | ICPIM-29556 3DViewer - Filters - Search (Asset - Module) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-03 15:22 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29573 | ICPIM-29561 Schemes - Set Color |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-03 15:21 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70% |  | ICPIM-32795
Test Case | ICPIM-29572 | ICPIM-29556 3DViewer - Filters - Search (Asset - Equipment) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-03 15:17 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29571 | ICPIM-29556 3DViewer - Filters - Search (Asset - Enclosure) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-03 15:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29570 | ICPIM-29533 Text - Zoom Selected Text | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 15:11 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29567 | ICPIM-29533 Text - Anchor, Unanchor Text | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 14:50 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29566 | ICPIM-29561 Schemes - Remove |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 14:33 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29564 | ICPIM-29561 Schemes - Add scheme |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 14:32 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29562 | ICPIM-29561 Schemes - Tabbing, resizing, etc. |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-03 14:31 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50% |  | ICPIM-32793, ICPIM-32794
Test Case | ICPIM-29560 | ICPIM-29533 Text - Copy and Paste Text | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 14:25 | 600 | 360 | 240 | 60% | 600 | 360 | 240 | 60%
Test Case | ICPIM-29559 | ICPIM-29557 Sort - Drop Zone |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-03 13:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29558 | ICPIM-29557 Launch the Sort Dialog |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-11-03 13:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29553 | ICPIM-29534 3DViewer - Hide list (V key) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-03 12:46 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29552 | ICPIM-29534 3DViewer - Hide list (Show Layers) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-11-03 12:45 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66% |  | ICPIM-30349
Test Case | ICPIM-29549 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Option Group - Web Interface) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:11 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-29548 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show Intelligent Ports Icon) |  |  | Mai Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:10 | 600 | 3600 | 0 | 100% | 600 | 3600 | 0 | 100% |  | ICPIM-33680
Test Case | ICPIM-29547 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show Device Status Icon) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Blocker | 2014-11-03 12:09 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-29243, ICPIM-34262
Test Case | ICPIM-29546 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show IT Services Instead of Schemes) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:07 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29545 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show Object Library Ids) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:06 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-29544 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show UpLinks) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:06 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29543 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show Number of Connections) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:05 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29542 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Show Class Name, Show Sub-Class Name) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29541 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Option Group - Equipment Items) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 12:02 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29540 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Navigator Hot Tracking) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 11:57 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29539 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Fonts) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-11-03 11:56 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-29707
Test Case | ICPIM-29538 | ICPIM-29536 TC - File - Configure My Settings - Functionality (Dropdowns) |  |  | Trinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-11-03 11:53 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29537 | ICPIM-29536 TC - File - Configure My Settings - My Settings (Menus, hotkeys, help, etc) |  |  | Ben Winters | Trinh Nguyen | Windows Client | Pass | 2014-11-03 11:50 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100%
Test Case | ICPIM-29535 | ICPIM-29533 Text - Add, Delete Text | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 11:42 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29532 | ICPIM-29527 Mapview - Remove (From Another Dashboard) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 10:45 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29531 | ICPIM-29527 Mapview - Remove (From Viewer) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 10:44 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29530 | ICPIM-29527 Mapview - Remove (From Trace) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 10:43 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29529 | ICPIM-29527 Mapview - Remove (From Browser) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 10:42 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29528 | ICPIM-29527 Mapview - Remove (From Navigator) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 10:39 | 600 | 480 | 120 | 80% | 600 | 480 | 120 | 80%
Test Case | ICPIM-29524 | ICPIM-29522 Mapview - Export | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-11-03 09:48 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29427 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Environment) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 15:52 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29426 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Heat - Top) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 15:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-35048
Test Case | ICPIM-29425 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Heat - Middle) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 15:37 | 900 | 1020 | 0 | 100% | 900 | 1020 | 0 | 100% |  | ICPIM-35048
Test Case | ICPIM-29424 | ICPIM-28786 Create Dictionary - General |  |  | An Vo | An Vo | Windows Client | Pass | 2014-10-31 15:35 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29423 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Heat - Bottom) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 15:27 | 900 | 1080 | 0 | 100% | 900 | 1080 | 0 | 100% |  | ICPIM-35048
Test Case | ICPIM-29421 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Heat) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 15:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-35048
Test Case | ICPIM-29420 | ICPIM-28927 Display - Leave Without Applying | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-31 15:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29419 | ICPIM-28984 User Management - Export Interface | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-31 14:58 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29417 | ICPIM-28984 User Management - Import Interface | All |  | An Vo | An Vo | Windows Client | Fail | 2014-10-31 14:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-29431, ICPIM-29434
Test Case | ICPIM-29415 | ICPIM-29414 User Management - Remove Interface | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-31 14:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29413 | ICPIM-29412 User Management - Clone Interface | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-31 14:53 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29411 | ICPIM-29410 User Management - Add Interface | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-31 14:51 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29406 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Fragmentation) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 14:40 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-29403 | ICPIM-29296 CSV - Copy to Server (Transfer sub tab) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-31 14:23 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100%
Test Case | ICPIM-29402 | ICPIM-29296 CSV - Copy to Server (Connect sub tab - Overview) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-31 14:21 | 2400 | 1500 | 900 | 62% | 2400 | 1500 | 900 | 62%
Test Case | ICPIM-29398 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Space) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 13:45 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-29396 | ICPIM-29395 Item Context Menu - Fit to Window | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-31 13:19 | 600 | 420 | 180 | 70% | 600 | 420 | 180 | 70%
Test Case | ICPIM-29385 | ICPIM-29384 Mapview - Import | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-31 10:47 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-29382 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - General (Lock Aspect Ratio) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-31 10:09 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-29381 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (General - Rotation) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-31 10:08 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-29380 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - Border (None, Solid, Dashed, Dotted) | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-28069
Test Case | ICPIM-29379 | ICPIM-29364 Pasted Item Options Menu - Format - Viewer - Masks | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:07 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0% |  | ICPIM-28068
Test Case | ICPIM-29378 | ICPIM-29364 Pasted Item Options Menu – Format - Viewstate (Top, Front, Back, User created viewstate) | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-28067
Test Case | ICPIM-29377 | ICPIM-29364 Pasted Item Options Menu – Format - Viewer Properties Dialog | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:05 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-28066
Test Case | ICPIM-29376 | ICPIM-29364 Pasted Item Options Menu -Format - Dashboard - Information | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:04 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-28065
Test Case | ICPIM-29375 | ICPIM-29364 Pasted Item Options Menu - Format - Dashboard – URL TC | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:03 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0% |  | ICPIM-28064
Test Case | ICPIM-29374 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (General - Object Alias) | All |  | An Vo | An Vo | Windows Client | Invalid | 2014-10-31 10:03 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-29373 | ICPIM-29364 Pasted Item Options Menu - Format - Dashboard – General (Rotation) | All |  | Tien Pham | Tien Pham | Windows Client | Invalid | 2014-10-31 10:02 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-28063
Test Case | ICPIM-29372 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (General - Link As Host) | All |  | An Vo | An Vo | Windows Client | Invalid | 2014-10-31 10:01 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-29371 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (General - Lock Aspect Ratio, Allow Connections, Allow Navigation and Anchor) | All |  | Tien Pham | An Vo | Windows Client | Invalid | 2014-10-31 09:57 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0% |  | ICPIM-28037
Test Case | ICPIM-29370 | ICPIM-29361 3DViewer - Filters - Calculated (Cabinet Power) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-31 09:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-29369 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (Border) | All |  | An Vo | An Vo |  | Invalid | 2014-10-31 09:55 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-29368 | ICPIM-29364 Pasted Item Options Menu - Format - Icon (Fill) | All |  | An Vo | An Vo |  | Invalid | 2014-10-31 09:52 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-29367 | ICPIM-29364 Pasted Items Options - Format (Icon) | All |  | An Vo | An Vo |  | Invalid | 2014-10-31 09:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-28034
Test Case | ICPIM-29366 | ICPIM-29364 Pasted Items Options - View Definitions | All |  | An Vo | An Vo |  | Invalid | 2014-10-31 09:47 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-28033
Test Case | ICPIM-29365 | ICPIM-29364 Pasted Items Options - Options | All |  | An Vo | An Vo |  | Invalid | 2014-10-31 09:46 | 600 |  | 600 | 0% | 600 |  | 600 | 0% |  | ICPIM-28032
Test Case | ICPIM-29363 | ICPIM-29301 Auto Routing - Globals - Color Cables by IT Service |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-31 09:40 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-29362 | ICPIM-29301 Auto Routing - Globals - Error Circuit Color - By Name or By RGB |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-31 09:40 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-29331 | ICPIM-29320 3DViewer - Hide Item (H key) | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-10-30 16:32 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31410
Test Case | ICPIM-29330 | ICPIM-29320 3DViewer - Hide Item (Display) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-10-30 16:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29329 | ICPIM-29316 Configure the "Web service Security" option of the "Web Service" tab | All |  | Trinh Nguyen | Tien Pham | Windows Client | Blocker | 2014-10-30 16:29 | 1500 | 7200 | 0 | 100% | 1500 | 7200 | 0 | 100% |  | ICPIM-34030, ICPIM-33916
Test Case | ICPIM-29328 | ICPIM-29316 Configure the "Use HTTPS" option of the "Web Services" tab | All |  | Mai Nguyen | Tien Pham | Windows Client | Invalid | 2014-10-30 16:28 | 900 | 7200 | 0 | 100% | 900 | 7200 | 0 | 100% |  | ICPIM-34030
Test Case | ICPIM-29327 | ICPIM-29316 Configure the "Log" and "SOAP Message Logging" options of the "Web Services" tab | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-30 16:26 | 1800 | 7200 | 0 | 100% | 1800 | 7200 | 0 | 100%
Test Case | ICPIM-29326 | ICPIM-29316 Configure the File Name of the "Allowed IP Address List" field of the "Web Service" tab | All |  | Trinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-30 16:24 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-34011
Test Case | ICPIM-29325 | ICPIM-29316 Configure the "Port" and "SOAP Message Timeout" settings of the "Web Service" tab | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-30 16:23 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-29324 | ICPIM-29316 Working with the Save and Load Certificate buttons of the "Web Service" tab | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-30 16:22 | 1500 | 5400 | 0 | 100% | 1500 | 5400 | 0 | 100% |  | ICPIM-33916
Test Case | ICPIM-29323 | ICPIM-29315 Configure access profiles to determine which web services user can access | All |  | Suzette Weiss | Tien Pham | Windows Client | Pass | 2014-10-30 16:16 | 1500 | 1080 | 420 | 72% | 1500 | 1080 | 420 | 72%
Test Case | ICPIM-29321 | ICPIM-29319 Commission - Remove IT Service |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 16:07 | 600 | 180 | 420 | 30% | 600 | 180 | 420 | 30%
Test Case | ICPIM-29318 | ICPIM-29314 Access to an email server within network | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-30 16:04 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29317 | ICPIM-29314 Verify the overview of the "Email" tab | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-30 16:02 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29313 | ICPIM-29310 Verify the overview of the "Support" tab of the "Generate" main-tab within the "Configure System" window |  |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-30 15:49 | 900 | 1080 | 0 | 100% | 900 | 1080 | 0 | 100%
Test Case | ICPIM-29312 | ICPIM-29306 Web Interfaces - Image Quality | All |  | Suzette Weiss | An Vo | Windows Client | New | 2014-10-30 15:43 | 1200 | 600 | 600 | 50% | 1200 | 600 | 600 | 50%
Test Case | ICPIM-29311 | ICPIM-29306 Web Interfaces - SSL Port | All |  | Suzette Weiss | An Vo | Windows Client | Pass | 2014-10-30 15:42 | 1200 | 420 | 780 | 35% | 1200 | 420 | 780 | 35%
Test Case | ICPIM-29309 | ICPIM-29306 Web Interfaces - Show on Login, Window Limit | All |  | Suzette Weiss | An Vo | Windows Client | In Progress | 2014-10-30 15:41 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29308 | ICPIM-29306 Web Interfaces - Clear Cache, Enable Web Server, Disable Web Server, Restart Web Server | All |  | Suzette Weiss | An Vo | Windows Client | Fail | 2014-10-30 15:40 | 1200 | 2100 | 0 | 100% | 1200 | 2100 | 0 | 100%
Test Case | ICPIM-29307 | ICPIM-29306 Web Interfaces - Root Location, Browser, Save, Port | All |  | Suzette Weiss | An Vo | Windows Client | Pass | 2014-10-30 15:39 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100%
Test Case | ICPIM-29305 | ICPIM-29304 Administration - Server | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-30 15:32 | 900 | 780 | 120 | 86% | 900 | 780 | 120 | 86% |  | ICPIM-29397
Test Case | ICPIM-29303 | ICPIM-29297 Search - Find Dashboards | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-10-30 14:19 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29302 | ICPIM-29301 Commission - Configure IT Service |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 14:14 | 1800 | 840 | 960 | 46% | 1800 | 840 | 960 | 46%
Test Case | ICPIM-29300 | ICPIM-29000 Configure Database security rights (Default and SNMP security rights) | All |  | Trinh Nguyen | Tien Pham | Windows Client | Blocker | 2014-10-30 14:08 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-34075, ICPIM-34262
Test Case | ICPIM-29299 | ICPIM-29000 Configure Database security rights (from Import Analyzer Mappings to View Import) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-10-30 14:06 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-29298 | ICPIM-29000 Configure Database security rights (from Analyzer Mapping to Import) | All |  | An Vo | Tien Pham | Windows Client | Pass | 2014-10-30 14:04 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-29289 | ICPIM-29255 Verify the overview of the "Manage Security Settings" window |  |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-30 13:17 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29281 | ICPIM-29168 Alarm Manager - Highlight And View Affected Equipmnet | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-30 10:54 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29280 | ICPIM-29168 Alarm Manager - Buttons | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-30 10:52 | 1500 | 1260 | 240 | 84% | 1500 | 1260 | 240 | 84%
Test Case | ICPIM-29278 | ICPIM-29261 Auto Routing - IT Service - Choose Intermediate patches by shortest distance | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:17 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29277 | ICPIM-29261 Auto Routing - IT Service - Choose Final Patch by shortest distance | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:17 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29276 | ICPIM-29261 Auto Routing - IT Service - Allow Front to back patching | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:16 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29275 | ICPIM-29261 Auto Routing - IT Service - Patch Rule - Within Any Equipment Room | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:16 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29274 | ICPIM-29261 Auto Routing - IT Service - Patch Rule - Within Equipment Room Only | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:16 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29273 | ICPIM-29261 Auto Routing - IT Service - Patch Rule - Within Row Only | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:16 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29272 | ICPIM-29261 Auto Routing - IT Service- Patch Rule - Within Enclosure only | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:15 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29271 | ICPIM-29261 Auto Routing - IT Service - Max Hop | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:15 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29270 | ICPIM-29261 IT Service - Currency Prefix | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:15 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29269 | ICPIM-29261 IT Service - Connector Types | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:15 | 900 | 480 | 420 | 53% | 900 | 480 | 420 | 53%
Test Case | ICPIM-29268 | ICPIM-29261 IT Service - Description | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:15 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29267 | ICPIM-29261 IT Service - Cost | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:14 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29266 | ICPIM-29261 IT Service - Color | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:14 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29265 | ICPIM-29261 IT Service - Link Class | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-30 10:14 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-33377
Test Case | ICPIM-29264 | ICPIM-29261 IT Service - Name | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:14 | 600 | 660 | 0 | 100% | 600 | 660 | 0 | 100%
Test Case | ICPIM-29262 | ICPIM-29261 Auto Routing - Add IT service | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-30 10:14 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-29254 | ICPIM-29251 Backup - Automatic | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-30 09:12 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-29253 | ICPIM-29251 Backup - Manual | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-30 09:11 | 1500 | 540 | 960 | 36% | 1500 | 540 | 960 | 36%
Test Case | ICPIM-29252 | ICPIM-29251 Backup - General | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-10-30 09:10 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100% |  | ICPIM-29467, ICPIM-29470, ICPIM-29780, ICPIM-29743
Test Case | ICPIM-29236 | ICPIM-29168 Alarm Manager - Log | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 17:40 | 600 | 240 | 360 | 40% | 600 | 240 | 360 | 40%
Test Case | ICPIM-29235 | ICPIM-29229 Setting the "Dashboard Default" option | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-29 17:39 | 2400 | 3600 | 0 | 100% | 2400 | 3600 | 0 | 100% |  | ICPIM-29602
Test Case | ICPIM-29234 | ICPIM-29168 Alarm Manager - Remove Alarm | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 17:39 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29233 | ICPIM-29229 Setting the "Navigator Default" option | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-29 17:38 | 2400 | 5400 | 0 | 100% | 2400 | 5400 | 0 | 100% |  | ICPIM-29602
Test Case | ICPIM-29232 | ICPIM-29168 Alarm Manager - Edit Alarm | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 17:38 | 1500 | 2040 | 0 | 100% | 1500 | 2040 | 0 | 100% |  | ICPIM-29827
Test Case | ICPIM-29231 | ICPIM-29229 Observe the overview of the "Data" sub-tab | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-29 17:37 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29230 | ICPIM-29168 Alarm Manager - Filter Alarm | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 17:37 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29213 | ICPIM-29200 Basic Search - Within a Location (Include Descendants) | All |  | Trinh Nguyen | Loan Ha | Windows Client | Invalid | 2014-10-29 17:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-31477
Test Case | ICPIM-29212 | ICPIM-29201 Types - Remove Non-Default Type | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 17:00 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29211 | ICPIM-29201 Types - Edit Statuses | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 17:00 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29210 | ICPIM-29201 Types - Edit Actions | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 17:00 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29209 | ICPIM-29201 Types - Add Statuses | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 17:00 | 900 | 240 | 660 | 26% | 900 | 240 | 660 | 26%
Test Case | ICPIM-29208 | ICPIM-29201 Types - Add Actions | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 17:00 | 900 | 240 | 660 | 26% | 900 | 240 | 660 | 26%
Test Case | ICPIM-29207 | ICPIM-29201 Types - Fields associated with Statuses | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 16:59 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29206 | ICPIM-29201 Types - Fields associated with Actions | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 16:59 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29205 | ICPIM-29201 Types - Default Statuses List | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 16:58 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29204 | ICPIM-29201 Types - Default Actions list | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 16:58 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29203 | ICPIM-29201 Types tab - UI check | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 16:58 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29202 | ICPIM-29200 Basic Search - Within a Location | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-29 16:53 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-30164
Test Case | ICPIM-29199 | ICPIM-29197 Basic Search - By Model | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-29 16:09 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100%
Test Case | ICPIM-29196 | ICPIM-29195 Change Management - Remove General Order | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 15:46 | 900 | 180 | 720 | 20% | 900 | 180 | 720 | 20%
Test Case | ICPIM-29194 | ICPIM-29189 General Orders - Update General Order | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 15:36 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-29193 | ICPIM-29144 Basic Search - By Scheme | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-29 15:36 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29192 | ICPIM-29189 General Orders - Currency Prefix | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 15:35 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-29191 | ICPIM-29189 General orders - Cost | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 15:35 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-29190 | ICPIM-29189 General orders - Create General order | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 15:35 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-29184 | ICPIM-29183 Change Management - Remove Cost Center | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 14:28 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29182 | ICPIM-29181 Change Management - Clone Cost Center | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 14:23 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29180 | ICPIM-29179 Change Management - Add Cost Center | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-29 14:03 | 600 | 120 | 480 | 20% | 600 | 120 | 480 | 20%
Test Case | ICPIM-29178 | ICPIM-29168 Alarm Manager - Filters (Cabling) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 14:00 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29177 | ICPIM-29168 Alarm Manager - Filters (IT Assets) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:59 | 900 | 360 | 540 | 40% | 900 | 360 | 540 | 40%
Test Case | ICPIM-29176 | ICPIM-29168 Alarm Manager - Filters (Powers) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:58 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29175 | ICPIM-29168 Alarm Manager - Filters (Enclosures) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:57 | 900 | 420 | 480 | 46% | 900 | 420 | 480 | 46%
Test Case | ICPIM-29174 | ICPIM-29168 Alarm Manager - Filters (Rows) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:56 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29173 | ICPIM-29168 Alarm Manager - Filters (Floor) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:54 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-29172 | ICPIM-29168 Alarm Manager - Filters (Roof) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:53 | 900 | 960 | 0 | 100% | 900 | 960 | 0 | 100%
Test Case | ICPIM-29171 | ICPIM-29168 Alarm Manager - Filters (Building) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:52 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29169 | ICPIM-29168 Alarm Manager (Viewer Pane) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 13:51 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-29167 | ICPIM-29131 Deleting a Task | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 13:30 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29166 | ICPIM-29131 Creating a New Task | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Fail | 2014-10-29 13:06 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29155 | ICPIM-29101 Authorize an un-authorize log entry in the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | New | 2014-10-29 11:00 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0%
Test Case | ICPIM-29149 | ICPIM-29147 Delete a selected log entry in the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-29 10:55 | 1200 | 960 | 240 | 80% | 1200 | 960 | 240 | 80%
Test Case | ICPIM-29146 | ICPIM-29145 Assign a log view to the selected user | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-29 10:48 | 1800 | 840 | 960 | 46% | 1800 | 840 | 960 | 46%
Test Case | ICPIM-29143 | ICPIM-29131 Tasks - Verify | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:07 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29142 | ICPIM-29131 Tasks - Task | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29141 | ICPIM-29131 Tasks - Review Work | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29140 | ICPIM-29131 Tasks - Review Change Request | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29139 | ICPIM-29131 Tasks - Resolve | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29138 | ICPIM-29131 Tasks - Re-Plan Change Request | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29137 | ICPIM-29131 Tasks - Plan Change request | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:06 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29136 | ICPIM-29131 Tasks - Execute Work | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:05 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29135 | ICPIM-29131 Tasks - Assign Work | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:05 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29134 | ICPIM-29131 Tasks - Approve Plan Change request | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:05 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29133 | ICPIM-29131 Tasks - Approve Change Request | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:05 | 900 | 120 | 780 | 13% | 900 | 120 | 780 | 13%
Test Case | ICPIM-29132 | ICPIM-29131 Access the Tasks Tab | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-29 10:02 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29130 | ICPIM-29105 Basic Search - By Manufacturer | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-29 09:57 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-29129 | ICPIM-29106 Set Template (Import and Export OID Template) | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-10-29 09:47 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70% |  | ICPIM-29441
Test Case | ICPIM-29128 | ICPIM-29106 Set Template (Discover Device Type - Negative Case) | All |  | Vinh Nguyen | An Vo | Windows Client | Blocker | 2014-10-29 09:46 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-29243, ICPIM-34262
Test Case | ICPIM-29127 | ICPIM-29106 Set Template (Discover Device Type) | All |  | Vinh Nguyen | An Vo | Windows Client | Blocker | 2014-10-29 09:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0% |  | ICPIM-29243, ICPIM-34262
Test Case | ICPIM-29126 | ICPIM-29106 Set Template (Search OID Template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:42 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-29125 | ICPIM-29106 Set Template (Expansion - Edit Script) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:41 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-29124 | ICPIM-29106 Set Template (Expansion - Add, Remove Script) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:39 | 1200 | 960 | 240 | 80% | 1200 | 960 | 240 | 80%
Test Case | ICPIM-29123 | ICPIM-29106 Set Template (Schematic - Rotate Viewer template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:35 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-29122 | ICPIM-29106 Set Template (Schematic - Remove Viewer template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:34 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-29121 | ICPIM-29030 Refresh the log entries in the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-29 09:34 | 900 | 780 | 120 | 86% | 900 | 780 | 120 | 86%
Test Case | ICPIM-29120 | ICPIM-29106 Set Template (Schematic - Set Viewer template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:32 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29119 | ICPIM-29106 Set Template (Creation - Override Interface) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:31 | 1200 | 960 | 240 | 80% | 1200 | 960 | 240 | 80%
Test Case | ICPIM-29116 | ICPIM-29106 Set Template (Creation - Override Creation Class) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:30 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-29112 | ICPIM-29106 Set Template (Add OID Template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-29 09:28 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-29104 | ICPIM-29103 Open and observe the overall look of the "Log Entry Details" window of the selected log entry in the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-28 17:13 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80% |  | ICPIM-29816
Test Case | ICPIM-29102 | ICPIM-29101 Enter comment to a log entry in the "Log Comment" window by selecting "Comment" context menu from the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 17:07 | 1200 | 660 | 540 | 55% | 1200 | 660 | 540 | 55%
Test Case | ICPIM-29100 | ICPIM-29090 Basic Search - By Number of Descendants (<>) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29099 | ICPIM-29090 Basic Search - By Number of Descendants (>=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:53 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29098 | ICPIM-29090 Basic Search - By Number of Descendants (<=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:53 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29097 | ICPIM-29090 Basic Search - By Number of Descendants (>) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:52 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29096 | ICPIM-29090 Basic Search - By Number of Descendants (<) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:51 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29095 | ICPIM-29090 Basic Search - By Number of Descendants (=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:50 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29089 | ICPIM-29087 Generate report based on the selected log entries on the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 16:31 | 1500 | 1020 | 480 | 68% | 1500 | 1020 | 480 | 68%
Test Case | ICPIM-29088 | ICPIM-29086 Generate report based on all log entries on the "Log" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 16:27 | 2100 | 1020 | 1080 | 48% | 2100 | 1020 | 1080 | 48%
Test Case | ICPIM-29083 | ICPIM-29079 Manage the view of log entries by configuring in the "Filters" tab within the "Log View Manager" window | All |  | Mai Nguyen | Tien Pham | Windows Client | Fail | 2014-10-28 16:05 | 2100 | 2880 | 0 | 100% | 2100 | 2880 | 0 | 100% |  | ICPIM-29940, ICPIM-8239
Test Case | ICPIM-29082 | ICPIM-29076 Basic Search - By Line of Business | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 16:04 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-29081 | ICPIM-29078 Manage the view of log entries by configuring in the "Types" tab within the "Log View Manager" window | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-28 16:03 | 1200 | 1140 | 60 | 95% | 1200 | 1140 | 60 | 95% |  | ICPIM-29939
Test Case | ICPIM-29074 | ICPIM-29073 Create Log View | All |  | Trinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 15:54 | 2100 | 1080 | 1020 | 51% | 2100 | 1080 | 1020 | 51% |  | ICPIM-29938, ICPIM-29939
Test Case | ICPIM-29068 | ICPIM-29064 User Management - Unassign Team members | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-28 15:37 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-29067 | ICPIM-29051 Basic Search - By Name (partial name - ending) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 15:34 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29066 | ICPIM-29064 User Management - Assign Team members | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-28 15:33 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-29065 | ICPIM-29051 Basic Search - By Name (partial name - beginning) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 15:33 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29063 | ICPIM-29058 Manage Teams 'iTRACS_T_' from Active Directory | All |  | Vinh Nguyen | An Vo | Windows Client | New | 2014-10-28 15:25 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-29062 | ICPIM-29051 Basic Search - By Name (partial name - middle) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 15:25 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29061 | ICPIM-29058 Manage interfaces 'iTRACS_I_' from Active Directory | All |  | Vinh Nguyen | An Vo | Windows Client | New | 2014-10-28 15:24 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-29060 | ICPIM-29058 Enforce 'iTRACS_U' group membership within Active Directory for Domain login | All |  | Vinh Nguyen | An Vo | Windows Client | New | 2014-10-28 15:23 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-29059 | ICPIM-29058 Enforce 'iTRACS_U' group membership within Active Directory for Unified login | All |  | Vinh Nguyen | An Vo | Windows Client | New | 2014-10-28 15:22 | 1500 | 3600 | 0 | 100% | 1500 | 3600 | 0 | 100%
Test Case | ICPIM-29057 | ICPIM-29051 Basic Search - By Name (whole name) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 15:18 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-29056 | ICPIM-28816 Save the alert in "Default Alerts" tab | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 15:12 | 1800 | 2220 | 0 | 100% | 1800 | 2220 | 0 | 100%
Test Case | ICPIM-29055 | ICPIM-28816 Assign Value fields to an alert in "Default Alerts" tab | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-28 15:10 | 2700 | 1440 | 1260 | 53% | 2700 | 1440 | 1260 | 53% |  | ICPIM-29643
Test Case | ICPIM-29054 | ICPIM-28816 Delete alert in "Default Alerts" tab | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 15:09 | 1500 | 480 | 1020 | 32% | 1500 | 480 | 1020 | 32%
Test Case | ICPIM-29053 | ICPIM-28816 Enable, disable alert in "Default Alerts" tab | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 15:08 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-29050 | ICPIM-29049 User Management - Remove Team | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-28 14:38 | 600 | 60 | 540 | 10% | 600 | 60 | 540 | 10%
Test Case | ICPIM-29048 | ICPIM-29012 Basic Search - By Data Store (Pickoff "<>", "Owned") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 14:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29047 | ICPIM-29012 Basic Search - By Data Store (Pickoff "<>", "Managed") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 14:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29044 | ICPIM-29038 User Management - Create Team with Team Emails | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-28 14:23 | 900 | 60 | 840 | 6% | 900 | 60 | 840 | 6%
Test Case | ICPIM-29043 | ICPIM-29038 User Management - Create Team | All |  | Suzette Weiss | Rachna Muthanna | Windows Client | Pass | 2014-10-28 14:22 | 900 | 60 | 840 | 6% | 900 | 60 | 840 | 6%
Test Case | ICPIM-29042 | ICPIM-29012 Basic Search - By Data Store (Pickoff "=", "Managed") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 14:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29041 | ICPIM-29012 Basic Search - By Data Store (Pickoff "=", "Leased") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 14:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29039 | ICPIM-28998 Update report settings without saving | All |  | Tien Pham | Tien Pham | Windows Client | Blocker | 2014-10-28 14:15 | 2100 | 1800 | 300 | 85% | 2100 | 1800 | 300 | 85% |  | ICPIM-29446
Test Case | ICPIM-29037 | ICPIM-29012 Basic Search - By Data Store (Yes/No "<>" "No") | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 14:13 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30075
Test Case | ICPIM-29036 | ICPIM-28998 Remove Search Report Teams from user | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-28 14:13 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-29401, ICPIM-29446
Test Case | ICPIM-29035 | ICPIM-29012 Basic Search - By Data Store (Yes/No "<>" "Yes") | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 14:12 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30075
Test Case | ICPIM-29034 | ICPIM-28998 Add Search reports to user | All |  | Tien Pham | Tien Pham | Windows Client | Blocker | 2014-10-28 14:12 | 2400 | 3600 | 0 | 100% | 2400 | 3600 | 0 | 100% |  | ICPIM-29401, ICPIM-29446
Test Case | ICPIM-29033 | ICPIM-29012 Basic Search - By Data Store (Yes/No "=" "No") | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 14:10 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30075
Test Case | ICPIM-29032 | ICPIM-29012 Basic Search - By Data Store (Yes/No "=" "Yes") | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 14:05 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-30075
Test Case | ICPIM-29031 | ICPIM-29030 Log - Log Viewer | All |  | Trinh Nguyen | An Vo | Windows Client | Invalid | 2014-10-28 14:00 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0% |  | ICPIM-29840, ICPIM-40441
Test Case | ICPIM-29029 | ICPIM-29012 Basic Search - By Data Store (Pickoff "<>", "Leased") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29028 | ICPIM-29012 Basic Search - By Data Store (Pickoff "=", "Owned") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:51 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29027 | ICPIM-28744 Ensure Enforce SKU Button Works on Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 13:47 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-29026 | ICPIM-29012 Basic Search - By Data Store (Value "Not Contain") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29025 | ICPIM-29012 Basic Search - By Data Store (Value "Ends with") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29024 | ICPIM-29012 Basic Search - By Data Store (Value "Contains") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29023 | ICPIM-29012 Basic Search - By Data Store (Value "Begins with") | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 13:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29022 | ICPIM-29012 Basic Search - By Data Store (Value <>) | All |  | Trinh Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 13:39 | 900 | 4500 | 0 | 100% | 900 | 4500 | 0 | 100% |  | ICPIM-29932, ICPIM-34442, ICPIM-34454
Test Case | ICPIM-29021 | ICPIM-29012 Basic Search - By Data Store (Value =) | All |  | Trinh Nguyen | Loan Ha | Windows Client | Fail | 2014-10-28 13:38 | 1800 | 9000 | 0 | 100% | 1800 | 9000 | 0 | 100% |  | ICPIM-29932, ICPIM-34442, ICPIM-34445, ICPIM-34448
Test Case | ICPIM-29020 | ICPIM-29000 User Management - Security (Customize setting) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 13:32 | 1500 | 3900 | 0 | 100% | 1500 | 3900 | 0 | 100% |  | ICPIM-29286
Test Case | ICPIM-29018 | ICPIM-29000 User Management - Security (Quick Edit: Only Defaults) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 13:30 | 1200 | 1500 | 0 | 100% | 1200 | 1500 | 0 | 100% |  | ICPIM-29286
Test Case | ICPIM-29009 | ICPIM-29004 Nav Trace- Parent | All |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2014-10-28 12:45 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-32943
Test Case | ICPIM-29008 | ICPIM-29004 Nav Trace- Crop | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-28 12:45 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29007 | ICPIM-29004 Nav Trace- Visual Trace Pane | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-28 12:45 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100% |  | ICPIM-30997
Test Case | ICPIM-29006 | ICPIM-29004 Nav Trace – Navigation Pane | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-28 12:45 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29005 | ICPIM-29004 Nav Trace – Launch dialog | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-28 12:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-29003 | ICPIM-28991 Basic Search - By IT Service (Providers Only) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 12:38 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-29002 | ICPIM-29000 User Management - Security (Quick Edit: Edit Scripts) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 12:32 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-29286
Test Case | ICPIM-29001 | ICPIM-29000 User Management - Security (Quick Edit: Read Only) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 12:31 | 1200 | 2400 | 0 | 100% | 1200 | 2400 | 0 | 100% |  | ICPIM-29286
Test Case | ICPIM-28999 | ICPIM-28991 Basic Search - By IT Service | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-28 12:28 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28989 | ICPIM-28984 Update the Interface settings without saving | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:46 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28988 | ICPIM-28984 Assign a language to an interface | All |  | Trinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-28 11:44 | 1500 | 2700 | 0 | 100% | 1500 | 2700 | 0 | 100% |  | ICPIM-33285
Test Case | ICPIM-28987 | ICPIM-28984 Log in with account that has no assigned interface | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:43 | 1500 | 300 | 1200 | 20% | 1500 | 300 | 1200 | 20%
Test Case | ICPIM-28986 | ICPIM-28984 Unassign interface from a selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:41 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-28985 | ICPIM-28984 Assign an interface to a selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:41 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-28983 | ICPIM-28926 Verify the functionality of the "Web Access" option | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-28 11:28 | 1500 | 18900 | 0 | 100% | 1500 | 18900 | 0 | 100% |  | ICPIM-34044
Test Case | ICPIM-28982 | ICPIM-28926 Verify the functionality of the "Login Method" option while setting to "Domain" | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-28 11:26 | 2400 | 2400 | 0 | 100% | 2400 | 2400 | 0 | 100% |  | ICPIM-29485, ICPIM-29482
Test Case | ICPIM-28981 | ICPIM-28926 Verify the functionality of the "Login Method" option while setting to "Unified" | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-28 11:25 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100% |  | ICPIM-29488
Test Case | ICPIM-28980 | ICPIM-28926 Verify the functionality of the "Login Method" option while setting to "Default" | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:11 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28976 | ICPIM-28926 Verify the functionality of the "Lock user out after x failed login attempts" option | All |  | Trinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 11:06 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-29354
Test Case | ICPIM-28974 | ICPIM-28926 Verify the functionality of the "Minimum password length" option | All |  | Trinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 11:03 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-29354
Test Case | ICPIM-28973 | ICPIM-28926 Verify the functionality of the "Password expires verify" option | All |  | Trinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-28 11:01 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-29354
Test Case | ICPIM-28972 | ICPIM-28966 User Management -Teams (Leave Without Saving) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 11:00 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60%
Test Case | ICPIM-28971 | ICPIM-28926 Verify the functionality of the “Password Change Required” dialog | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 11:00 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28970 | ICPIM-28966 User Management - Teams (Unassigned Team To User) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28969 | ICPIM-28926 Set the "User must change password at next logon" option for selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:59 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28968 | ICPIM-28966 User Management - Teams (Assign Team To User) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28967 | ICPIM-28926 Lock or unlock a selected user from logging into iTRACS CPIM | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:57 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28965 | ICPIM-28926 Set PIN number for selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:56 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28964 | ICPIM-28926 Update the password for selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:54 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28963 | ICPIM-28744 Ensure Force Placement Button Works Correctly on Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28962 | ICPIM-28744 Ensure Assets Are Moved From Location Conflict to Mapped When Location Conflict is Resolved Using Editable Fields on Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:53 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28961 | ICPIM-28744 Ensure Changes to the Editable Fields in Location Conflict Tab Are Saved When Save Button is Clicked | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:52 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28960 | ICPIM-28926 Update the Account settings without saving | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:52 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-28959 | ICPIM-28744 Ensure the Slot Field is Editable in the Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:52 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28958 | ICPIM-28744 Ensure U Position Field is Editable in the Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28957 | ICPIM-28926 Update the account settings for selected user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:51 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28956 | ICPIM-28744 Ensure Enclosure Pad Field is Editable in Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28955 | ICPIM-28744 Ensure Asset Moves From Location Conflict to Mapped When Location Conflict is Resolved Through The Data Exchange Location Conflicts Dialog | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:51 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28954 | ICPIM-28744 Ensure Force Location Button Works Correctly in the Data Exchange Location Conflicts Dialog | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:50 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28953 | ICPIM-28926 Update the account settings for administrator user | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:50 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28952 | ICPIM-28744 Ensure Apply Button Functions Correctly in the Data Exchange Location Conflicts Dialog | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:50 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28951 | ICPIM-28744 Ensure a New Location Can Be Entered in Data Exchange Location Conflicts Dialog | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28950 | ICPIM-28744 Ensure Data Exchange Location Conflicts Dialog Viewer Pane Displays Correctly | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:49 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28949 | ICPIM-28744 Ensure Data Displayed in Data Exchange Location Conflicts Dialog Changes when a Different Child Asset is Selected | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:42 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28948 | ICPIM-28744 Ensure Data Displayed in Data Exchange Location Conflicts Dialog is Accurate per the Selected Asset | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:41 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28947 | ICPIM-28744 Ensure All Child Assets in Conflict In Parent Are Displayed in Data Exchange Location Conflicts Dialog | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:41 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28946 | ICPIM-28744 Ensure Data Exchange Location Conflicts Dialog Opens to Parent View of Selected Asset | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:40 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28945 | ICPIM-28744 Ensure Data Exchange Location Conflicts Dialog Opens from Location Conflicts Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:40 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28944 | ICPIM-28744 On Unmapped Tab, Ensure an Asset Can Be Mapped By Dragging and Dropping Asset From Root Navigator | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 10:37 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28943 | ICPIM-28744 Ensure Clear Button Works on Not Monitored Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:34 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28942 | ICPIM-28744 Ensure Clear Button Works on Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28941 | ICPIM-28744 Ensure Clear Button Works on Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28940 | ICPIM-28744 Ensure Clear Button Works on SKU Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28939 | ICPIM-28744 Ensure Enforce Location Button Works on Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:33 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28938 | ICPIM-28744 Ensure Bypass Location Button Works on Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:32 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28937 | ICPIM-28744 Ensure Enforce SKU Button Works on Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:32 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28936 | ICPIM-28744 Ensure Bypass SKU Button Works on SKU Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:32 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28935 | ICPIM-28744 Ensure Create SKU Button Works on SKU Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:31 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28934 | ICPIM-28927 User Management - Display (Main Window Appearance's Setting) | All |  | An Vo | An Vo | Windows Client | Fail | 2014-10-28 10:30 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-29170
Test Case | ICPIM-28933 | ICPIM-28744 Ensure Create SKU Button Works on Unmapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 10:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28932 | ICPIM-28927 User Management - Display (Layout) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:29 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-28931 | ICPIM-28927 User Management - Display (Status Bar) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:28 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28930 | ICPIM-28927 User Management - Display (Ancestry Bar) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:27 | 1500 | 600 | 900 | 40% | 1500 | 600 | 900 | 40%
Test Case | ICPIM-28929 | ICPIM-28927 User Management - Display (Buttons) | All |  | An Vo | An Vo | Windows Client | Fail | 2014-10-28 10:25 | 2100 | 2100 | 0 | 100% | 2100 | 2100 | 0 | 100% |  | ICPIM-29290
Test Case | ICPIM-28928 | ICPIM-28927 User Management - Display (Menu) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-28 10:24 | 1500 | 1800 | 0 | 100% | 1500 | 1800 | 0 | 100%
Test Case | ICPIM-28925 | ICPIM-28922 Updating the user information in "Unified" or "Domain" login method | All |  | Tien Pham | Tien Pham | Windows Client | Fail | 2014-10-28 10:15 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-29293
Test Case | ICPIM-28924 | ICPIM-28922 Update the user information without saving | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:11 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28923 | ICPIM-28922 Update the user information | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-28 10:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28921 | ICPIM-28744 Ensure Delete Button Works From Not Monitored Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:31 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28920 | ICPIM-28744 Ensure Delete Button Works From Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28919 | ICPIM-28744 Ensure Delete Button Works From Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28918 | ICPIM-28744 Ensure Delete Button Works From SKU Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28917 | ICPIM-28744 Ensure Delete Button Works From Unmapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:30 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28916 | ICPIM-28744 Ensure Search Button Works From Not Monitored Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:29 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28915 | ICPIM-28744 Ensure Search Button Works From Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:29 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28914 | ICPIM-28744 Ensure Search Button Works From Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:29 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28913 | ICPIM-28744 Ensure Search Button Works From Unmapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:29 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28912 | ICPIM-28744 Ensure Enable Monitoring Button Works From Not Monitored Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:25 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28911 | ICPIM-28744 Ensure Disable Monitoring Button Works From Mapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:25 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28910 | ICPIM-28744 Ensure Disable Monitoring Button Works From Location Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:25 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28909 | ICPIM-28744 Ensure Disable Monitoring Button Works From SKU Conflict Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:25 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28908 | ICPIM-28744 Ensure Disable Monitoring Button Works From Unmapped Tab | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-28 09:24 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28907 | ICPIM-28744 Ensure Attribute To Datastore Mappings Can Be Deleted/Removed | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 09:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28906 | ICPIM-28744 Ensure Attributes Can be Assigned to Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 09:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28905 | ICPIM-28744 Ensure Fields and Tabs are Labeled Correctly in Attributes Tab | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 09:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28904 | ICPIM-28744 Ensure Fields And Tabs Are Labeled Correctly in Assets Tab | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 09:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28903 | ICPIM-28744 Ensure The Attributes Tab Loads Correctly | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-28 09:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28902 | ICPIM-28898 Active Sessions - Disconnect User | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 09:21 | 1500 | 2100 | 0 | 100% | 1500 | 2100 | 0 | 100% |  | ICPIM-29401
Test Case | ICPIM-28901 | ICPIM-28898 Active Sessions - Refresh Screen | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-28 09:19 | 1200 | 3180 | 0 | 100% | 1200 | 3180 | 0 | 100% |  | ICPIM-29401
Test Case | ICPIM-28900 | ICPIM-28898 Active Sessions - General | All |  | Vinh Nguyen | An Vo | Windows Client | Fail | 2014-10-28 09:18 | 1200 | 3180 | 0 | 100% | 1200 | 3180 | 0 | 100% |  | ICPIM-29401, ICPIM-39513, ICPIM-39189
Test Case | ICPIM-28897 | ICPIM-28896 The "View" option of the log views | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-27 18:53 | 1200 | 1020 | 180 | 85% | 1200 | 1020 | 180 | 85%
Test Case | ICPIM-28895 | ICPIM-28890 Schema - Associate Classes - Rules (Connection) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 18:44 | 1800 | 840 | 960 | 46% | 1800 | 840 | 960 | 46%
Test Case | ICPIM-28894 | ICPIM-28890 Schema - Associate Classes - Rules - Creation (Descendant) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 18:42 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-28893 | ICPIM-28890 Schema - Associate Classes - Rules - Creation (Ancestor) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 18:41 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28892 | ICPIM-28890 Schema - Associate Classes (Groups) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 18:40 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-28891 | ICPIM-28889 Export only selected log entri(es) in "Log" dialog | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-27 18:39 | 900 | 660 | 240 | 73% | 900 | 660 | 240 | 73%
Test Case | ICPIM-28888 | ICPIM-28824 Delete Template Based Alerts | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-27 18:17 | 900 | 420 | 480 | 46% | 900 | 420 | 480 | 46%
Test Case | ICPIM-28887 | ICPIM-28824 Edit Template Based Alerts | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-27 18:16 | 1500 | 900 | 600 | 60% | 1500 | 900 | 600 | 60% |  | ICPIM-29648
Test Case | ICPIM-28885 | ICPIM-28884 Library Item Preview | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-27 17:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28883 | ICPIM-28876 Export Multiple Library Items | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-27 17:52 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-28882 | ICPIM-28876 Export a Library Item | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-27 17:50 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28881 | ICPIM-28878 Log - Right Click - Archive |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-10-27 17:45 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28879 | ICPIM-28744 Ensure Asset Reconciliation Dialog Loads Correctly | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-27 17:42 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28877 | ICPIM-28875 Export all log entries in "Log" dialog | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-27 17:37 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-28874 | ICPIM-28873 View Load Mask |  |  | An Vo | Trinh Nguyen | Windows Client | Fail | 2014-10-27 17:20 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-33149
Test Case | ICPIM-28872 | ICPIM-28868 Create Child within Library Item (From Template) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-27 17:07 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-28871 | ICPIM-28859 Alarms - Manage Alarm (Type) | All |  | Mai Nguyen | An Vo | Windows Client | Fail | 2014-10-27 16:49 | 1200 | 2520 | 0 | 100% | 1200 | 2520 | 0 | 100% |  | ICPIM-29825, ICPIM-29826, ICPIM-29822
Test Case | ICPIM-28870 | ICPIM-28859 Alarms - Manage Alarm (State) | All |  | Mai Nguyen | An Vo | Windows Client | Fail | 2014-10-27 16:47 | 1200 | 1560 | 0 | 100% | 1200 | 1560 | 0 | 100% |  | ICPIM-29824
Test Case | ICPIM-28869 | ICPIM-28859 Alarms - Manage Alarm (Severity) | All |  | Mai Nguyen | An Vo | Windows Client | Fail | 2014-10-27 16:46 | 1200 | 1560 | 0 | 100% | 1200 | 1560 | 0 | 100% |  | ICPIM-29823
Test Case | ICPIM-28867 | ICPIM-28845 Delete Equipment Based Alert |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-10-27 16:25 | 420 | 180 | 240 | 42% | 420 | 180 | 240 | 42%
Test Case | ICPIM-28866 | ICPIM-28845 Edit Equipment Based Alerts |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-10-27 16:22 | 900 | 780 | 120 | 86% | 900 | 780 | 120 | 86%
Test Case | ICPIM-28865 | ICPIM-28845 Add Equipment Based Alerts |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-10-27 16:18 | 900 | 840 | 60 | 93% | 900 | 840 | 60 | 93% |  | ICPIM-29648
Test Case | ICPIM-28864 | ICPIM-28862 Favorites - Remove Multiple Favorites | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:11 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28863 | ICPIM-28862 Favorites - Remove Favorites | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:09 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28861 | ICPIM-28860 Favorites - Jump to Favorites | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:07 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28858 | ICPIM-28855 Favorites -Adding a Description | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:02 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28857 | ICPIM-28855 Favorites - Adding Multiple favorites | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:02 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28856 | ICPIM-28855 Favorites - Add Single Favorites | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 16:02 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28854 | ICPIM-28812 Associate Classes - Datastores (Remove Datastores) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-27 15:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28853 | ICPIM-28847 Manage Favorites- Move To Top | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28852 | ICPIM-28847 Manage Favorites- Move To Bottom | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28851 | ICPIM-28847 Manage Favorites – Move UP | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28850 | ICPIM-28847 Manage Favorites- Move Down | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:55 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28849 | ICPIM-28847 Manage Favorites- Display name | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28848 | ICPIM-28847 Manage Favorites – Launch Dialog | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-27 15:54 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28846 | ICPIM-28845 Equipment Based Alerts – Default values |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-10-27 15:27 | 900 | 420 | 480 | 46% | 900 | 420 | 480 | 46% |  | ICPIM-29647
Test Case | ICPIM-28840 | ICPIM-28839 3D Viewer - Viewstates |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Fail | 2014-10-27 13:57 |  | 1560 | 0 | 100% |  | 1560 | 0 | 100% |  | ICPIM-29615, ICPIM-29616
Test Case | ICPIM-28838 | ICPIM-28824 Create Template Based Alerts | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-27 13:45 | 1200 | 480 | 720 | 40% | 1200 | 480 | 720 | 40%
Test Case | ICPIM-28837 | ICPIM-28836 Schema - Remove Class Group | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:39 | 1200 | 720 | 480 | 60% | 1200 | 720 | 480 | 60%
Test Case | ICPIM-28835 | ICPIM-28831 Schema - Configure Class Group (Template) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:36 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28834 | ICPIM-28831 Schema - Configure Class Group (Collection) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:35 | 1500 | 840 | 660 | 56% | 1500 | 840 | 660 | 56%
Test Case | ICPIM-28833 | ICPIM-28831 Schema - Configure Class Group (Identification) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:33 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-28832 | ICPIM-28831 Schema - Configure Class Group (Creation) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:30 | 1200 | 840 | 360 | 70% | 1200 | 840 | 360 | 70%
Test Case | ICPIM-28830 | ICPIM-28829 Schema - Add Class Group | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-27 13:26 | 1200 | 960 | 240 | 80% | 1200 | 960 | 240 | 80%
Test Case | ICPIM-28828 | ICPIM-26018 Ensure Data Points Set to "Polled" Display This Status In Data Source Mapping | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-27 11:59 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28825 | ICPIM-28824 Overview of the "Template Based Alerts" sub-tab | All |  | Vinh Nguyen | Tien Pham | Windows Client | Fail | 2014-10-24 16:54 | 1200 | 420 | 780 | 35% | 1200 | 420 | 780 | 35% |  | ICPIM-29647
Test Case | ICPIM-28823 | ICPIM-28812 Associate Classes - Datastores (Create Historical Datastore Using Configure Schema) | All |  | Trinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 16:11 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-29159
Test Case | ICPIM-28822 | ICPIM-28812 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Image") | All |  | Mai Nguyen | An Vo | Windows Client | Fail | 2014-10-24 16:09 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-29407, ICPIM-29449
Test Case | ICPIM-28821 | ICPIM-28812 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Memo") | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-24 16:07 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28820 | ICPIM-28812 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Date") | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-24 16:05 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28819 | ICPIM-28812 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Long") | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-24 16:04 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28818 | ICPIM-28812 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Double") | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-24 16:02 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28817 | ICPIM-28816 Add an alert in "Default Alerts" tab | All |  | Mai Nguyen | Tien Pham | Windows Client | Pass | 2014-10-24 15:52 | 2400 | 1380 | 1020 | 57% | 2400 | 1380 | 1020 | 57%
Test Case | ICPIM-28815 | ICPIM-28813 Export Dictionary |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-10-24 15:26 | 1200 | 780 | 420 | 65% | 1200 | 780 | 420 | 65%
Test Case | ICPIM-28814 | ICPIM-28812 Associate Classes - Datastores (Add Datastores) | All |  | An Vo | An Vo | Windows Client | Pass | 2014-10-24 15:26 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28811 | ICPIM-28810 Schema - Classes - Import Dictionary | All |  | Vinh Nguyen | Tien Pham | Windows Client | Pass | 2014-10-24 15:22 | 1680 | 720 | 960 | 42% | 1680 | 720 | 960 | 42%
Test Case | ICPIM-28809 | ICPIM-28806 Edit Dictionary - New control |  |  | Vinh Nguyen | Trinh Nguyen | Windows Client | Pass | 2014-10-24 15:10 | 1200 | 960 | 240 | 80% | 1200 | 960 | 240 | 80%
Test Case | ICPIM-28808 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Boolean") | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 15:10 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-28807 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Attached File") | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 15:08 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28805 | ICPIM-26018 Ensure Data Points From Third Party System Can Be Enabled For Polling | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 15:08 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28804 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Manual Entry data category "Text") | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 15:06 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28803 | ICPIM-28801 Schema - Classes - Remove Dictionary (Delete this dictionary) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-24 15:05 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-28802 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Derived / Calculated Data With Storage Configurations) | All |  | Thuy Tran | An Vo | Windows Client | Pass | 2014-10-24 15:03 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-29159
Test Case | ICPIM-28800 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Derived / Calculated Data) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 15:00 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28799 | ICPIM-28786 Define Dictionary Wizard Main Functionalities |  |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-10-24 15:00 | 1500 | 1140 | 360 | 76% | 1500 | 1140 | 360 | 76%
Test Case | ICPIM-28798 | ICPIM-28786 Replace Old Dictionary Using Dialog Editor |  |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-10-24 14:57 | 1200 | 1080 | 120 | 90% | 1200 | 1080 | 120 | 90%
Test Case | ICPIM-28794 | ICPIM-28775 Basic Search - By Connections (<>) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:55 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28793 | ICPIM-28786 Create Dictionary Using “Dialog Editor” |  |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-10-24 14:54 | 900 | 720 | 180 | 80% | 900 | 720 | 180 | 80%
Test Case | ICPIM-28792 | ICPIM-28775 Basic Search - By Connections (>=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28791 | ICPIM-28786 Replace Old Dictionary With Define Dictionary Wizard |  |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-10-24 14:50 | 1800 | 1380 | 420 | 76% | 1800 | 1380 | 420 | 76%
Test Case | ICPIM-28790 | ICPIM-28786 Create Dictionary With Define Dictionary Wizard |  |  | An Vo | Trinh Nguyen | Windows Client | Pass | 2014-10-24 14:44 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28789 | ICPIM-28782 User Management - Configure User - Access (leave without Applying) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-24 14:43 | 1620 | 900 | 720 | 55% | 1620 | 900 | 720 | 55%
Test Case | ICPIM-28788 | ICPIM-28782 User Management - Configure User - Access (Add, Remove for administrator user) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-24 14:41 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-28787 | ICPIM-28782 User Management - Configure User - Access (Add, Remove for non-administrator user) | All |  | Tien Pham | Tien Pham | Windows Client | Pass | 2014-10-24 14:37 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28785 | ICPIM-28758 Associate Classes - Datastores (Create Datastores Based On Collected Data) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 14:35 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28784 | ICPIM-28775 Basic Search - By Connections (<=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:31 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28783 | ICPIM-28758 Associate Classes - Datastores (Export Datastores) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 14:31 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28781 | ICPIM-28775 Basic Search - By Connections (>) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28780 | ICPIM-28758 Associate Classes - Datastores (Import Datastores) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 14:29 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-28779 | ICPIM-28758 Associate Classes - Datastores (Moving A Datastore) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 14:21 | 1500 |  | 1500 | 0% | 1500 |  | 1500 | 0%
Test Case | ICPIM-28778 | ICPIM-28758 Associate Classes - Datastores (Add, Remove Datastores) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 14:18 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-28777 | ICPIM-28775 Basic Search - By Connections (<) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28776 | ICPIM-28775 Basic Search - By Connections (=) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 14:07 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28774 | ICPIM-26018 Ensure Agent Can Be Deleted | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:28 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28773 | ICPIM-26018 Ensure Agent Instance Can Be Deleted | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:28 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28772 | ICPIM-26018 Ensure Report Button Functions | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:28 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-35454
Test Case | ICPIM-28771 | ICPIM-26018 Ensure Discover Button Functions | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Invalid | 2014-10-24 13:28 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-34230
Test Case | ICPIM-28770 | ICPIM-26018 Ensure Asset Reconciliation Dialog Can Be Opened For Agent Instance | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:28 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28769 | ICPIM-26018 Ensure Agent Instance Configuration Can Be Edited | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28768 | ICPIM-28758 Associate Classes - General (Find Class) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 13:18 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-28767 | ICPIM-28758 Associate Classes - General (Sub-Classes) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 13:14 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28766 | ICPIM-26018 Ensure an Agent Instance Can be Configured | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 13:14 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28765 | ICPIM-28758 Associate Classes - General (Clear And Set Icon For New Class) | All |  | Mai Nguyen | An Vo | Windows Client | Fail | 2014-10-24 13:12 | 1200 | 3000 | 1800 | 62% | 1200 | 3000 | 1800 | 62% |  | ICPIM-29246, ICPIM-34976, ICPIM-34979, ICPIM-34985, ICPIM-34988
Test Case | ICPIM-28764 | ICPIM-28758 Associate Classes - General (Set New Class As Root Item) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 13:07 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28763 | ICPIM-28758 Associate Classes - General (Add, Remove Classes) | All |  | Vinh Nguyen | An Vo | Windows Client | Pass | 2014-10-24 12:58 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100%
Test Case | ICPIM-28762 | ICPIM-28761 Basic Search - By Sub Class | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 12:57 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28760 | ICPIM-28753 Trace- Textual Trace | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-24 12:25 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-28759 | ICPIM-26018 Ensure Configured Agents Appear in the Agent Pane | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-10-24 12:01 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28757 | ICPIM-28753 Trace- Textual Trace- Text/HTML | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-24 11:42 | 900 | 1200 | 0 | 100% | 900 | 1200 | 0 | 100%
Test Case | ICPIM-28756 | ICPIM-28753 Trace- Textual Trace-Refresh | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-24 11:42 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28755 | ICPIM-28753 Trace- Textual Trace- Number of Ancestors | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-24 11:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28754 | ICPIM-28753 Trace- Textual Trace- Launch dialog | All |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2014-10-24 11:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100% |  | ICPIM-32842
Test Case | ICPIM-28752 | ICPIM-28750 Basic Search - By Class (Inherit) | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 11:11 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28751 | ICPIM-28750 Basic Search - By Class | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 11:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28749 | ICPIM-28720 Navigation- Tool Bar - VM Manager | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28748 | ICPIM-28720 Navigation- Tool Bar- Commission | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28747 | ICPIM-28720 Navigation- Tool Bar- Planner | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:44 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-28746 | ICPIM-28720 Navigation- Tool Bar- Audit | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28745 | ICPIM-28720 Navigation- Tool Bar- Help | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28743 | ICPIM-28720 Navigation- Tool Bar -Refresh | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28742 | ICPIM-28720 Navigation- Tool Bar- Reports | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:43 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28741 | ICPIM-28720 Navigation- Tool Bar- Search | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:42 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28740 | ICPIM-28720 Navigation- Tool Bar - Asset Log | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:42 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28739 | ICPIM-28720 Navigation- Tool Bar- Library | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:42 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28738 | ICPIM-28720 Navigation- Tool Bar- Templates | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:42 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28737 | ICPIM-28720 Navigation- Tool Bar- Dashboard | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:41 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28736 | ICPIM-28720 Navigation- Tool Bar- Viewer | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:41 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28735 | ICPIM-28720 Navigation- Tool Bar- Log | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:41 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28734 | ICPIM-28720 Navigation- Tool Bar- Favorites | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:40 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28733 | ICPIM-28720 Navigation- Tool Bar- Browse | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:40 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28732 | ICPIM-28720 Navigation- Tool Bar- Trace | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:40 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28731 | ICPIM-28720 Navigation- Tool Bar- Dictionary | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:40 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28730 | ICPIM-28720 Navigation- Tool Bar- Properties | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28729 | ICPIM-28702 Import Library Item (Multiple Items) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 09:39 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28728 | ICPIM-28720 Navigation- Tool Bar- Disconnect | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28727 | ICPIM-28720 Navigation- Tool Bar- Connect | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28726 | ICPIM-28720 Navigation- Tool Bar- Delete | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28725 | ICPIM-28702 Import Library Item (Single Item) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-24 09:39 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28724 | ICPIM-28720 Navigation- Tool Bar- Create | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:39 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28723 | ICPIM-28720 Navigation- Tool Bar- Root | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:38 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28721 | ICPIM-28720 Navigation- Tool Bar- My Settings | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:23 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28719 | ICPIM-28718 Navigation-Browser | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-24 09:17 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28701 | ICPIM-28619 Remove SNMP Access | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-23 15:17 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28700 | ICPIM-28618 Configure SNMP Access - V3 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-23 15:16 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28699 | ICPIM-28618 Configure SNMP Access - V2 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-23 15:16 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28698 | ICPIM-28618 Configure SNMP Access - V1 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-23 15:16 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28692 | ICPIM-28689 Remove multiple Library Items | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 13:17 | 1200 | 3000 | 0 | 100% | 1200 | 3000 | 0 | 100% |  | ICPIM-30284
Test Case | ICPIM-28691 | ICPIM-28689 Remove a Library Item | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 13:16 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100% |  | ICPIM-30284
Test Case | ICPIM-28688 | ICPIM-28686 Library Item Catalog - Edit - Create: Template Preview | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 11:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28687 | ICPIM-28686 Library Item Catalog - Manage - Create: Template Preview | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 11:44 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28676 | ICPIM-28657 Rename Libary Item in Properties panel | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 10:43 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28675 | ICPIM-28657 Rename Library Item in Edit Navigator with single click | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-23 10:41 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28658 | ICPIM-28657 Rename Library Item in Edit Navigator (F2) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 16:48 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28656 | ICPIM-28650 Navigation- Context menu - Ancestry bar | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 16:09 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-28655 | ICPIM-28650 Navigation- Context menu - Viewer | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 16:06 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28654 | ICPIM-28650 Navigation- Context menu- Dashboard | All |  | Tien Pham | Rachna Muthanna | Windows Client | Pass | 2014-10-22 16:04 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28653 | ICPIM-28650 Navigation- Context menu - Trace | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 16:00 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28652 | ICPIM-28650 Navigation- Context menu - Browser | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 15:59 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-28651 | ICPIM-28650 Navigation- Context menu - Navigator | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 15:52 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-28649 | ICPIM-28648 Navigation- Data Tool tip | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-22 15:44 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28644 | ICPIM-28643 Navigation- Menu Bar | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 15:19 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28642 | ICPIM-28641 Navigation- Navigate To | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 14:59 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28640 | ICPIM-28639 Navigation- Navigator | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 14:49 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28638 | ICPIM-28612 Connectivity Commissioning Configuration - Route to Rack | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 14:48 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28637 | ICPIM-28612 Connectivity Commissioning Configuration - Route to Row | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 14:47 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28636 | ICPIM-28612 Connectivity Commissioning Configuration - Connectors | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 14:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28635 | ICPIM-28612 Connectivity Commissioning Configuration - Route to DC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 14:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28634 | ICPIM-28612 Connectivity Commissioning Configuration - Service Type | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-10-22 14:44 | 900 | 2700 | 0 | 100% | 900 | 2700 | 0 | 100% |  | ICPIM-30433, ICPIM-30436, ICPIM-32834
Test Case | ICPIM-28633 | ICPIM-28612 Connectivity Commissioning Configuration - Service | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 14:40 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28632 | ICPIM-28617 Add SNMP Access - V3 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 14:39 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28631 | ICPIM-28617 Add SNMP Access - V2 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 14:39 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28630 | ICPIM-28617 Add SNMP Access - V1 | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 14:38 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28629 | ICPIM-28628 Navigation- Root Navigator | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 14:01 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28627 | ICPIM-28624 Navigation- Status Bar- JobQueue | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 13:40 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28626 | ICPIM-28624 Navigation- Status Bar- Interface | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 13:37 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-28625 | ICPIM-28624 Navigation- Status Bar- Dialogs & Menus | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-22 13:30 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28623 | ICPIM-28616 Remove SNMP Trap Forward | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 12:46 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28622 | ICPIM-28615 Remove SNMP Trap | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 12:46
Test Case | ICPIM-28621 | ICPIM-28613 Configure SNMP Trap | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 12:45 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28620 | ICPIM-28614 Configure Trap Forward | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-22 12:45 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28610 | ICPIM-28605 Power Commissioning Configuration - PDU Breaker, Balance Phase | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 11:32 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28609 | ICPIM-28605 Power Commissioning Configuration - Junction Box, Template | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 11:30 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28608 | ICPIM-28605 Power Commissioning Configuration - Source Filter | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 11:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28607 | ICPIM-28605 Power Commissioning Configuration - Source Type | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 11:29 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28606 | ICPIM-28605 Power Commissioning Configuration - Power Source | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-22 11:28 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-28604 | ICPIM-28603 Connectivity - Drag and Drop Source and Destination Objects | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 18:49 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28602 | ICPIM-28596 Connectivity - Connect Tab - Create link | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 18:41 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28601 | ICPIM-28596 Connectivity - Connect Tab - Existing link | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 18:25 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28600 | ICPIM-28599 Connectivity - Creating a virtual Connection | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 18:18 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28598 | ICPIM-28596 Connectivity - Connect Tab - Virtual Links | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 18:15 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28597 | ICPIM-28596 Connectivity - Connect Tab | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:58 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-28595 | ICPIM-28590 Connectivity - Schedule Tab - Cost | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:28 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-28594 | ICPIM-28590 Connectivity - Schedule Tab - Specify Order | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:27 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-28593 | ICPIM-28590 Connectivity - Schedule Tab - Specify Request | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:26 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-28592 | ICPIM-28590 Connectivity - Schedule Tab - Specify Project | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:24 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-28591 | ICPIM-28590 Connectivity - Schedule Tab | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 17:06 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28589 | ICPIM-28581 Rotate a Created Child Library Item | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 16:46 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28588 | ICPIM-28587 Connectivity - Drop Zone | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 16:43 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28586 | ICPIM-28581 Create Child within Library Item (From Library Item) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 16:33 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-30281
Test Case | ICPIM-28585 | ICPIM-28582 Launch Connect dialog - From the menu | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 16:21 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-28584 | ICPIM-28582 Launch Connect dialog - From a navigator | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 16:20 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-28583 | ICPIM-28582 Launch Connect dialog - From the Ancestry bar | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 16:20 | 900 | 540 | 360 | 60% | 900 | 540 | 360 | 60%
Test Case | ICPIM-28580 | ICPIM-28578 Rotate a Created Library Item | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 15:13 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28579 | ICPIM-28578 Create Library Item (From Template) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 14:56 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28577 | ICPIM-28570 Row Pad Editor dialog –POSITION – Position Number | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 13:17 | 900 | 1500 | 0 | 100% | 900 | 1500 | 0 | 100%
Test Case | ICPIM-28576 | ICPIM-28570 Row Pad Editor dialog –POSITION – Realign Enclosures | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 13:09 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28575 | ICPIM-28570 Row Pad Editor dialog –POSITION – Set Enclosure | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 13:08 | 600 | 1500 | 0 | 100% | 600 | 1500 | 0 | 100%
Test Case | ICPIM-28574 | ICPIM-28568 Search for Library Item Catalog (Name) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 13:07 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28573 | ICPIM-28570 Row Pad Editor dialog –POSITION – Reverse Pads | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 13:01 | 600 | 900 | 0 | 100% | 600 | 900 | 0 | 100%
Test Case | ICPIM-28572 | ICPIM-28570 Row Pad Editor dialog –POSITION – Spacing | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 13:00 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28571 | ICPIM-28570 Row Pad Editor dialog –POSITION –Align to Row | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 12:58 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28569 | ICPIM-28568 Search for Library Item Catalog (Class, Manufacturer, Template) | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-21 12:27 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-28567 | ICPIM-28563 Row Pad Editor – Creation – From library | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 11:11 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28566 | ICPIM-28563 Row Pad Editor – Creation – Create Library Items | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-21 11:03 | 900 | 1800 | 0 | 100% | 900 | 1800 | 0 | 100%
Test Case | ICPIM-28565 | ICPIM-28563 Row Pad Editor – Creation –Build pads | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 10:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28564 | ICPIM-28563 Row Pad Editor – Creation – Clone pads | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-21 09:19 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-28558 | ICPIM-28557 Adding a SNMP Trap Forward | All |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-20 16:26 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28554 | ICPIM-28548 Delete a Threshold | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-20 16:08 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-28552 | ICPIM-28550 Row Pad Editor –Navigator | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 16:05 | 600 | 1200 | 0 | 100% | 600 | 1200 | 0 | 100%
Test Case | ICPIM-28551 | ICPIM-28548 Add a new Threshold | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-20 16:04 | 2700 | 540 | 2160 | 20% | 2700 | 540 | 2160 | 20%
Test Case | ICPIM-28549 | ICPIM-28548 Class Based Alerts Defaults | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-10-20 15:58 | 1800 | 480 | 1320 | 26% | 1800 | 480 | 1320 | 26% |  | ICPIM-29647
Test Case | ICPIM-28542 | ICPIM-28541 Create Report from Browser | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-20 13:36 | 1800 | 1140 | 660 | 63% | 1800 | 1140 | 660 | 63%
Test Case | ICPIM-28540 | ICPIM-28476 Navigation- Ancestry Bar- Standard Context menu | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-20 13:22 | 300 | 600 | 0 | 100% | 300 | 600 | 0 | 100%
Test Case | ICPIM-28536 | ICPIM-28476 Navigation- Ancestry Bar- Drag and Drop | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-20 13:17 | 300 | 600 | 0 | 100% | 300 | 600 | 0 | 100%
Test Case | ICPIM-28530 | ICPIM-28516 Save and Assign Window Layout | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-20 13:06 | 3600 | 4020 | 0 | 100% | 3600 | 4020 | 0 | 100% |  | ICPIM-29614
Test Case | ICPIM-28522 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Connectivity | All |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2014-10-20 11:55 | 60 | 1200 | 0 | 100% | 60 | 1200 | 0 | 100% |  | ICPIM-30806
Test Case | ICPIM-28521 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Panels | All |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2014-10-20 11:41 | 60 | 1200 | 0 | 100% | 60 | 1200 | 0 | 100% |  | ICPIM-33013
Test Case | ICPIM-28520 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Cooling | All |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2014-10-20 11:38 | 60 | 600 | 0 | 100% | 60 | 600 | 0 | 100% |  | ICPIM-32991
Test Case | ICPIM-28519 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Power | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:36 | 60 | 300 | 0 | 100% | 60 | 300 | 0 | 100%
Test Case | ICPIM-28518 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Pads | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:33 | 60 | 300 | 0 | 100% | 60 | 300 | 0 | 100%
Test Case | ICPIM-28517 | ICPIM-28510 Row Pad Editor –Display Tab – Show -Enclosures | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:26 | 60 | 300 | 0 | 100% | 60 | 300 | 0 | 100%
Test Case | ICPIM-28515 | ICPIM-28510 Row Pad Editor –Display Tab – Show - Tile Grid | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:12 | 60 | 300 | 0 | 100% | 60 | 300 | 0 | 100%
Test Case | ICPIM-28514 | ICPIM-28510 Row Pad Editor –Display Tab – Row | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:02 | 60 | 900 | 0 | 100% | 60 | 900 | 0 | 100%
Test Case | ICPIM-28513 | ICPIM-28510 Row Pad Editor –Display Tab – Datacenter | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 11:00 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-28512 | ICPIM-28510 Row Pad Editor –Display Tab – Site | All |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2014-10-20 10:57 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-28511 | ICPIM-28509 Change the user | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-10-20 10:55 | 1800 | 960 | 840 | 53% | 1800 | 960 | 840 | 53%
Test Case | ICPIM-28508 | ICPIM-28506 Adding a SNMP Trap |  |  | Garrett S. | Garrett S. | Data Exchange Agent | New | 2014-10-20 10:26 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-28505 | ICPIM-28308 Asset Space - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:08
Test Case | ICPIM-28504 | ICPIM-28307 Schema - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:07
Test Case | ICPIM-28503 | ICPIM-28306 Asset Power - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:07
Test Case | ICPIM-28502 | ICPIM-28305 Asset Network - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:07
Test Case | ICPIM-28501 | ICPIM-28304 Data Stores - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:07
Test Case | ICPIM-28500 | ICPIM-28303 Asset Data - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:07
Test Case | ICPIM-28499 | ICPIM-28302 Asset Cooling - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:06
Test Case | ICPIM-28496 | ICPIM-28317 Asset Inventory - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:05
Test Case | ICPIM-28495 | ICPIM-28316 Asset Hierarchy - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:05
Test Case | ICPIM-28494 | ICPIM-28301 Assets - Data Accuracy *INCOMPLETE* | All |  | Garrett S. | Garrett S. | Application Layer | Invalid | 2014-10-20 09:04
Test Case | ICPIM-28477 | ICPIM-28476 Navigation- Ancestry Bar- Display hierarchy | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-10-17 15:42 | 300 | 300 | 0 | 100% | 300 | 300 | 0 | 100%
Test Case | ICPIM-28475 | ICPIM-28473 Change User Password | All |  | Vinh Nguyen | Loan Ha | Windows Client | Fail | 2014-10-17 15:32 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-29605, ICPIM-29608, ICPIM-29611
Test Case | ICPIM-28468 | ICPIM-28309 Thermals (Cooling) | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-17 08:45 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28467 | ICPIM-28309 Space | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-17 08:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28466 | ICPIM-28309 Properties | All |  | Thuy Tran | Garrett S. | Application Layer | Pass | 2014-10-17 08:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28465 | ICPIM-28309 Power | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-17 08:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28464 | ICPIM-28309 Network | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-17 08:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28455 | ICPIM-28454 3D Viewer - Adding Tile Grid | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-16 15:53 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28446 | ICPIM-28445 Template Manager - Importing a Template package | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-16 10:12 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-33635
Test Case | ICPIM-28437 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator Reporting | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 10:17 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28436 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator - Policies (Analyzer Card USB - SPP, Mapping) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 10:15 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28435 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator - Policies (HMI) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 10:13 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28434 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator - Policies (Chassis group) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 10:10 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28433 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator (Patch Zone Generation) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 10:05 | 5400 |  | 5400 | 0% | 5400 |  | 5400 | 0%
Test Case | ICPIM-28432 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator (Generate By Device) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 09:53 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28431 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator (Generate By Enclosure) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 09:38 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28430 | ICPIM-28423 DEA - Connectivity - NGA AutoGenerator (Generate By Equipment Room) | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 09:34 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-28429 | ICPIM-28443 DEA - Connectivity - Analyzer Multi map | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-10-15 09:24 | 5400 |  | 5400 | 0% | 5400 |  | 5400 | 0%
Test Case | ICPIM-28426 | ICPIM-28309 Compute | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-14 15:58 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28425 | ICPIM-28309 Ensure Service is Accessible | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-10-14 15:58 | 300 | 180 | 120 | 60% | 300 | 180 | 120 | 60%
Test Case | ICPIM-28424 | ICPIM-28441 DEA - Connectivity - Analyzer Mapping | All |  | Loan Ha | Loan Ha | Data Exchange Agent | Invalid | 2014-10-14 15:38 | 5400 |  | 5400 | 0% | 5400 |  | 5400 | 0%
Test Case | ICPIM-28422 | ICPIM-28421 TC File-Advanced-Asset Management-Map | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2014-10-14 15:09 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-33757, ICPIM-33763
Test Case | ICPIM-28395 | ICPIM-28364 ExportAssetChangeManagement | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28394 | ICPIM-28364 ExportAssetCooling | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28393 | ICPIM-28364 ExportAssetNetwork | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28392 | ICPIM-28364 ExportAssetSpace | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28391 | ICPIM-28364 ExportAssetPowerConnectivity | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28390 | ICPIM-28364 ExportAssetPower | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28389 | ICPIM-28364 ExportAssetData | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28388 | ICPIM-28364 ExportDataStores | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:45 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0% |  | ICPIM-38451
Test Case | ICPIM-28387 | ICPIM-28364 ExportAssetInventory | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:44 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28386 | ICPIM-28364 ExportAssetHierarchy | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:44 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28385 | ICPIM-28364 ExportAssets | All |  | Garrett S. | Garrett S. | Analytics | Pass | 2014-10-13 15:44 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-28384 | ICPIM-27030 Run As Job - Hierarchy | All |  | Thuy Tran | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28383 | ICPIM-27030 Run As Job - Inventory | All |  | Thuy Tran | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28382 | ICPIM-27030 Run As Job - Schema | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28381 | ICPIM-27030 Run As Job - Data | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28380 | ICPIM-27030 Run As Job - Cooling | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28379 | ICPIM-27030 Run As Job - Network | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28378 | ICPIM-27030 Run As Job - Power | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28377 | ICPIM-27030 Run As Job - Space | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28376 | ICPIM-27030 Run As Job - Data Stores | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-38451
Test Case | ICPIM-28375 | ICPIM-27030 Run As Job - Assets | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:30 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28374 | ICPIM-27030 Run Now - Hierarchy | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28373 | ICPIM-27030 Run Now - Inventory | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28372 | ICPIM-27030 Run Now - Schema | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16%
Test Case | ICPIM-28371 | ICPIM-27030 Run Now - Data | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16%
Test Case | ICPIM-28370 | ICPIM-27030 Run Now - Cooling | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 300 | 1500 | 16% | 1800 | 300 | 1500 | 16%
Test Case | ICPIM-28369 | ICPIM-27030 Run Now - Network | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28368 | ICPIM-27030 Run Now - Power | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-28367 | ICPIM-27030 Run Now - Space | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100%
Test Case | ICPIM-28366 | ICPIM-27030 Run Now - Data Stores | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83% |  | ICPIM-38451
Test Case | ICPIM-28365 | ICPIM-27030 Run Now - Assets | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-10-13 15:29 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83%
Test Case | ICPIM-28363 | ICPIM-28362 Template Manager - Automated package Import | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-13 14:28 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-33662, ICPIM-35698
Test Case | ICPIM-28344 | ICPIM-28343 Template Manager - Search For Templates In Packages | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-10 14:39 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28315 | ICPIM-28293 Creating a CAD Object Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-09 15:06 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-33305, ICPIM-34991
Test Case | ICPIM-28314 | ICPIM-28293 Creating a 3D Object Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-09 15:05 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-33282
Test Case | ICPIM-28313 | ICPIM-28293 Creating a Tile Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-09 15:05 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32873
Test Case | ICPIM-28312 | ICPIM-28293 Creating a Plugin Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-09 15:05 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32873
Test Case | ICPIM-28311 | ICPIM-28293 Adding an Enclosure Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-10-09 15:04 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-32784, ICPIM-32930, ICPIM-33170
Test Case | ICPIM-28310 | ICPIM-28293 Adding a Connector Template | All |  | Vinh Nguyen | Rachna Muthanna | Windows Client | Pass | 2014-10-09 15:01 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-28128 | ICPIM-28127 Ensure OperationalDataWS is Used by this DEA | All |  | Garrett S. | Garrett S. |  | Pass | 2014-10-03 14:52 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28109 | ICPIM-27920 Error Logging | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-02 15:26
Test Case | ICPIM-28108 | ICPIM-27920 Remove Assets - Non Unique Parent and Child Specified | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-02 15:21
Test Case | ICPIM-28107 | ICPIM-27920 Remove Assets - Parent Asset Specified for Non Unique Assets | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-02 15:10
Test Case | ICPIM-28095 | ICPIM-27920 Remove Assets - Do Not Remove Library Items | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-01 16:34
Test Case | ICPIM-28094 | ICPIM-27920 Data Connections | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-10-01 16:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-28093 | ICPIM-28030 Quick Menu | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 15:06 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-28092 | ICPIM-28030 Datastore - General - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 15:06 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28091 | ICPIM-28030 Datastore - General - URL | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 15:05 |  | 840 | 0 | 100% |  | 840 | 0 | 100% |  | ICPIM-30747
Test Case | ICPIM-28090 | ICPIM-28030 Datastore (Default, Chart) | All |  | An Vo | Todd Brewer |  | Pass | 2014-10-01 15:04 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-28089 | ICPIM-28030 Datastore - General - Link as Host | All |  | An Vo | Todd Brewer |  | Pass | 2014-10-01 15:04 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100%
Test Case | ICPIM-28088 | ICPIM-28030 Datastore - General | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 15:03 |  | 960 | 0 | 100% |  | 960 | 0 | 100%
Test Case | ICPIM-28087 | ICPIM-28030 Datastore - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 15:02 |  | 720 | 0 | 100% |  | 720 | 0 | 100%
Test Case | ICPIM-28086 | ICPIM-28030 Datastore - Font | All |  | An Vo | Todd Brewer |  | Pass | 2014-10-01 15:02 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-30940
Test Case | ICPIM-28085 | ICPIM-28030 Datastore - Fill | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 15:01 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28084 | ICPIM-28030 Datastore - Historical - Start/End Date | All |  | Mai Nguyen | Todd Brewer |  | Blocker | 2014-10-01 15:01 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34119
Test Case | ICPIM-28083 | ICPIM-28030 Datastore - Chart Format (Legend Options) | All |  | An Vo | Todd Brewer | Windows Client | Pass | 2014-10-01 15:00 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28082 | ICPIM-28030 Datastore - Historical - Show Name | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 14:59 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-30938
Test Case | ICPIM-28081 | ICPIM-28030 Datastore - Chart - Historical | All |  | An Vo | Todd Brewer | Windows Client | Blocker | 2014-10-01 14:59 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-34119
Test Case | ICPIM-28080 | ICPIM-28030 Datastore - Default - Historical | All |  | An Vo | Todd Brewer | Windows Client | Blocker | 2014-10-01 14:58 | 1200 | 1800 | 0 | 100% | 1200 | 1800 | 0 | 100% |  | ICPIM-34119
Test Case | ICPIM-28079 | ICPIM-28030 Datastore - Chart Format (Title Options) | All |  | An Vo | Todd Brewer | Windows Client | Pass | 2014-10-01 14:57 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-28078 | ICPIM-28030 Datastore - Start/End Date | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:56 |  | 540 | 0 | 100% |  | 540 | 0 | 100%
Test Case | ICPIM-28077 | ICPIM-28030 Datastore - Show Name | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:56 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28076 | ICPIM-28030 Datastore - Type | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:55 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-28075 | ICPIM-28030 Datastore | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:52 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28074 | ICPIM-28030 Viewer - General - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:47 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28073 | ICPIM-28030 Viewer - General - URL | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 14:46 |  | 960 | 0 | 100% |  | 960 | 0 | 100% |  | ICPIM-30747
Test Case | ICPIM-28072 | ICPIM-28030 Viewer - General - Object Alias & Rotation | All |  | Mai Nguyen | Todd Brewer | Windows Client | Fail | 2014-10-01 14:45 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34168
Test Case | ICPIM-28071 | ICPIM-28030 Viewer - General - Link As Host | All |  | Mai Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:44 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-28070 | ICPIM-28030 Viewer - General | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:43 |  | 960 | 0 | 100% |  | 960 | 0 | 100%
Test Case | ICPIM-28069 | ICPIM-28030 Viewer - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:42 |  | 540 | 0 | 100% |  | 540 | 0 | 100% |  | ICPIM-29380
Test Case | ICPIM-28068 | ICPIM-28030 Viewer - Masks | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:38 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-29379
Test Case | ICPIM-28067 | ICPIM-28030 Viewer - Viewstates | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:38 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-29378
Test Case | ICPIM-28066 | ICPIM-28030 Viewer | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:37 |  | 420 | 0 | 100% |  | 420 | 0 | 100% |  | ICPIM-29377
Test Case | ICPIM-28065 | ICPIM-28030 Properties - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:35 |  | 540 | 0 | 100% |  | 540 | 0 | 100% |  | ICPIM-29376
Test Case | ICPIM-28064 | ICPIM-28030 Properties - URL | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 14:33 |  | 840 | 0 | 100% |  | 840 | 0 | 100% |  | ICPIM-30747, ICPIM-29375
Test Case | ICPIM-28063 | ICPIM-28030 Properties - Rotation | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 14:21 |  | 540 | 0 | 100% |  | 540 | 0 | 100% |  | ICPIM-29373
Test Case | ICPIM-28062 | ICPIM-28030 Properties - Object Alias | All |  | Mai Nguyen | Todd Brewer | Windows Client | Fail | 2014-10-01 13:53 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34168
Test Case | ICPIM-28061 | ICPIM-28030 Properties - Link As Host | All |  | Mai Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:52 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-28060 | ICPIM-28030 Properties - Anchor | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:51 |  | 660 | 0 | 100% |  | 660 | 0 | 100%
Test Case | ICPIM-28059 | ICPIM-28030 Properties - Allow Navigation | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:50 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-33722
Test Case | ICPIM-28058 | ICPIM-28030 Properties - Allow Connections | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:49 |  | 720 | 0 | 100% |  | 720 | 0 | 100%
Test Case | ICPIM-28057 | ICPIM-28030 Properties - Lock Aspect Ratio | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:48 |  | 540 | 0 | 100% |  | 540 | 0 | 100%
Test Case | ICPIM-28056 | ICPIM-28030 Properties - General | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:48 |  | 240 | 0 | 100% |  | 240 | 0 | 100%
Test Case | ICPIM-28055 | ICPIM-28030 Properties - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:47 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28054 | ICPIM-28030 Properties | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 13:46 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28053 | ICPIM-28030 Format - Trace - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:49 |  | 420 | 0 | 100% |  | 420 | 0 | 100%
Test Case | ICPIM-28052 | ICPIM-28030 Format - Trace - URL | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 12:48 |  | 840 | 0 | 100% |  | 840 | 0 | 100% |  | ICPIM-30747
Test Case | ICPIM-28051 | ICPIM-28030 Format - Trace - Object Alias & Rotation | All |  | Mai Nguyen | Todd Brewer | Windows Client | Fail | 2014-10-01 12:45 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34168
Test Case | ICPIM-28050 | ICPIM-28030 Format - Trace - Link as Host | All |  | Mai Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:44 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-28049 | ICPIM-28030 Format - Trace - General | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:43 |  | 1740 | 0 | 100% |  | 1740 | 0 | 100%
Test Case | ICPIM-28048 | ICPIM-28030 Format - Trace - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:43 |  | 660 | 0 | 100% |  | 660 | 0 | 100%
Test Case | ICPIM-28047 | ICPIM-28030 Format - Trace | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:17 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-28046 | ICPIM-28030 Format - Image - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:08 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28045 | ICPIM-28030 Format - Image - Anchor | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 12:08 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-30660
Test Case | ICPIM-28044 | ICPIM-28030 Format - Image - Aspect Ratio | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:07 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-28043 | ICPIM-28030 Format - Image - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:05 |  | 960 | 0 | 100% |  | 960 | 0 | 100%
Test Case | ICPIM-28042 | ICPIM-28030 Format - Icon - Information | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 12:04 |  | 420 | 0 | 100% |  | 420 | 0 | 100%
Test Case | ICPIM-28041 | ICPIM-28030 Format - Icon - URL | All |  | Vinh Nguyen | Todd Brewer |  | Fail | 2014-10-01 12:03 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-30747
Test Case | ICPIM-28040 | ICPIM-28030 Format - Icon - General - Rotation | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:37 |  | 480 | 0 | 100% |  | 480 | 0 | 100%
Test Case | ICPIM-28039 | ICPIM-28030 Format - Icon - General - Object Alias | All |  | Mai Nguyen | Todd Brewer | Windows Client | Fail | 2014-10-01 10:36 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34168
Test Case | ICPIM-28038 | ICPIM-28030 Format - Icon - General - Link As Host | All |  | Trinh Nguyen | Todd Brewer | Windows Client | Pass | 2014-10-01 10:35 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-28037 | ICPIM-28030 Format - Icon - General | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:34 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100% |  | ICPIM-29371
Test Case | ICPIM-28036 | ICPIM-28030 Format - Icon - Border | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:30 |  | 720 | 0 | 100% |  | 720 | 0 | 100%
Test Case | ICPIM-28035 | ICPIM-28030 Format - Icon - Fill | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:28 |  | 720 | 0 | 100% |  | 720 | 0 | 100%
Test Case | ICPIM-28034 | ICPIM-28030 Format - Icon | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:27 |  | 300 | 0 | 100% |  | 300 | 0 | 100% |  | ICPIM-29367
Test Case | ICPIM-28033 | ICPIM-28030 View Definitions | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:26 |  | 1440 | 0 | 100% |  | 1440 | 0 | 100% |  | ICPIM-29366
Test Case | ICPIM-28032 | ICPIM-28030 Options | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:26 |  | 360 | 0 | 100% |  | 360 | 0 | 100% |  | ICPIM-29365
Test Case | ICPIM-28031 | ICPIM-28030 Preconditions | All |  | Vinh Nguyen | Todd Brewer |  | Pass | 2014-10-01 10:24 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-28025 | ICPIM-28364 ExportSchema | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-09-30 16:50 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-27978 | ICPIM-27920 Ensure Modules are Imported and Placed Correctly | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-09-26 15:28 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-27977 | ICPIM-27920 Ensure Using a Class in "CreateFrom" Creates Log Entry | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-09-26 15:23 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-27955 | ICPIM-14714 Portfolio - Advanced Search: by Combination of Name, Type, Group Type and Attribute | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-09-25 19:34 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-27954 | ICPIM-14714 Portfolio - Advanced Search: by Attribute | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2014-09-25 19:30 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-27962
Test Case | ICPIM-27953 | ICPIM-14714 Portfolio - Advanced Search: by Group Type | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-09-25 19:27 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-27952 | ICPIM-14714 Portfolio - Advanced Search: by Type | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-09-25 19:21 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-27922 | ICPIM-27920 Updating Datastores: Full Update (placeholder) | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-09-24 15:09 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-24177
Test Case | ICPIM-27921 | ICPIM-27920 Updating Datastores: Partial Update (placeholder) | All |  | Garrett S. | Garrett S. |  | In Progress | 2014-09-24 15:08 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100% |  | ICPIM-24177
Test Case | ICPIM-27909 | ICPIM-39837 Change Management - Remove CR: Complete a Remove CR Schedule task | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-09-24 02:36 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-27905 | ICPIM-21844 Change Management - Repurpose CR: Complete a Repurpose CR Schedule task | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2014-09-24 01:15 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-27910, ICPIM-23506
Test Case | ICPIM-27901 | ICPIM-21827 Change Management - Move CR: Complete a Move CR Schedule task | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-09-23 21:55 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-27887 | ICPIM-24520 Ensure UI Elements Updated Per Joe's Desires | All |  | Garrett S. | Garrett S. |  | Pass | 2014-09-23 12:38 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-27852
Test Case | ICPIM-27641 | ICPIM-28308 Ensure Analytics Excludes Inactive Work Orders | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-09-11 10:01 | 3600 | 6000 | 0 | 100% | 3600 | 6000 | 0 | 100% |  | ICPIM-26224, ICPIM-27695, ICPIM-26191
Test Case | ICPIM-27640 | ICPIM-28308 Ensure ExportAssetSpace Excludes Assets Outside of Cabinets | All |  | Thuy Tran | Garrett S. | Application Layer | Fail | 2014-09-11 09:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-34465, ICPIM-26189
Test Case | ICPIM-27596 | ICPIM-27025 Reassign Items | All |  | Garrett S. | Garrett S. |  | New | 2014-09-10 17:07 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-27579 | ICPIM-27025 Application New Connection - Virtual Machine | All |  | Garrett S. | Garrett S. |  | New | 2014-09-10 15:10 | 900 | 300 | 600 | 33% | 900 | 300 | 600 | 33%
Test Case | ICPIM-27536 | ICPIM-27135 Add/Remove Database {WIP} | All |  | Todd Brewer | Todd Brewer | Windows Client | New | 2014-09-09 17:24 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-27484 | ICPIM-36605 Portfolio - Asset Attributes: Edit Datastores | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2014-09-05 14:21 | 10800 | 9000 | 1800 | 83% | 10800 | 9000 | 1800 | 83% |  | ICPIM-27129, ICPIM-27333, ICPIM-27813, ICPIM-27861, ICPIM-27580, ICPIM-35038, ICPIM-25805, ICPIM-25368
Test Case | ICPIM-27482 | ICPIM-27135 Upgrade Scenarios | All |  | Todd Brewer | Todd Brewer | Windows Client | New | 2014-09-05 14:04 | 14400 |  | 14400 | 0% | 14400 |  | 14400 | 0%
Test Case | ICPIM-27481 | ICPIM-27135 Smoke Test | All |  | Todd Brewer | Todd Brewer | Windows Client | New | 2014-09-05 13:52 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-27480 | ICPIM-27477 imVision port names updated against CPIM port | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-09-05 13:14 | 10800 | 10200 | 600 | 94% | 10800 | 10200 | 600 | 94% |  | ICPIM-27508, ICPIM-23637
Test Case | ICPIM-27478 | ICPIM-27477 imVision Configuration -TC | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-09-05 13:07 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-23637
Test Case | ICPIM-27476 | ICPIM-27475 Decommission - Power Policy: Immediate Connections | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2014-09-05 11:47 | 7200 | 3600 | 3600 | 50% | 7200 | 3600 | 3600 | 50% |  | ICPIM-25863
Test Case | ICPIM-27466 | ICPIM-38539 Task Management - Tasks: Bulk updating items | All |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-09-05 09:48 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-27436 | ICPIM-27435 Change Management - Edit Work Projects: Naming Work Projects | All |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-09-04 12:44 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-27422, ICPIM-27447, ICPIM-25149
Test Case | ICPIM-27432 | ICPIM-27431 Portfolio - Dashboard Viewer: Drill-in for non-leveled Assets | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2014-09-04 12:06 | 10800 | 7200 | 3600 | 66% | 10800 | 7200 | 3600 | 66% |  | ICPIM-18933
Test Case | ICPIM-27417 | ICPIM-27025 Remove Items From Virtual Machine Manager | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 16:08 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27413 | ICPIM-27025 Application New Connection - Hardware | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 16:00 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27412 | ICPIM-27025 Virtual Machine New Connection | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 16:00 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27411 | ICPIM-27025 Hardware New Connection | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 15:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27410 | ICPIM-27025 Hypervisor New Connection | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 15:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27409 | ICPIM-27025 Cluster New Connection | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 15:59 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27401 | ICPIM-27400 Manage Favorites - Add/Edit Description of Favorite -TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-09-03 14:29 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-27399 | ICPIM-27025 Create Application - Map to Hardware | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 12:54 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-27398 | ICPIM-27025 Change Application Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27397 | ICPIM-27025 Change Hardware Assignment | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27396 | ICPIM-27025 Change Virtual Machine Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27395 | ICPIM-27025 Change Hypervisor Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:34 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-27394 | ICPIM-27025 Change Cluster Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-27393 | ICPIM-27025 Remove Application Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-27392 | ICPIM-27025 Remove Hardware Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 600 | 300 | 300 | 50% | 600 | 300 | 300 | 50%
Test Case | ICPIM-27391 | ICPIM-27025 Remove Virtual Machine Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-27390 | ICPIM-27025 Remove Hypervisor Mapping | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100% |  | ICPIM-27584
Test Case | ICPIM-27389 | ICPIM-27025 Edit Application | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27388 | ICPIM-27025 Edit Virtual Machine | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27387 | ICPIM-27025 Edit Assigned Hardware | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:33 |  | 900 | 1800 | 33% |  | 900 | 1800 | 33%
Test Case | ICPIM-27386 | ICPIM-27025 Edit Hypervisor | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:32 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27385 | ICPIM-27025 Edit Cluster | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:32 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27384 | ICPIM-27025 Create Application - Map to Virtual Machine | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:31 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27383 | ICPIM-27025 Assign Hardware | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:31 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33%
Test Case | ICPIM-27382 | ICPIM-27025 Create Virtual Machine | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:31 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27381 | ICPIM-27025 Create Hypervisor | All |  | Garrett S. | Garrett S. |  | New | 2014-09-03 11:30 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-27350 | ICPIM-22983 Tasks - Filter by Target Location | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2014-09-02 10:05 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-27216
Test Case | ICPIM-27349 | ICPIM-27348 Filter Change Request by Information | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2014-09-02 10:00 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-27216
Test Case | ICPIM-27345 | ICPIM-27344 Web UI - Change Selected Icon: iTracs GREEN icon when selected | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2014-08-29 15:31 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-25417, ICPIM-26322
Test Case | ICPIM-27343 | ICPIM-27025 Create Cluster | All |  | Suzette Weiss | Garrett S. | Windows Client | New | 2014-08-29 14:56 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-27324 | ICPIM-27323 BBB: Post Commissioning Power Phase Report | All |  | Loan Ha | Loan Ha |  | Fail | 2014-08-28 13:52 |  | 23400 | 0 | 100% |  | 23400 | 0 | 100% |  | ICPIM-27340, ICPIM-33292
Test Case | ICPIM-27307 | ICPIM-27306 Ensure CPIM Log is Thread Safe | All |  | Garrett S. | Garrett S. |  | New | 2014-08-27 16:50 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-25752
Test Case | ICPIM-27285 | ICPIM-27284 Adding ability to inherit IT Services from Library Item TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-08-27 10:07 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-27281 | ICPIM-27280 Intel DCM 3.8 added to installer TC | All |  | Loan Ha | Loan Ha |  | Pass | 2014-08-26 16:37 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-27275 | ICPIM-27274 Commission - Set Destination: Select destination | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2014-08-26 15:39 | 7200 | 4500 | 2700 | 62% | 7200 | 4500 | 2700 | 62% |  | ICPIM-27271, ICPIM-26706, ICPIM-25233, ICPIM-25807
Test Case | ICPIM-27232 | ICPIM-27231 Intel DCM Update 3.8 TC | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-08-26 09:32 | 10800 | 10800 | 0 | 100% | 10800 | 10800 | 0 | 100% |  | ICPIM-27320
Test Case | ICPIM-27226 | ICPIM-24520 Review Debug Log | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-08-25 13:57 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-27213 | ICPIM-27211 Datastore value change log recording | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-08-25 12:54 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100% |  | ICPIM-27219
Test Case | ICPIM-27203 | ICPIM-24520 Ensure Assets in Active Commission Are Mapped But Not Placed | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-25 09:53 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-26855
Test Case | ICPIM-27200 | ICPIM-24520 Ensure Ability is Provided to Supply Missing 3rd Party Info in Asset Reconciliation Dialog | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-25 09:46 | 3600 | 4800 | 0 | 100% | 3600 | 4800 | 0 | 100% |  | ICPIM-27505, ICPIM-26851, ICPIM-27199
Test Case | ICPIM-27199 | ICPIM-24520 Ensure Force override for 3rd Party Location | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-25 09:31 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-27497, ICPIM-27505, ICPIM-26853, ICPIM-27200
Test Case | ICPIM-27198 | ICPIM-24520 Ensure Assets Can be Parented By "Store" Class Assets and Return No Errors | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-25 09:20 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25% |  | ICPIM-26852, ICPIM-25767
Test Case | ICPIM-27192 | ICPIM-24520 Ensure SKU Match, Unique ID Absent Shall Match Assets | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-25 09:08 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33% |  | ICPIM-26854, ICPIM-25055, ICPIM-25724, ICPIM-25760, ICPIM-25761
Test Case | ICPIM-27163 | ICPIM-27162 Assigned Template in Audit dialog -TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2014-08-22 13:23 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-27139, ICPIM-27144, ICPIM-27149, ICPIM-27158, ICPIM-16681, ICPIM-17474, ICPIM-27155
Test Case | ICPIM-27161 | ICPIM-27135 Web Client Setup | All |  | Trinh Nguyen | Todd Brewer | Web Client | Pass | 2014-08-22 13:16 | 3600 | 300 | 3300 | 8% | 3600 | 300 | 3300 | 8%
Test Case | ICPIM-27154 | ICPIM-27135 Pre-req install testing | All |  | Todd Brewer | Todd Brewer | Windows Client | New | 2014-08-22 08:41 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-27153 | ICPIM-27135 Uninstall Testing for default installed location | All |  | Mai Nguyen | Todd Brewer | Windows Client | Fail | 2014-08-22 08:39 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-20651, ICPIM-26891, ICPIM-34072, ICPIM-35061, ICPIM-35084
Test Case | ICPIM-27152 | ICPIM-27135 Install Testing | All |  | Todd Brewer | Todd Brewer | Windows Client | New | 2014-08-22 08:39 | 14400 |  | 14400 | 0% | 14400 |  | 14400 | 0%
Test Case | ICPIM-27148 | ICPIM-20059 Enhancement - Power can only be connected to Power | All |  | Todd Brewer | Todd Brewer | Windows Client | Pass | 2014-08-21 15:03 | 7200 | 14400 | 0 | 100% | 7200 | 14400 | 0 | 100% |  | ICPIM-9577
Test Case | ICPIM-27147 | ICPIM-27135 Version Number | All |  | Tien Pham | Todd Brewer | Web Client, Windows Client | Fail | 2014-08-21 14:09 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33% |  | ICPIM-34078, ICPIM-34567
Test Case | ICPIM-27128 | ICPIM-27127 Provide Drag and Drop Ability to Move a Connection | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2014-08-21 10:21 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-27178, ICPIM-27137
Test Case | ICPIM-27082 | ICPIM-28317 ExportAssetInventory | All |  | Garrett S. | Garrett S. |  | Pass | 2014-08-19 12:06 | 7200 | 7500 | 0 | 100% | 7200 | 7500 | 0 | 100%
Test Case | ICPIM-27080 | ICPIM-28302 ExplortAssetCooling | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27079 | ICPIM-28305 ExportAssetNetwork | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27078 | ICPIM-28308 ExportAssetSpace | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27076 | ICPIM-28306 ExportAssetPower | All |  | Thuy Tran | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 1800 | 9000 | 16% | 10800 | 1800 | 9000 | 16%
Test Case | ICPIM-27075 | ICPIM-28303 ExportAssetData | All |  | Thuy Tran | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27074 | ICPIM-28304 ExportDataStores | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:05 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27073 | ICPIM-28316 ExportAssetHierarchy | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:04 | 10800 | 5700 | 5100 | 52% | 10800 | 5700 | 5100 | 52% |  | ICPIM-27129
Test Case | ICPIM-27072 | ICPIM-28301 ExportAssets | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:04 | 10800 | 1800 | 9000 | 16% | 10800 | 1800 | 9000 | 16%
Test Case | ICPIM-27071 | ICPIM-28307 ExportSchema | All |  | Garrett S. | Garrett S. | Application Layer | Pass | 2014-08-19 12:04 | 10800 | 2100 | 8700 | 19% | 10800 | 2100 | 8700 | 19%
Test Case | ICPIM-27032 | ICPIM-27030 Security right for 'Analytics' Menu Item ('Display Analytics Menu' - Default off) | All |  | Khang Nguyen | Garrett S. | Application Layer | Pass | 2014-08-18 11:04 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66% |  | ICPIM-27033
Test Case | ICPIM-27026 | ICPIM-27025 VM Manager Dialog Redesign | All |  | Suzette Weiss | Garrett S. |  | Fail | 2014-08-18 10:21 | 3600 | 1200 | 2400 | 33% | 3600 | 1200 | 2400 | 33% |  | ICPIM-27047, ICPIM-24694, ICPIM-25170
Test Case | ICPIM-27023 | ICPIM-26018 Delete Button in Asset Reconciliation | All |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-08-18 09:53 | 3600 | 600 | 3000 | 16% | 3600 | 600 | 3000 | 16% |  | ICPIM-24946
Test Case | ICPIM-26986 | ICPIM-26315 Disney Avery Label Report: Take 3 - Using Avery Office Plugin | All |  | Garrett S. | Garrett S. | Windows Client | Pass | 2014-08-14 10:00 |  | 5400 | 7200 | 42% |  | 5400 | 7200 | 42%
Test Case | ICPIM-26974 | ICPIM-26201 AuthenticationWS | All |  | Garrett S. | Garrett S. |  | New | 2014-08-13 09:08
Test Case | ICPIM-26908 | ICPIM-26905 Ensure All PDUs Within CPIM are Discovered by DEA | All |  | Garrett S. | Garrett S. |  | New | 2014-08-07 10:33
Test Case | ICPIM-26907 | ICPIM-26905 Configuration | All |  | Garrett S. | Garrett S. |  | New | 2014-08-07 10:31
Test Case | ICPIM-26906 | ICPIM-26905 Automated Logic Installation | All |  | Garrett S. | Garrett S. |  | New | 2014-08-07 10:31
Test Case | ICPIM-26771 | ICPIM-26716 UAT:- Commissioning a Server |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:10
Test Case | ICPIM-26770 | ICPIM-26716 UAT:- Viewing the Commission Results |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:09
Test Case | ICPIM-26769 | ICPIM-26716 UAT:- Commissioning an Enclosure |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:08
Test Case | ICPIM-26768 | ICPIM-26716 UAT:- Cloning a Report |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:08
Test Case | ICPIM-26767 | ICPIM-26716 UAT:- Defining a New Report |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:07
Test Case | ICPIM-26766 | ICPIM-26716 UAT:- Generating a Standard Report |  |  | Loan Ha | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:06
Test Case | ICPIM-26765 | ICPIM-26716 UAT:- Saving the Dashboard as a Graphic |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:05 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26764 | ICPIM-26716 UAT:- Printing a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 11:04 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26763 | ICPIM-26716 UAT:- Removing an Item from a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:56 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26762 | ICPIM-26716 UAT:- Removing Dashboards |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:54 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26761 | ICPIM-26716 UAT:- Editing a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:53 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26760 | ICPIM-26716 UAT:- Opening a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:47 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26759 | ICPIM-26716 UAT:- Finding a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:46 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26758 | ICPIM-26716 UAT:- Copying Existing Formatting to an Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:45 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26757 | ICPIM-26716 UAT:- Displaying an Item in 3D |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:43 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-26756 | ICPIM-26716 UAT:- Creating Labels for Dashboard Items |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:42 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26755 | ICPIM-26716 UAT:- Building a Dashboard |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:42 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26754 | ICPIM-26716 UAT:- Mapping Assets to Line of Business |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:41 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-26753 | ICPIM-26716 UAT:- Conducting a Commission Search by Line of Business |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:39 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26752 | ICPIM-26716 UAT:- Conducting a Basic Search by Line of Business |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:39 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26751 | ICPIM-26716 UAT:- Filtering the Viewer Display by Line of Business |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:38 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26750 | ICPIM-26716 UAT:- Assigning a Line of Business to an Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:37 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26749 | ICPIM-26716 UAT:- Adding and Configuring a Line of Business |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:36 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26748 | ICPIM-26716 UAT:- Creating a View State |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:36 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26747 | ICPIM-26716 UAT:- Conducting a Basic Search |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:34 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-26746 | ICPIM-26716 UAT:-Viewing a Dictionary |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:33 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-26745 | ICPIM-26716 UAT:- Viewing Datastores in a Browser Window or Report |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:32 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-26744 | ICPIM-26716 UAT:- Viewing Datastores in Dashboards |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:27 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26743 | ICPIM-26716 UAT:- Viewing Datastores in the Viewer |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:26 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26742 | ICPIM-26716 UAT:- Entering a Datastore Value |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:26 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26741 | ICPIM-26716 UAT:- Creating Datastores |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:25 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26740 | ICPIM-26716 UAT:- Accessing Datastores |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:25 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26739 | ICPIM-26716 UAT:- Assigning a Template to an Equipment Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:24 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26738 | ICPIM-26716 UAT:- Importing a Library Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:23 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26737 | ICPIM-26716 UAT:- Exporting a Library Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:22 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26736 | ICPIM-26716 UAT:- Copying a Library Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:22 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26735 | ICPIM-26716 UAT:- Editing a Library Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:21 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26734 | ICPIM-26716 UAT:- Creating a Library Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:20 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-26733 | ICPIM-26716 UAT:- Viewing the Index Value Identification |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:20 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26732 | ICPIM-26716 UAT:- Hiding and Showing Items in the Viewer |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:19 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26731 | ICPIM-26716 UAT:- Accessing View States |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:18 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26730 | ICPIM-26716 UAT:-Modifying View Settings |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:14 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26729 | ICPIM-26716 UAT:- Opening the Viewer |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:14 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26728 | ICPIM-26716 UAT:- Viewing a Power Trace |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:13 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26727 | ICPIM-26716 UAT:- Viewing a Connectivity Trace |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:12 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26726 | ICPIM-26716 UAT:- Deleting Database Items |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:11 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26725 | ICPIM-26716 UAT:- Renaming Database Items |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:10 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26724 | ICPIM-26716 UAT:- Copying Database Items |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:08 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26723 | ICPIM-26716 UAT:- Moving Database Items |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:07 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26722 | ICPIM-26716 UAT:- Creating a Database Item |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:05 |  | 120 | 0 | 100% |  | 120 | 0 | 100%
Test Case | ICPIM-26721 | ICPIM-26716 UAT:- Adding a Subclass |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:03 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26720 | ICPIM-26716 UAT:- Adding a New Class |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:01 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26719 | ICPIM-26716 UAT:- Working with Database Classes |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 10:00 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-26718 | ICPIM-26716 UAT:- Adding a New User |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 09:59 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26717 | ICPIM-26716 UAT:- Logging In Using a Full Install |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-08-01 09:58 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-26543 | ICPIM-26201 AssetManagementWS | All |  | Garrett S. | Garrett S. |  | Pass | 2014-07-22 08:57 |  | 64800 | 0 | 100% |  | 64800 | 0 | 100%
Test Case | ICPIM-26388 | ICPIM-26274 Webex w/ Derek @ Cedars |  |  | Garrett S. | Garrett S. |  | Invalid | 2014-07-11 16:16 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-26379 | ICPIM-26378 TC- Library export results in empty library | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2014-07-11 11:13 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-26347 | ICPIM-26334 Commission - Results | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2014-07-09 11:29 | 7200 | 8400 | 0 | 100% | 7200 | 8400 | 0 | 100% |  | ICPIM-26364, ICPIM-26361, ICPIM-27253, ICPIM-26987
Test Case | ICPIM-26346 | ICPIM-40026 Decommission - Results | All |  | Tien Pham | Loan Ha | Web Client | Fail | 2014-07-09 11:27 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100% |  | ICPIM-26364, ICPIM-27261, ICPIM-26361, ICPIM-38356, ICPIM-26987
Test Case | ICPIM-26325 | ICPIM-26324 Historical Info - Standard Report – Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2014-07-08 11:38 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-25507, ICPIM-26462, ICPIM-26465, ICPIM-26369
Test Case | ICPIM-26323 | ICPIM-23308 Ensure Popup throughout UI display at an Appropriate Size to Display Needed Data | All |  | Trinh Nguyen | Garrett S. | Web Client | Pass | 2014-07-08 11:29 | 7200 | 3600 | 3600 | 50% | 7200 | 3600 | 3600 | 50% |  | ICPIM-27107
Test Case | ICPIM-26322 | ICPIM-23308 Ensure the Correct Icons are Being Used | All |  | Trinh Nguyen | Garrett S. | Web Client | Pass | 2014-07-08 10:28 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-27345
Test Case | ICPIM-26317 | ICPIM-26315 Disney Avery Label Report redo |  |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-07-08 10:15 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-25922
Test Case | ICPIM-26313 | ICPIM-23308 Regression: Ensure Nomenclature Matches Current Standard | All |  | Trinh Nguyen | Garrett S. | Web Client | Pass | 2014-07-08 10:01 | 7200 | 1800 | 5400 | 25% | 7200 | 1800 | 5400 | 25% |  | ICPIM-25135
Test Case | ICPIM-26273 | ICPIM-23308 Ensure Font Color is Consistent with iTRACS UI Specifications Throughout Interface | All |  | Trinh Nguyen | Garrett S. | Web Client | Pass | 2014-07-03 14:03 | 10800 | 1800 | 9000 | 16% | 10800 | 1800 | 9000 | 16% |  | ICPIM-25410
Test Case | ICPIM-26222 | ICPIM-26201 VisualizationWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:35
Test Case | ICPIM-26221 | ICPIM-26201 VirtualMachineManagementWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:35
Test Case | ICPIM-26220 | ICPIM-26201 UserProfilesWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:35
Test Case | ICPIM-26219 | ICPIM-26201 UserManagementWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:35
Test Case | ICPIM-26218 | ICPIM-26201 TemplateWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26217 | ICPIM-26201 TaskManagementWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26216 | ICPIM-26201 SimulationWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26215 | ICPIM-26201 SecurityWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26214 | ICPIM-26201 RoleManagementWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26213 | ICPIM-26201 ReportingWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:34
Test Case | ICPIM-26212 | ICPIM-26201 OperationalDataWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:33
Test Case | ICPIM-26211 | ICPIM-26201 NotificationWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:33
Test Case | ICPIM-26210 | ICPIM-26201 MapviewWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:33
Test Case | ICPIM-26209 | ICPIM-26201 IWSProxyService | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:33
Test Case | ICPIM-26208 | ICPIM-26201 IWSCapacityManagement | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:33
Test Case | ICPIM-26207 | ICPIM-26201 IWSAssetManagement | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:32
Test Case | ICPIM-26206 | ICPIM-26201 EquipmentClassWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:32
Test Case | ICPIM-26205 | ICPIM-26201 ConnectivityWS | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-30 14:32 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-26449
Test Case | ICPIM-26204 | ICPIM-26201 ChangeManagementWS | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-30 14:32 |  | 64800 | 0 | 100% |  | 64800 | 0 | 100%
Test Case | ICPIM-26203 | ICPIM-26201 AssetChangeManagementWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:32
Test Case | ICPIM-26202 | ICPIM-26201 AlarmWS | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-30 14:31
Test Case | ICPIM-26187 | ICPIM-12703 Web - Remember Me Login | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-06-27 12:39 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-26117 | ICPIM-26116 Separate Jaspersoft Installation from CPIM Suite | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-06-24 09:59 | 10800 | 9000 | 1800 | 83% | 10800 | 9000 | 1800 | 83%
Test Case | ICPIM-26019 | ICPIM-26018 Ensure Data Exchange Agent Manager Opens |  |  | Thuy Tran | Garrett S. | Data Exchange Agent | Pass | 2014-06-20 12:48 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-26011 | ICPIM-24520 Ensure Flat FIle DEA is Following CPIM Container Rules | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-20 11:09 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25%
Test Case | ICPIM-26007 | ICPIM-24520 Ensure Datastores for Mapped Assets are Updated with Values from CSV File | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-20 11:01 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50% |  | ICPIM-25370
Test Case | ICPIM-25922 | ICPIM-25921 Disney Avery Label Custom Report | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-06-12 15:30 |  | 16200 | 0 | 100% |  | 16200 | 0 | 100% |  | ICPIM-25968, ICPIM-25971, ICPIM-26317
Test Case | ICPIM-25920 | ICPIM-25712 Decommissioning a Cabinet with “Disconnect direct power circuit and decommission PDU Breaker" rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-12 13:05 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-25919 | ICPIM-25712 Decommissioning a Cabinet with "Disconnect direct power circuit” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-12 13:00 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-25917 | ICPIM-25712 Decommissioning a Cabinet with “Immediate power circuit connection” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-12 12:39 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-25884 | ICPIM-25883 Library Item Catalog | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2014-06-10 14:15 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-17825, ICPIM-25885
Test Case | ICPIM-25850 | ICPIM-25839 Ensure PDU Data Provided by Power IQ is Populated in Analytics Tables | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Invalid | 2014-06-09 12:46
Test Case | ICPIM-25849 | ICPIM-25839 Ensure PDU Data is Returned By Power IQ DEA and Populated in Correct Data Stores | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 12:45 |  | 21600 | 0 | 100% |  | 21600 | 0 | 100%
Test Case | ICPIM-25848 | ICPIM-25839 Ensure Power Analytics for Enclosures is Summed From Child Assets | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Invalid | 2014-06-09 12:37
Test Case | ICPIM-25847 | ICPIM-25839 Ensure User Can Map Data Stores to Power IQ Data Points Congruous with Other DEA's | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 12:33 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-25846 | ICPIM-25839 Ensure Power IQ DEA is Populating Mapped Data Stores with Correct Data for Mapped Devices | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 12:32 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-25845 | ICPIM-25839 Ensure Power IQ DEA Data is Being Populated and Updated in Real Time in Analytics Tables | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Invalid | 2014-06-09 12:31
Test Case | ICPIM-25844 | ICPIM-25839 Ensure Power IQ DEA Is Logging Errors | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 12:29 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-25843 | ICPIM-25839 Ensure Power IQ DEA Maps Devices by Name | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 11:39 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100%
Test Case | ICPIM-25842 | ICPIM-25839 Configure Power IQ DEA and Connect to Demo System | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 11:38 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-26022, ICPIM-25890
Test Case | ICPIM-25841 | ICPIM-25839 Ensure Necessary Data Stores are Present for Power IQ DEA | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 11:36 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-25840 | ICPIM-25839 Install Power IQ DEA | All |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-06-09 11:35 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100%
Test Case | ICPIM-25771 | ICPIM-24520 Module sent in with unique ID that maps to 2 Modules in CPIM | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:16 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-25998
Test Case | ICPIM-25770 | ICPIM-24520 Panel sent in with unique ID that maps to 2 Panels in CPIM | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:16 | 3600 | 3600 | 1800 | 66% | 3600 | 3600 | 1800 | 66% |  | ICPIM-25998
Test Case | ICPIM-25769 | ICPIM-24520 Export file created for mapped devices | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:15 | 3600 | 1500 | 2100 | 41% | 3600 | 1500 | 2100 | 41% |  | ICPIM-25983
Test Case | ICPIM-25768 | ICPIM-24520 Mapping Power Modules | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:14 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-25767 | ICPIM-24520 Ensure Parenting of Panel to Store | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-04 11:13 | 3600 | 3660 | 2640 | 58% | 3600 | 3660 | 2640 | 58% |  | ICPIM-27198
Test Case | ICPIM-25766 | ICPIM-24520 Module moved to another Panel | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:07 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75%
Test Case | ICPIM-25765 | ICPIM-24520 Panels moved to another enclosure | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:07 | 3600 | 4800 | 0 | 100% | 3600 | 4800 | 0 | 100% |  | ICPIM-25977
Test Case | ICPIM-25764 | ICPIM-24520 Panels overlap each other on file input | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:06 | 3600 | 6600 | 0 | 100% | 3600 | 6600 | 0 | 100% |  | ICPIM-25974
Test Case | ICPIM-25763 | ICPIM-24520 Module with existing Unique ID sent in | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:05 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-25762 | ICPIM-24520 Panel with existing Unique ID sent in | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:04 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-25761 | ICPIM-24520 Module with non-existing Unique ID sent in | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:04 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75% |  | ICPIM-27192
Test Case | ICPIM-25760 | ICPIM-24520 Panel with non-existing Unique ID sent in | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 11:03 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75% |  | ICPIM-27192
Test Case | ICPIM-25756 | ICPIM-24520 Ensure CSV File is Scraped from Specified Directory | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-04 10:56 |  | 1200 | 600 | 66% |  | 1200 | 600 | 66%
Test Case | ICPIM-25730 | ICPIM-24520 Negative Test - Ensure Re-Sync of Devices Does Not Cause Location Conflict | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:44 | 3600 | 3000 | 600 | 83% | 3600 | 3000 | 600 | 83%
Test Case | ICPIM-25729 | ICPIM-24520 Module Parenting - Ensure Module Type is Adhered To | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:44 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75%
Test Case | ICPIM-25728 | ICPIM-24520 - - | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-06-03 11:42
Test Case | ICPIM-25727 | ICPIM-24520 Ensure Parenting of Module to Panel | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:41 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-25726 | ICPIM-24520 Ensure Parenting of Panel/Device to Cabinet | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:41 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-25725 | ICPIM-24520 Ensure Panels and Modules are Moved Appropriately when Parent is Changed | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:40 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66%
Test Case | ICPIM-25724 | ICPIM-24520 Ensure New Assets Are Created Using Correct SKU(Library Item) | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:20 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-25815, ICPIM-25817, ICPIM-27192
Test Case | ICPIM-25723 | ICPIM-24520 Ensure Flat File Agent Naming is Correct After Installation | All |  | Garrett S. | Garrett S. |  | Pass | 2014-06-03 11:12 | 1800 | 3900 | 0 | 100% | 1800 | 3900 | 0 | 100% |  | ICPIM-13815
Test Case | ICPIM-25718 | ICPIM-25712 Decommissioning a Switch with “Disconnect direct power circuit and decommission PDU Breaker" rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:14 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-25902
Test Case | ICPIM-25717 | ICPIM-25712 Decommissioning a Switch with “Immediate power circuit connection” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:13 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-25716 | ICPIM-25712 Decommissioning a Switch with "Disconnect direct power circuit” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:11 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-25715 | ICPIM-25712 Decommissioning a Server with “Disconnect direct power circuit and decommission PDU Breaker" rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:08 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-25714 | ICPIM-25712 Decommissioning a Server with "Disconnect direct power circuit” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:06 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100%
Test Case | ICPIM-25713 | ICPIM-25712 Decommissioning a Server with “Immediate power circuit connection” rule. | All |  | Loan Ha | Loan Ha |  | Pass | 2014-06-02 16:04 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-25662 | ICPIM-28722 Ensure The Necessary RF Code Data Stores Have Been Created in CPIM |  |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-05-29 13:34 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-33869, ICPIM-33872, ICPIM-25955
Test Case | ICPIM-25661 | ICPIM-28722 Ensure Sensor Data is Polled at the Same Interval as Asset Data in RF Code |  |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-05-29 13:34 |  | 7500 | 600 | 92% |  | 7500 | 600 | 92%
Test Case | ICPIM-25660 | ICPIM-28722 Ensure RF Code Sensor Data Can Be Mapped Against Sensor Data Stores |  |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-05-29 13:34 |  | 8400 | 0 | 100% |  | 8400 | 0 | 100%
Test Case | ICPIM-25659 | ICPIM-28722 Ensure RF Code Data that is Mapped to CPIM Assets is Correct |  |  | Garrett S. | Garrett S. | Data Exchange Agent | Pass | 2014-05-29 13:33 |  | 8400 | 0 | 100% |  | 8400 | 0 | 100%
Test Case | ICPIM-25237 | ICPIM-14860 About CPIM Browser Interface - CPIM Browser Help 4.1 | All |  | An Vo | Rachna Muthanna | Web Client | Pass | 2014-05-06 17:25 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-25178 | ICPIM-25177 Custom Report: Find Objects with Duplicate Vconns |  |  | Loan Ha | Loan Ha |  | Pass | 2014-05-05 09:49 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-25055 | ICPIM-24520 Ensure SKU Datastore Is Used To Identify Asset to SKU Mapping | All |  | Garrett S. | Garrett S. |  | Pass | 2014-04-28 12:39 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-25779, ICPIM-25783, ICPIM-27192, ICPIM-24474
Test Case | ICPIM-24729 | ICPIM-38539 Task Management - Tasks: Assign/Unassign | All |  | An Vo | Loan Ha | Web Client | Pass | 2014-04-21 13:12 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-24587 | ICPIM-23417 Analytics: Verify Cooling Tables | All |  | Garrett S. | Garrett S. |  | Pass | 2014-04-16 13:20 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-24586 | ICPIM-23417 Analytics: Ensure Thermals Datastores | All |  | Garrett S. | Garrett S. |  | Pass | 2014-04-16 13:19 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-24585 | ICPIM-23417 Analytics: Verify Thermals Tables | All |  | Garrett S. | Garrett S. |  | Pass | 2014-04-16 13:18 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-24584 | ICPIM-23417 Analytics: Verifiy Space Tables | All |  | Garrett S. | Garrett S. |  | Pass | 2014-04-16 13:17 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-24563 | ICPIM-16346 Review Charts on Ever Level, Compare Willow to Mims. | All |  | Garrett S. | Garrett S. | Windows Client | Pass | 2014-04-15 16:58 |  | 16200 | 0 | 100% |  | 16200 | 0 | 100%
Test Case | ICPIM-24521 | ICPIM-24520 - - | All |  | Garrett S. | Garrett S. |  | Invalid | 2014-04-11 15:00 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100%
Test Case | ICPIM-24199 | ICPIM-22982 Asset Management WS Scheme Support | All |  | Garrett S. | Garrett S. |  | Pass | 2014-03-31 16:43 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-24207
Test Case | ICPIM-24097 | ICPIM-27477 SystemMax Controler Support | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-26 15:42 |  | 13800 | 0 | 100% |  | 13800 | 0 | 100%
Test Case | ICPIM-24095 | ICPIM-24094 Delete dialog: Default focus on Cancel button |  |  | Mai Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-03-26 15:14 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33% |  | ICPIM-33754
Test Case | ICPIM-24093 | ICPIM-27477 Administrative Support for Synch Errors | All |  | Garrett S. | Rachna Muthanna |  | New | 2014-03-26 15:03 | 10800 | 9000 | 1800 | 83% | 10800 | 9000 | 1800 | 83%
Test Case | ICPIM-24082 | ICPIM-16346 Analytics Test Pre-Conditions and Configuration | All |  | Garrett S. | Garrett S. | Windows Client | Invalid | 2014-03-26 14:48 | 28800 |  | 28800 | 0% | 28800 |  | 28800 | 0%
Test Case | ICPIM-23928 | ICPIM-23917 Fiber Switch Ports Breakdown by Location (Table) -TC | All |  | Trinh Nguyen | Rachna Muthanna | Web Client | Fail | 2014-03-18 15:06 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-23927 | ICPIM-23917 Shelf Space Totals by Location (Bar Graph) | All |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-03-18 15:03 | 3600 | 6000 | 0 | 100% | 3600 | 6000 | 0 | 100% |  | ICPIM-34791, ICPIM-23964
Test Case | ICPIM-23926 | ICPIM-23917 Switch Cards and Blades Totals by Location (Bar Graph) | All |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:59 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-34791, ICPIM-23961
Test Case | ICPIM-23925 | ICPIM-23917 U Positions by Location (Bar Graph) | All |  | An Vo | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:58 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-34791, ICPIM-23947
Test Case | ICPIM-23924 | ICPIM-23917 Shelf Space Totals by Location (Table) | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:54 | 3600 | 5700 | 0 | 100% | 3600 | 5700 | 0 | 100% |  | ICPIM-34791, ICPIM-23952, ICPIM-34797
Test Case | ICPIM-23923 | ICPIM-23917 Power Totals by Location (Bar Graph)- TC | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:52 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-34791, ICPIM-23944, ICPIM-23941
Test Case | ICPIM-23922 | ICPIM-23917 Fiber Positions Breakdown by Location (Table) -TC | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Pass | 2014-03-18 14:49 | 3600 | 4800 | 0 | 100% | 3600 | 4800 | 0 | 100% |  | ICPIM-34791
Test Case | ICPIM-23921 | ICPIM-23917 Enclosure Temperature (Celsius Table) - TC | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:47 | 3600 | 6900 | 0 | 100% | 3600 | 6900 | 0 | 100% |  | ICPIM-34791, ICPIM-23938, ICPIM-34794
Test Case | ICPIM-23920 | ICPIM-23917 Copper Switch Ports Breakdown by Location (Table) - TC | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:40 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-34791
Test Case | ICPIM-23919 | ICPIM-23917 Copper Positions Breakdown by Location (Table) - TC | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Fail | 2014-03-18 14:39 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-34791
Test Case | ICPIM-23896 | ICPIM-23667 Build #27 Installation and Configuration | All |  | Rachna Muthanna | Rachna Muthanna |  | Pass | 2014-03-18 09:58 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-23887 | ICPIM-23886 Converting Intel DCM DEA to Operational Data WS | All |  | Loan Ha | Loan Ha | Windows Client | Invalid | 2014-03-17 13:59 | 10800 | 19800 | 0 | 100% | 10800 | 19800 | 0 | 100% |  | ICPIM-24234, ICPIM-24420, ICPIM-27443, ICPIM-22972
Test Case | ICPIM-23884 | ICPIM-23667 Build #25 Installation and Configuration |  |  | Garrett S. | Garrett S. |  | Fail | 2014-03-17 13:05 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-23878 | ICPIM-23877 3DViewer: Load Textures Option | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2014-03-17 11:04 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-24157
Test Case | ICPIM-23831 | ICPIM-23667 Build #25 Installation and Configuration | All |  | Rachna Muthanna | Rachna Muthanna |  | Pass | 2014-03-12 15:37 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100% |  | ICPIM-23826
Test Case | ICPIM-23815 | ICPIM-27477 imVision: Support for Point-to-Point Connectivity-TC | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-12 11:22 | 10800 | 11700 | 0 | 100% | 10800 | 11700 | 0 | 100% |  | ICPIM-24203, ICPIM-24227, ICPIM-24230, ICPIM-24249, ICPIM-24827, ICPIM-24200, ICPIM-24240, ICPIM-24243, ICPIM-24312, ICPIM-24835, ICPIM-24838, ICPIM-24841, ICPIM-24844, ICPIM-24224
Test Case | ICPIM-23812 | ICPIM-23811 Textual Trace -TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-03-12 10:30 | 7200 | 28800 | 0 | 100% | 7200 | 28800 | 0 | 100%
Test Case | ICPIM-23810 | ICPIM-22999 CSV Download |  |  | Loan Ha | Loan Ha |  | Pass | 2014-03-12 09:40 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-23804 | ICPIM-27477 Adhoc Synch Execution (differential/partial sync, not implemented) | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-11 14:35 | 10800 | 4800 | 6000 | 44% | 10800 | 4800 | 6000 | 44% |  | ICPIM-24588, ICPIM-24203, ICPIM-24227, ICPIM-24230, ICPIM-24249, ICPIM-24447, ICPIM-24480, ICPIM-24200, ICPIM-24240, ICPIM-24243, ICPIM-24312, ICPIM-24224
Test Case | ICPIM-23802 | ICPIM-27477 Synch Data on Update | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-11 13:56 | 7200 | 18900 | 0 | 100% | 7200 | 18900 | 0 | 100% |  | ICPIM-34253
Test Case | ICPIM-23785 | ICPIM-27477 imVision: Construction of imVision SKU library-TC | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-10 15:42 | 7200 | 6600 | 600 | 91% | 7200 | 6600 | 600 | 91% |  | ICPIM-24203, ICPIM-24227, ICPIM-24230, ICPIM-24249, ICPIM-24200, ICPIM-24240, ICPIM-24243, ICPIM-24312, ICPIM-24224, ICPIM-23335
Test Case | ICPIM-23783 | ICPIM-27477 Administation of Location Conflicts | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-03-10 14:37 | 10800 | 3600 | 7200 | 33% | 10800 | 3600 | 7200 | 33%
Test Case | ICPIM-23781 | ICPIM-23780 Identifying the size of the images associated with a template | All |  | Jeff Wojnar | Loan Ha | Windows Client | Invalid | 2014-03-10 14:17
Test Case | ICPIM-23777 | ICPIM-23776 Display Sub-class in Visual Trace |  |  | Vinh Nguyen | Rachna Muthanna | Windows Client | New | 2014-03-10 12:30 | 3600 | 2400 | 1200 | 66% | 3600 | 2400 | 1200 | 66% |  | ICPIM-33784
Test Case | ICPIM-23701 | ICPIM-23667 Build #12 Installation and Configuration |  |  | Garrett S. | Garrett S. |  | Pass | 2014-03-06 14:13 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100%
Test Case | ICPIM-23577 | ICPIM-23308 Deny CR and Follow-up on a CR - Regression Test Case | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-28 15:56 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-23581, ICPIM-25090
Test Case | ICPIM-23544 | ICPIM-23308 Admin Menu- Regression Test case | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2014-02-27 15:56 | 3600 | 6300 | 0 | 100% | 3600 | 6300 | 0 | 100% |  | ICPIM-23541
Test Case | ICPIM-23539 | ICPIM-23308 Editing and Visual Work Actions - Regression Test case | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-27 15:43 | 7200 | 12600 | 0 | 100% | 7200 | 12600 | 0 | 100% |  | ICPIM-23558, ICPIM-23551, ICPIM-23540
Test Case | ICPIM-23532 | ICPIM-23308 Advance Navigation Bar / Ghost Bar – Regression Test case | All |  | Phuong Phan | Rachna Muthanna | Web Client | Pass | 2014-02-27 13:52 | 7200 | 2700 | 4500 | 37% | 7200 | 2700 | 4500 | 37% |  | ICPIM-27286, ICPIM-26706, ICPIM-19938
Test Case | ICPIM-23509 | ICPIM-23308 Changes Tab – Active/Inactive CR’s- Regression Test case | All |  | Phuong Phan | Rachna Muthanna | Web Client | Pass | 2014-02-26 13:30 | 7200 | 12600 | 0 | 100% | 7200 | 12600 | 0 | 100% |  | ICPIM-24619, ICPIM-26706
Test Case | ICPIM-23507 | ICPIM-23308 Tasks (Types/Status) Tab - Regression Test case | All |  | Trinh Nguyen | Loan Ha | Web Client | Pass | 2014-02-26 13:25 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-23487, ICPIM-23499, ICPIM-23510, ICPIM-27352, ICPIM-26706, ICPIM-23508
Test Case | ICPIM-23506 | ICPIM-21844 Change Management - Repurpose CR: Plan Work Project | All |  | Thuy Tran | Rachna Muthanna | Web Client | Pass | 2014-02-26 12:29 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-23594, ICPIM-27910, ICPIM-27905
Test Case | ICPIM-23491 | ICPIM-39472 Portfolio - Favorites: Root Items | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2014-02-26 09:31 | 7200 | 8100 | 0 | 100% | 7200 | 8100 | 0 | 100%
Test Case | ICPIM-23478 | ICPIM-39837 Change Management - Remove CR: Work Flow | All |  | Thuy Tran | Rachna Muthanna | Web Client | Pass | 2014-02-25 15:41 | 10800 | 21600 | 0 | 100% | 10800 | 21600 | 0 | 100%
Test Case | ICPIM-23465 | ICPIM-21827 Change Management - Move CR: Move CR with multiple associated assets | All |  | Vinh Nguyen | Rachna Muthanna | Web Client | Blocker | 2014-02-25 12:26 | 7200 | 16200 | 0 | 100% | 7200 | 16200 | 0 | 100% |  | ICPIM-35321, ICPIM-23615, ICPIM-35318, ICPIM-23616
Test Case | ICPIM-23459 | ICPIM-23308 Reports- Regression Test case | All |  | Phuong Phan | Jaimes Shonkwiler | Web Client | Pass | 2014-02-25 10:15 | 7200 | 23400 | 0 | 100% | 7200 | 23400 | 0 | 100% |  | ICPIM-23702, ICPIM-23705, ICPIM-23969
Test Case | ICPIM-23455 | ICPIM-39836 Change Management - Install CR: Work Flow | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2014-02-25 10:11 | 7200 | 25200 | 0 | 100% | 7200 | 25200 | 0 | 100% |  | ICPIM-20853, ICPIM-26706, ICPIM-23460
Test Case | ICPIM-23440 | ICPIM-27477 Sync attribute values from imVision to CPIM | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | New | 2014-02-24 16:04 | 10800 | 11400 | 0 | 100% | 10800 | 11400 | 0 | 100% |  | ICPIM-24676
Test Case | ICPIM-23438 | ICPIM-27477 imVision DEA: Default attribute to datastore mappings | All |  | Garrett S. | Jaimes Shonkwiler |  | New | 2014-02-24 15:39 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-24150, ICPIM-24676
Test Case | ICPIM-23437 | ICPIM-23436 Administration of SKU Conflicts | All |  | Loan Ha | Loan Ha | Data Exchange Agent | Pass | 2014-02-24 15:35 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-23435 | ICPIM-23308 MYDCIM- Regression Test Case | All |  | Thuy Tran | Rachna Muthanna | Web Client | Pass | 2014-02-24 15:00 | 7200 | 6000 | 1200 | 83% | 7200 | 6000 | 1200 | 83% |  | ICPIM-24013
Test Case | ICPIM-23434 | ICPIM-27477 CTMR_013_Remove a patching connection between an iPatch Panel and a non iPatch Panel - Mapped in CPIM | All |  | Khang Nguyen | Jaimes Shonkwiler | Data Exchange Agent | New | 2014-02-24 14:21 |  | 7200 | 2400 | 75% |  | 7200 | 2400 | 75% |  | ICPIM-34242
Test Case | ICPIM-23432 | ICPIM-23431 Displaying information for previous and executing synchs | All |  | Loan Ha | Loan Ha | Data Exchange Agent | Pass | 2014-02-24 14:14 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-23429 | ICPIM-23308 Trace- Regression Test Case | All |  | Trinh Nguyen | Rachna Muthanna | Web Client | Pass | 2014-02-24 13:08 | 7200 | 18000 | 0 | 100% | 7200 | 18000 | 0 | 100% |  | ICPIM-23600, ICPIM-23603, ICPIM-23606, ICPIM-26706
Test Case | ICPIM-23428 | ICPIM-23425 Displaying Synch Stats | All |  | Loan Ha | Loan Ha | Data Exchange Agent | Pass | 2014-02-24 13:04 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-24263
Test Case | ICPIM-23427 | ICPIM-23424 User ID returns own assigned interfaces (non-admin user) | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-24 12:58 |  | 4200 | 0 | 100% |  | 4200 | 0 | 100% |  | ICPIM-24255
Test Case | ICPIM-23426 | ICPIM-23424 User ID returns assigned interfaces (Admin User) | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-24 12:54 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-23423 | ICPIM-23417 Analytics: Ensure "Space Density Target" data store. | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-24 10:31 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-23422 | ICPIM-23419 Administration for imVision DEA | All |  | Loan Ha | Loan Ha | Data Exchange Agent | Pass | 2014-02-24 10:31 | 10800 | 7200 | 3600 | 66% | 10800 | 7200 | 3600 | 66% |  | ICPIM-24240
Test Case | ICPIM-23420 | ICPIM-23417 Analytics: Verify Power Tables | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-24 10:20 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-23418 | ICPIM-27477 iTRACS DEA Configuration for imVision | All |  | Garrett S. | Loan Ha | Data Exchange Agent | New | 2014-02-24 09:59 | 10800 | 14400 | 0 | 100% | 10800 | 14400 | 0 | 100%
Test Case | ICPIM-23416 | ICPIM-23410 Single CR - CR time related details | All |  | Rachna Muthanna | Jaimes Shonkwiler | Web Client | Pass | 2014-02-24 08:48 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-24619, ICPIM-19804, ICPIM-19791, ICPIM-19794, ICPIM-19798, ICPIM-19816, ICPIM-22476
Test Case | ICPIM-23415 | ICPIM-23308 Level layout 11- Module Class- Component -Regression Test Case. | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2014-02-21 15:50 | 7200 | 15300 | 0 | 100% | 7200 | 15300 | 0 | 100% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-22164, ICPIM-35235
Test Case | ICPIM-23414 | ICPIM-23308 Level layout 10- Panel Class- RACK Mounted Asset- Regression Test Case. | All |  | Thuy Tran | Rachna Muthanna | Web Client | Pass | 2014-02-21 14:43 | 10800 | 16500 | 0 | 100% | 10800 | 16500 | 0 | 100% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-24608, ICPIM-22164
Test Case | ICPIM-23411 | ICPIM-23410 Single CR - Update CR Titles and Descriptions | All |  | Rachna Muthanna | Jaimes Shonkwiler | Web Client | Pass | 2014-02-21 14:30 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-19801, ICPIM-19810, ICPIM-19927, ICPIM-24458, ICPIM-19807
Test Case | ICPIM-23409 | ICPIM-27477 imVision DEA scheduling sync interval or running on demand | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | New | 2014-02-21 14:00 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34230, ICPIM-34233
Test Case | ICPIM-23406 | ICPIM-23370 DEA Sync Collision Reconciliation - Location Collision - Ignore | All |  | Garrett S. | Garrett S. | Data Exchange Agent, UI/Data Content | New | 2014-02-21 13:23 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-23404 | ICPIM-23370 DEA Sync Collision Reconciliation - Location Collision - 3rd Party Location Scheduled to be Occupied in CPIM (not reconcilable) | All |  | Garrett S. | Garrett S. | Data Exchange Agent, UI/Data Content | New | 2014-02-21 11:26 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-23403 | ICPIM-23308 Level layout 9- Enclosure/ Cabinet -Floor Mounted Asset- Regression Test Case. | All |  | Thuy Tran | Rachna Muthanna | Web Client | Pass | 2014-02-21 11:14 | 10800 | 12000 | 0 | 100% | 10800 | 12000 | 0 | 100% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-24608, ICPIM-22164
Test Case | ICPIM-23401 | ICPIM-23370 DEA Sync Collision Reconciliation - Location Collision - 3rd Party Location Occupied in CPIM (not reconcilable) | All |  | Garrett S. | Garrett S. | Data Exchange Agent, UI/Data Content | New | 2014-02-21 11:05 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-23400 | ICPIM-23308 Level layout 8- ROW -Regression Test Case | All |  | Trinh Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-21 11:01 | 10800 | 26400 | 0 | 100% | 10800 | 26400 | 0 | 100% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-22164, ICPIM-35215
Test Case | ICPIM-23398 | ICPIM-22980 Change Request Details - View CR Status history details | All |  | Rachna Muthanna | Jaimes Shonkwiler | Web Client | Pass | 2014-02-21 10:54 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-23395 | ICPIM-23394 Task List View: work action details on hover | All |  | Rachna Muthanna | Jaimes Shonkwiler |  | Pass | 2014-02-21 10:17 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100% |  | ICPIM-24619
Test Case | ICPIM-23391 | ICPIM-23370 DEA Sync Collision Reconciliation - Location Collision - 3rd Party Location Exists (reconcilable) | All |  | Garrett S. | Garrett S. | Data Exchange Agent, UI/Data Content | New | 2014-02-21 09:41 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-23390 | ICPIM-39055 Associate Assets - Enhancing the Assets Assigned to CR lists capabilities | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-21 09:06 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-24537
Test Case | ICPIM-23386 | ICPIM-23308 Level layout 7- Room/POD Area -Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-20 16:00 | 10800 | 14700 | 0 | 100% | 10800 | 14700 | 0 | 100% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-22164, ICPIM-35215
Test Case | ICPIM-23385 | ICPIM-23370 DEA Sync Collision Reconciliation - Invalid Location | All |  | Garrett S. | Garrett S. | Data Exchange Agent, UI/Data Content | New | 2014-02-20 15:56 | 28800 | 32670 | 0 | 100% | 28800 | 32670 | 0 | 100%
Test Case | ICPIM-23384 | ICPIM-23308 Level layout 6- Zone/Data center- Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-20 15:52 | 10800 | 10200 | 600 | 94% | 10800 | 10200 | 600 | 94% |  | ICPIM-24320, ICPIM-22027, ICPIM-23837, ICPIM-23986, ICPIM-24323, ICPIM-22164, ICPIM-35215
Test Case | ICPIM-23383 | ICPIM-23308 Level layout 5- Floor -Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-20 15:46 | 10800 | 16500 | 0 | 100% | 10800 | 16500 | 0 | 100% |  | ICPIM-22027, ICPIM-23837, ICPIM-24323, ICPIM-22164, ICPIM-35215
Test Case | ICPIM-23382 | ICPIM-23410 Single CR - Interactive tool bar | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-20 15:14 | 5400 | 3600 | 1800 | 66% | 5400 | 3600 | 1800 | 66% |  | ICPIM-24557
Test Case | ICPIM-23380 | ICPIM-23308 Level layout 4- Building/ Grounds- Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Blocker | 2014-02-20 14:27 | 10800 | 11100 | 0 | 100% | 10800 | 11100 | 0 | 100% |  | ICPIM-35218, ICPIM-22027, ICPIM-23837, ICPIM-24323, ICPIM-22164
Test Case | ICPIM-23379 | ICPIM-23308 Level layout 3- Campus/ Site - Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Pass | 2014-02-20 14:19 | 10800 | 10200 | 600 | 94% | 10800 | 10200 | 600 | 94% |  | ICPIM-22027, ICPIM-23564, ICPIM-23567, ICPIM-23837, ICPIM-24323, ICPIM-22164
Test Case | ICPIM-23378 | ICPIM-23377 Web UI - Web Template: Loading the Web Browser pages | All |  | Raul Garcia | Loan Ha | Web Client | Pass | 2014-02-20 14:18 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0% |  | ICPIM-23308
Test Case | ICPIM-23376 | ICPIM-23308 Level layout 2- Region - Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-20 14:03 | 10800 | 10200 | 600 | 94% | 10800 | 10200 | 600 | 94% |  | ICPIM-22027, ICPIM-22590, ICPIM-23564, ICPIM-23567, ICPIM-23837, ICPIM-24323, ICPIM-22164, ICPIM-35209
Test Case | ICPIM-23375 | ICPIM-23308 Level layout 1- Organization- Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-20 13:42 | 10800 | 19200 | 0 | 100% | 10800 | 19200 | 0 | 100% |  | ICPIM-27759, ICPIM-22027, ICPIM-23564, ICPIM-23567, ICPIM-24323, ICPIM-24608, ICPIM-22164, ICPIM-35209
Test Case | ICPIM-23374 | ICPIM-22980 Change Request Details - CR pop-ups for Data (Title/Desc) | All |  | Thuy Tran | Loan Ha | Web Client | Pass | 2014-02-20 13:34 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-27935, ICPIM-24501, ICPIM-27957
Test Case | ICPIM-23372 | ICPIM-23410 Single CR - Display Work Action details | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-20 12:55 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-24517
Test Case | ICPIM-23369 | ICPIM-23363 JasperReports Leverage Analytics | All |  | Rachna Muthanna | Garrett S. | Data Model | Pass | 2014-02-20 11:52 | 86400 | 18000 | 68400 | 20% | 86400 | 18000 | 68400 | 20% |  | ICPIM-25035
Test Case | ICPIM-23368 | ICPIM-23367 Exporting Report Results - TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2014-02-20 11:19 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-23366 | ICPIM-23410 Single CR - View the assigned tasks | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-20 10:59 | 5400 | 2700 | 2700 | 50% | 5400 | 2700 | 2700 | 50%
Test Case | ICPIM-23362 | ICPIM-23361 Append CR name to TASK title –TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2014-02-20 09:38 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-24138
Test Case | ICPIM-23360 | ICPIM-27274 Commission - Set Destination: Navigating thru "Search Within" option | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2014-02-20 09:23 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-23357 | ICPIM-22980 Change Request Details - CR pop-ups for Time Status | All |  | Garrett S. | Garrett S. | Web Client | Pass | 2014-02-19 17:17 | 7200 | 900 | 6300 | 12% | 7200 | 900 | 6300 | 12%
Test Case | ICPIM-23326 | ICPIM-22980 Change Request Details - CR pop-ups for Work Actions | All |  | Garrett S. | Garrett S. | Web Client | Pass | 2014-02-19 16:02 | 7200 | 900 | 6300 | 12% | 7200 | 900 | 6300 | 12%
Test Case | ICPIM-23315 | ICPIM-23308 Search Results- Regression Test Case. | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Fail | 2014-02-19 14:35 | 3600 | 4200 | 0 | 100% | 3600 | 4200 | 0 | 100% |  | ICPIM-21452, ICPIM-27926
Test Case | ICPIM-23314 | ICPIM-22750 Parent child reporting | All |  | Tien Pham | Jaimes Shonkwiler | Web Client | In Progress | 2014-02-19 13:34 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-23313 | ICPIM-23308 Quick Search- Regression Test case | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Pass | 2014-02-19 11:14 | 3600 | 12000 | 0 | 100% | 3600 | 12000 | 0 | 100% |  | ICPIM-24560, ICPIM-27352, ICPIM-26706
Test Case | ICPIM-23309 | ICPIM-23308 Advanced Search - Regression Test case | All |  | Khang Nguyen | Rachna Muthanna | Web Client | Pass | 2014-02-19 10:32 | 7200 | 32700 | 0 | 100% | 7200 | 32700 | 0 | 100% |  | ICPIM-23672, ICPIM-23652, ICPIM-23678, ICPIM-23664, ICPIM-24294, ICPIM-24297, ICPIM-22506, ICPIM-26706
Test Case | ICPIM-23301 | ICPIM-27477 Manually map imVision properties to CPIM datastores | All |  | Garrett S. | Jaimes Shonkwiler |  | New | 2014-02-19 08:17 |  | 300 | 0 | 100% |  | 300 | 0 | 100% |  | ICPIM-24150, ICPIM-24676
Test Case | ICPIM-23292 | ICPIM-27477 imVision: New assets added to imVision show up in CPIM- T.C | All |  | Garrett S. | Rachna Muthanna | Windows Client | New | 2014-02-18 12:20 |  | 12900 | 0 | 100% |  | 12900 | 0 | 100% |  | ICPIM-24203, ICPIM-24227, ICPIM-24230, ICPIM-24249, ICPIM-24200, ICPIM-24240, ICPIM-24243, ICPIM-24312, ICPIM-24224
Test Case | ICPIM-23281 | ICPIM-23278 IPAD- Quick Search- Enter 2 Characters- TC | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Pass | 2014-02-18 10:20 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-23280 | ICPIM-23278 IPAD- Quick Search- Result Type- TC | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-18 10:16 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-23282
Test Case | ICPIM-23279 | ICPIM-23278 IPAD Quick Search- Location -TC | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-18 10:09 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-23282
Test Case | ICPIM-23232 | ICPIM-27477 Synch All imVision Assets | All |  | Garrett S. | Loan Ha | Windows Client | New | 2014-02-18 09:18 | 14400 | 18600 | 0 | 100% | 14400 | 18600 | 0 | 100% |  | ICPIM-24150, ICPIM-24950, ICPIM-24676
Test Case | ICPIM-23230 | ICPIM-23226 Windows 32 Client Help | All |  | Rachna Muthanna | Jaimes Shonkwiler | All | Pass | 2014-02-18 08:26 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-23229 | ICPIM-23226 Web Client Help | All |  | Rachna Muthanna | Jaimes Shonkwiler | All | Pass | 2014-02-18 08:15
Test Case | ICPIM-23228 | ICPIM-23226 Web Client | All |  | Rachna Muthanna | Jaimes Shonkwiler | All | Pass | 2014-02-18 08:05
Test Case | ICPIM-23227 | ICPIM-23226 Windows 32 client | All |  | Rachna Muthanna | Jaimes Shonkwiler | All | Pass | 2014-02-18 08:03
Test Case | ICPIM-23156 | ICPIM-21575 New CR Confirmation - Go to CR | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-17 15:31 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-23466
Test Case | ICPIM-23150 | ICPIM-23142 Web UI - Tooltips: Column Headers and Truncated Cells | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2014-02-17 14:39 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-23492
Test Case | ICPIM-23115 | ICPIM-23087 Tasks - Delegate Work - Interact with detailed information | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-17 13:40 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100%
Test Case | ICPIM-23063 | ICPIM-23039 IPAD- Viewing details of Individual Tasks – Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-17 11:03 | [9 empty] | ICPIM-23157, ICPIM-23170, ICPIM-23136, ICPIM-23144, ICPIM-23089, ICPIM-23092, ICPIM-23167
Test Case | ICPIM-23062 | ICPIM-23039 IPAD- Updating Individual Tasks – Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-17 11:02 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-23089, ICPIM-23147, ICPIM-23151
Test Case | ICPIM-23043 | ICPIM-23039 IPAD- Tasks : Actions page – Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-17 10:36 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100% |  | ICPIM-23088, ICPIM-23162
Test Case | ICPIM-23041 | ICPIM-23039 IPAD- Creating and viewing Tasks – Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-17 10:33 |  | 21600 | 0 | 100% |  | 21600 | 0 | 100% |  | ICPIM-23031, ICPIM-23128, ICPIM-23107, ICPIM-23131, ICPIM-23135
Test Case | ICPIM-23033 | ICPIM-23032 Tasks - Authorize CR - Interact with detailed information | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2014-02-17 10:00 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100% |  | ICPIM-24467, ICPIM-24470, ICPIM-24476
Test Case | ICPIM-23028 | ICPIM-23026 IPAD- Mapping and Scanning Barcodes –Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-02-17 09:24 |  | 18000 | 0 | 100% |  | 18000 | 0 | 100% |  | ICPIM-23120, ICPIM-23128, ICPIM-23112, ICPIM-23176, ICPIM-23116
Test Case | ICPIM-23027 | ICPIM-23025 Tasks - Verify CR - Interact with detailed information | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2014-02-17 09:24 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-24467, ICPIM-24470, ICPIM-24476, ICPIM-24464
Test Case | ICPIM-23024 | ICPIM-22999 Editable vs Read only Properties |  |  | Garrett S. | Jaimes Shonkwiler |  | Invalid | 2014-02-17 09:03 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-23017 | ICPIM-20189 Tasks - Execute Work - Interact with detailed information | All |  | An Vo | Loan Ha | Web Client | Pass | 2014-02-17 08:44 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-21354, ICPIM-24490, ICPIM-24495
Test Case | ICPIM-23001 | ICPIM-22999 Properties datastores are searchable |  |  | Loan Ha | Jaimes Shonkwiler |  | Pass | 2014-02-14 15:19 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-24597
Test Case | ICPIM-23000 | ICPIM-22999 Datastores in Properties flyout (Web Client) |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-14 15:16 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100%
Test Case | ICPIM-22990 | ICPIM-22989 New Change Request - CR Title | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-14 13:38 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-22988 | ICPIM-22982 Verify Master license file is updated | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-14 12:44 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-22987 | ICPIM-22982 Equipment Class WS Support for Schemes | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-14 12:40 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-22986 | ICPIM-22982 Equipment Class WS Support for Subclass | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-14 12:39 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-22985 | ICPIM-22982 Asset Management WS Subclass Support | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-14 12:23 | 5400 | 9600 | 0 | 100% | 5400 | 9600 | 0 | 100% |  | ICPIM-24188, ICPIM-24185
Test Case | ICPIM-22984 | ICPIM-22983 Tasks - Filter by Line of Business | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-14 10:59 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-22981 | ICPIM-22980 Change Request Details - View CR Details | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2014-02-14 09:45 | 3600 | 6300 | 0 | 100% | 3600 | 6300 | 0 | 100% |  | ICPIM-24138, ICPIM-24476, ICPIM-19860
Test Case | ICPIM-22979 | ICPIM-27348 Filter CRs by CR Types and Status | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-13 15:39 | 3600 | 4500 | 0 | 100% | 3600 | 4500 | 0 | 100% |  | ICPIM-24138
Test Case | ICPIM-22974 | ICPIM-23087 Tasks - Delegate Work - Display the number of tasks assigned to the team/user | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2014-02-13 13:27 | 3600 | 9000 | 0 | 100% | 3600 | 9000 | 0 | 100% |  | ICPIM-23499, ICPIM-23505
Test Case | ICPIM-22972 | ICPIM-18689 Temperature alarm is triggered via Intel DCM WILLOW | All |  | Garrett S. | Jaimes Shonkwiler | All | Fail | 2014-02-13 13:05 |  | 18000 | 0 | 100% |  | 18000 | 0 | 100% |  | ICPIM-34431, ICPIM-27443, ICPIM-23887
Test Case | ICPIM-22971 | ICPIM-22956 Visual Search by Power options (TBD) | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-13 11:08 |  | 3300 | 0 | 100% |  | 3300 | 0 | 100%
Test Case | ICPIM-22958 | ICPIM-22956 Find syscat datastore (number of power input port connections specified) | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-13 10:32 |  | 5700 | 0 | 100% |  | 5700 | 0 | 100%
Test Case | ICPIM-22957 | ICPIM-22956 Find syscat report (number of power input port connections specified) | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2014-02-13 10:32 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-22953 | ICPIM-22952 Quick Search for CRs | All |  | Rachna Muthanna | Jaimes Shonkwiler | Web Client | Pass | 2014-02-13 09:58 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-22951 | ICPIM-28722 Ensure RF Code Temperature Data Triggers CPIM Alarm Manager Alarm | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-02-13 09:09 |  | 21600 | 0 | 100% |  | 21600 | 0 | 100% |  | ICPIM-24673, ICPIM-24832, ICPIM-26012
Test Case | ICPIM-22760 | ICPIM-22750 Email Jaspersoft Reports | All |  | Vinh Nguyen | Jaimes Shonkwiler | Web Client | Fail | 2014-02-04 07:45 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-34791, ICPIM-35031
Test Case | ICPIM-22759 | ICPIM-22750 Jaspersoft Help (should be CPIM-specific and not Jaspersoft's default help file) | All |  | Vinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:43 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-22758 | ICPIM-22750 Seeded Jaspersoft report | All |  | Mai Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:41 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-34791
Test Case | ICPIM-22757 | ICPIM-22750 Jaspersoft "iTRACS Reports" available in report selection list | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:40 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100%
Test Case | ICPIM-22756 | ICPIM-22750 Create simple Jaspersoft report using analytics (Jaspersoft portal) | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:39 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-22755 | ICPIM-22750 Create Ad Hoc View (Jaspersoft portal) | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:39 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-22754 | ICPIM-22750 Analytics data available for report creation | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Fail | 2014-02-04 07:39 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34768
Test Case | ICPIM-22753 | ICPIM-22750 Default DataSource and Domain provided on installation | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:37 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-22751 | ICPIM-22750 Install and Configure Jaspersoft | All |  | Trinh Nguyen | Jaimes Shonkwiler | Web Client | Pass | 2014-02-04 07:36 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-24182, ICPIM-24391
Test Case | ICPIM-22719 | ICPIM-22718 Add iPAD Help Files to Installer - TC | All |  | Rachna Muthanna | Rachna Muthanna | Mobile Client | Fail | 2014-01-31 13:49 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-23233, ICPIM-23236, ICPIM-23239, ICPIM-23243, ICPIM-23246, ICPIM-23249, ICPIM-23252, ICPIM-23256, ICPIM-23259, ICPIM-23262, ICPIM-23265, ICPIM-23272, ICPIM-23275
Test Case | ICPIM-22704 | ICPIM-22703 Filter Jasper Report using seed item |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | Fail | 2014-01-31 08:07
Test Case | ICPIM-22589 | ICPIM-18689 Populate Intel DCM with devices and data via the local network (UPDATE FOR USING SIMULATOR) | All |  | Garrett S. | Jaimes Shonkwiler | All | Pass | 2014-01-28 09:50 |  | 6000 | 0 | 100% |  | 6000 | 0 | 100%
Test Case | ICPIM-22588 | ICPIM-18689 Mapped attribute data is copied to CPIM datastores | All |  | Garrett S. | Jaimes Shonkwiler | All | Pass | 2014-01-28 09:44 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100%
Test Case | ICPIM-22561 | ICPIM-21946 Re-test ICPIM-16190 | All |  | Melissa C. | Melissa C. |  | Pass | 2014-01-27 14:00
Test Case | ICPIM-22560 | ICPIM-21946 Re-test ICPIM-16188 | All |  | Melissa C. | Melissa C. |  | Pass | 2014-01-27 13:58
Test Case | ICPIM-22518 | ICPIM-21946 Re-Test ICPIM-20432 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Fail | 2014-01-23 16:35 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-22517 | ICPIM-21946 Re-Test ICPIM-20861 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2014-01-23 16:30 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-22516 | ICPIM-21946 Re-Test ICPIM-15563 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Fail | 2014-01-23 16:29 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-22515 | ICPIM-21946 Re-Test ICPIM-20860 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2014-01-23 16:28 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-22514 | ICPIM-21946 Re-Test ICPIM-20850 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2014-01-23 16:26 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100%
Test Case | ICPIM-22431 | ICPIM-19329 add liebert sitescan to installer | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | All | Pass | 2014-01-22 13:36 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-22419 | ICPIM-14058 PDU breaker - available row power (enclosure search) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2014-01-22 12:25
Test Case | ICPIM-22418 | ICPIM-14058 PDU breaker -available row power (loose gear) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2014-01-22 12:25
Test Case | ICPIM-22416 | ICPIM-14058 switch port count accuracy | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2014-01-22 12:23
Test Case | ICPIM-22415 | ICPIM-14058 bootbox count accuracy | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2014-01-22 12:23
Test Case | ICPIM-22384 | ICPIM-22383 KPMG- Multi- Connector Test Case. | All |  | Trinh Nguyen | Rachna Muthanna | Windows Client | Fail | 2014-01-21 10:07 | 10800 | 10800 | 0 | 100% | 10800 | 10800 | 0 | 100% |  | ICPIM-22341
Test Case | ICPIM-22273 | ICPIM-22038 Liebert SiteScan Licensing | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-17 07:34 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-22274
Test Case | ICPIM-22272 | ICPIM-22038 Mapped attribute to datastore data is updated when change occurs within Liebert SiteScan | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-17 07:27 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-22046 | ICPIM-22038 Map Devices (Auto Mapping) | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100%
Test Case | ICPIM-22045 | ICPIM-22038 Map Devices (Manual Mapping) | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 8100 | 0 | 100% |  | 8100 | 0 | 100%
Test Case | ICPIM-22044 | ICPIM-22038 Liebert SiteScan Attributes shall be polled at every DEA instance start up or reset | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-22041 | ICPIM-22038 Log created for Liebert SiteScan | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 2100 | 0 | 100% |  | 2100 | 0 | 100%
Test Case | ICPIM-22040 | ICPIM-22038 Liebert SiteScan: Configure DEA and Instance Connectivity Verification | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 21600 | 0 | 100% |  | 21600 | 0 | 100% |  | ICPIM-34477
Test Case | ICPIM-22039 | ICPIM-22038 Liebert SiteScan Installer | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2014-01-10 10:26 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-22190
Test Case | ICPIM-21869 | ICPIM-21868 Access Jaspersoft Management interface via iTRACS web UI myDCIM page | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2014-01-02 14:31 | 3600 | 3300 | 300 | 91% | 3600 | 3300 | 300 | 91% |  | ICPIM-21870
Test Case | ICPIM-21861 | ICPIM-21860 Windows Client: Change Control Tab Changes | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2013-12-27 11:30 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100% |  | ICPIM-24217, ICPIM-24221
Test Case | ICPIM-21859 | ICPIM-27431 Test Case: ICPIM-21526 | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-12-27 11:09 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-21845 | ICPIM-21844 Change Management - Repurpose CR: Work Flow | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-12-26 12:08 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-21888
Test Case | ICPIM-21840 | ICPIM-20040 View Work Action - Edit Work Action | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-12-26 08:24 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-21849, ICPIM-21893, ICPIM-21947
Test Case | ICPIM-21831 | ICPIM-21827 Change Management - Move CR: Work Flow | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-12-20 10:14 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-21803, ICPIM-21972
Test Case | ICPIM-21622 | ICPIM-21620 Commission - Recommission | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-11-27 13:55 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-21619 | ICPIM-23410 Single CR - Work Action First Viewed Date | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-11-27 13:51 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-21063, ICPIM-21623
Test Case | ICPIM-21614 | ICPIM-14714 Portfolio - Advanced Search: Add Search Filter dialog | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-11-27 13:00 | 7200 | 12000 | 0 | 100% | 7200 | 12000 | 0 | 100% |  | ICPIM-21560, ICPIM-21551, ICPIM-21615
Test Case | ICPIM-21578 | ICPIM-21575 New CR Confirmation - Master Request Number and Secondary Request Number | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-11-27 11:15 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-21577 | ICPIM-21576 Test Case: ICPIM-21092 | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-27 11:10 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-21547 | ICPIM-14642 Connection Context Menu (Type) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-11-25 15:35 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-21546 | ICPIM-14642 Connection Context Menu (View Connections) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-11-25 14:46 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-21545 | ICPIM-14642 Connection Context Menu TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-11-25 13:32 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-21544 | ICPIM-14642 Multiselection Options (Paste, Zoom Selected, Anchor Selected, Unpaste) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-11-25 13:08 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100%
Test Case | ICPIM-21543 | ICPIM-14642 Multiselection Options (Copy Format) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-11-25 12:39 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100%
Test Case | ICPIM-21279 | ICPIM-39055 Associate Assets - Pop up Search dialog automatically when navigating to Asset Allocation page | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-06 14:37 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-21276 | ICPIM-24735 Change Management - Status: In progress | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-11-06 14:32 |  | 6600 | 0 | 100% |  | 6600 | 0 | 100%
Test Case | ICPIM-21274 | ICPIM-39055 Associate Assets - Return Search Result | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-06 14:18 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-21270 | ICPIM-23410 Single CR - Navigate back to Changes tab | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-06 13:57 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100%
Test Case | ICPIM-21267 | ICPIM-21266 Cancel Change Request - Force Comment | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-06 13:29 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100%
Test Case | ICPIM-21217 | ICPIM-21185 Commissioning Creates Too Many Move Work Actions- TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-11-05 15:16 | 14400 | 14400 | 0 | 100% | 14400 | 14400 | 0 | 100%
Test Case | ICPIM-21209 | ICPIM-23410 Single CR - Actual Start Date, End Date | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-11-05 14:48 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75%
Test Case | ICPIM-21203 | ICPIM-19994 MyDCIM - Tasks - Modify Task Display | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-11-05 14:21 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-21200 | ICPIM-22980 Change Requests Details - Title Bar | All |  | An Vo | Rachna Muthanna | Web Client | Pass | 2013-11-05 13:50 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-21197 | ICPIM-21195 Task Management - My Tasks: Include CR link on the task list | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-11-05 13:44 | 21600 | 7800 | 13800 | 36% | 21600 | 7800 | 13800 | 36%
Test Case | ICPIM-21191 | ICPIM-21180 Test Case: ICPIM-21067 | All |  | Garrett S. | Loan Ha | Web Client | New | 2013-11-05 13:09 | [9 empty] | ICPIM-21067
Test Case | ICPIM-21190 | ICPIM-16022 Test Case: ICPIM-20913 | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-05 13:08 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-21189 | ICPIM-23050 Tasks - Schedule CR: Read only mode | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-11-05 13:07 | 3600 | 6600 | 0 | 100% | 3600 | 6600 | 0 | 100%
Test Case | ICPIM-21188 | ICPIM-21172 Test Case: ICPIM-21096 | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-11-05 13:06 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-21181 | ICPIM-12696 Maintenance: Split AssetChangeManagementAPI:containertypes.hpp-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-11-05 10:44 | 21600 | 7200 | 14400 | 33% | 21600 | 7200 | 14400 | 33% |  | ICPIM-21509, ICPIM-21512
Test Case | ICPIM-21173 | ICPIM-12696 Maintenance: Complete changes for new table (IMGENERICTYPEMAP)- TC |  |  | Garrett S. | Rachna Muthanna |  | Invalid | 2013-11-05 10:30
Test Case | ICPIM-20977 | ICPIM-17107 Verify OpsdbProxyService CPU usage upon full sync completion | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Service | New | 2013-10-30 08:54
Test Case | ICPIM-20976 | ICPIM-17107 Sync transactions queue when web service communication with CPIM is down | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Service | New | 2013-10-30 08:41
Test Case | ICPIM-20917 | ICPIM-20916 Hide Work Generated from Web within Windows Change Control Interface- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-10-28 15:08 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-20923
Test Case | ICPIM-20895 | ICPIM-13471 DEA windows services are removed upon uninstall (Placeholder) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-10-26 16:36
Test Case | ICPIM-20767 | ICPIM-40305 Web UI - Direct URL: Saved State | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-10-25 12:56 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-20577 | ICPIM-23050 Tasks - Schedule CR: Work Flow | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-10-22 10:43 | 10800 | 11700 | 0 | 100% | 10800 | 11700 | 0 | 100%
Test Case | ICPIM-20576 | ICPIM-20574 RESTful API provides service to retrieve itservices information |  |  | Garrett S. | Garrett S. |  | New | 2013-10-22 10:41 | 14400 |  | 14400 | 0% | 14400 |  | 14400 | 0%
Test Case | ICPIM-20575 | ICPIM-20574 AssetChangeManagment includes method for itservices information. |  |  | Garrett S. | Garrett S. |  | New | 2013-10-22 10:39 | 14400 |  | 14400 | 0% | 14400 |  | 14400 | 0%
Test Case | ICPIM-20567 | ICPIM-23142 Web UI - Tooltips: For Web Client | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-10-22 09:23 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-21981, ICPIM-22031
Test Case | ICPIM-20494 | ICPIM-19471 Add roots UserProfile using special characters soapUI | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-10-17 15:45 | 1800 | 2400 | 0 | 100% | 1800 | 2400 | 0 | 100% |  | ICPIM-20499
Test Case | ICPIM-20439 | ICPIM-19180 Add Asset ChangeManagement using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Fail | 2013-10-16 18:03 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-20482
Test Case | ICPIM-20436 | ICPIM-19180 Update Asset ChangeManagement using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-10-16 17:59 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-20428 | ICPIM-20418 AssetChangeManagementWS: Work Project Commission | All |  | Loan Ha | Loan Ha | Web Service | Pass | 2013-10-16 13:00 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-20399 | ICPIM-20392 Email reports that have been completed and ran in Jaspersoft | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Fail | 2013-10-15 15:57 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-20193 | ICPIM-40024 Task Management - Resolve Work Action Flow | All |  | An Vo | Melissa C. | Web Client | Fail | 2013-10-05 14:30 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-20192 | ICPIM-20047 Task Management - Verify Work Action Flow | All |  | An Vo | Melissa C. | Web Client | Fail | 2013-10-05 14:27 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-20191 | ICPIM-20047 Task Management - Verify Work Action - Interact with detailed information | All |  | An Vo | Melissa C. | Web Client | Fail | 2013-10-05 14:25 | 1800 | 5400 | 0 | 100% | 1800 | 5400 | 0 | 100% |  | ICPIM-21340
Test Case | ICPIM-20190 | ICPIM-20189 Task Management - Execute Work Flow | All |  | An Vo | Melissa C. | Web Client | Fail | 2013-10-05 14:17 | 1800 | 5400 | 0 | 100% | 1800 | 5400 | 0 | 100% |  | ICPIM-21494, ICPIM-21500, ICPIM-21480, ICPIM-21483, ICPIM-21488, ICPIM-21497
Test Case | ICPIM-20188 | ICPIM-20183 Change Management - Complete CR: Notify Requester | All |  | Loan Ha | Melissa C. | Web Client | Pass | 2013-10-05 14:01 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-20187 | ICPIM-20183 Change Management - Complete CR: Analytics Updated | All |  | Loan Ha | Melissa C. | Web Client | Fail | 2013-10-05 13:58 | 10800 | 18000 | 0 | 100% | 10800 | 18000 | 0 | 100% |  | ICPIM-22278
Test Case | ICPIM-20186 | ICPIM-20183 Change Management - Complete CR: Closing Work Actions | All |  | Loan Ha | Melissa C. | Web Client | Pass | 2013-10-05 13:54 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100% |  | ICPIM-21347
Test Case | ICPIM-20185 | ICPIM-20183 Change Management - Complete CR: Closing Work Projects | All |  | Loan Ha | Melissa C. | Web Client | Pass | 2013-10-05 13:51 | 3600 | 4500 | 0 | 100% | 3600 | 4500 | 0 | 100%
Test Case | ICPIM-20184 | ICPIM-20183 Change Management - Complete CR: Closing a Change Request | All |  | Loan Ha | Melissa C. | Web Client | Pass | 2013-10-05 13:46 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-20123 | ICPIM-20121 User can set power capping policy in CPIM database and this will be propagated to Intel DCM Manager | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-10-03 17:53 | 14400 |  | 14400 | 0% | 14400 |  | 14400 | 0%
Test Case | ICPIM-20122 | ICPIM-20121 Intel DCM DEA can retrieve power capping data from Intel DCM manager | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-10-03 17:52 | 7200 |  | 7200 | 0% | 7200 |  | 7200 | 0%
Test Case | ICPIM-20116 | ICPIM-20115 Execute Jaspersoft report in Web UI | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Client | Pass | 2013-10-03 17:38 | 3600 | 2700 | 900 | 75% | 3600 | 2700 | 900 | 75%
Test Case | ICPIM-20112 | ICPIM-20111 Email / Share Jaspersoft report via Web UI P3M1 version |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Client | Pass | 2013-10-03 17:30 |  | 5400 | 0 | 100% |  | 5400 | 0 | 100%
Test Case | ICPIM-20108 | ICPIM-20107 View Jaspersoft report in Web UI report list | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Client | Pass | 2013-10-03 17:19 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-20105 | ICPIM-38701 Portfolio - Graphical List: Google Maps Configurable Key | All |  | Tien Pham | Rachna Muthanna |  | Pass | 2013-10-03 15:05 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100% |  | ICPIM-20660
Test Case | ICPIM-20079 | ICPIM-40305 Web UI - Direct URL: Messages text | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-10-02 16:20 | 7200 | 12300 | 0 | 100% | 7200 | 12300 | 0 | 100%
Test Case | ICPIM-20076 | ICPIM-22980 Change Request Details - Ghost Bar | All |  | An Vo | Rachna Muthanna | Web Client | Fail | 2013-10-02 15:47 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-22031
Test Case | ICPIM-20060 | ICPIM-20059 Connect- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-10-02 10:17 | 21600 | 14400 | 7200 | 66% | 21600 | 14400 | 7200 | 66%
Test Case | ICPIM-20048 | ICPIM-20047 Task Management - Verify Work Action: Technician Manager | All |  | Tien Pham | Loan Ha | Web Client | Fail | 2013-10-01 15:10 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-20857, ICPIM-20865, ICPIM-22142
Test Case | ICPIM-20046 | ICPIM-23087 Delegate Work - Delegate Work Action by Tech Manager | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-10-01 15:08 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-20822, ICPIM-20882, ICPIM-20879
Test Case | ICPIM-20041 | ICPIM-20040 View Work Action - View General Information | All |  | An Vo | Loan Ha | Web Client | Pass | 2013-10-01 15:06 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-20835, ICPIM-20838, ICPIM-20842, ICPIM-20847, ICPIM-20853
Test Case | ICPIM-20005 | ICPIM-20004 myDCIM - Branding (Update customer's logo) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-27 13:15 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75%
Test Case | ICPIM-20003 | ICPIM-20002 myDCIM - Searches | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-27 13:12 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100% |  | ICPIM-20601, ICPIM-20604
Test Case | ICPIM-20000 | ICPIM-19999 myDCIM - Reports | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-27 13:06 |  | 8400 | 0 | 100% |  | 8400 | 0 | 100% |  | ICPIM-20584, ICPIM-20623, ICPIM-20626
Test Case | ICPIM-19998 | ICPIM-19997 myDCIM - Change Requests | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-27 13:04 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100%
Test Case | ICPIM-19996 | ICPIM-19994 myDCIM - Tasks | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-27 11:46 | 10800 | 5400 | 5400 | 50% | 10800 | 5400 | 5400 | 50% |  | ICPIM-20619
Test Case | ICPIM-19995 | ICPIM-18259 Submit a task via PHP |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-09-27 11:24 | 7200 | 2400 | 4800 | 33% | 7200 | 2400 | 4800 | 33%
Test Case | ICPIM-19992 | ICPIM-23087 Tasks - Delegate Work - Reassign tasks | All |  | An Vo | Loan Ha | Web Client | Fail | 2013-09-27 10:23 | 10800 | 14400 | 0 | 100% | 10800 | 14400 | 0 | 100% |  | ICPIM-20771, ICPIM-20822, ICPIM-21940, ICPIM-20778, ICPIM-20787, ICPIM-20798, ICPIM-20807, ICPIM-22057
Test Case | ICPIM-19776 | ICPIM-19180 Ensure values are stored in the database as their escaped values, not the raw character. | All |  | Garrett S. | Garrett S. | PHP, Web Service | Pass | 2013-09-23 09:54
Test Case | ICPIM-19730 | ICPIM-19725 ASPLC-06 User can place module within asset at set location- TC |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-20 11:25 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-19716 | ICPIM-19714 ASPLC-05 User can place module within asset at any location-TC |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-20 10:11 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-19715 | ICPIM-18165 User will have some form of admin access to Jaspersoft admin menu within web client | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Fail | 2013-09-20 10:09 | 10800 | 1800 | 9000 | 16% | 10800 | 1800 | 9000 | 16% |  | ICPIM-20841
Test Case | ICPIM-19696 | ICPIM-18165 Schedule Report (backend) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-09-20 08:41 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19694 | ICPIM-18165 Delete Report (backend) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-09-20 08:35 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19540 | ICPIM-19537 TaskManagementWS queries will return ISO date format | All |  | Garrett S. | Jaimes Shonkwiler | PHP | Pass | 2013-09-17 09:24 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19539 | ICPIM-19537 AssetChangeManagementWS queries will return ISO date format | All |  | Garrett S. | Jaimes Shonkwiler | PHP | Pass | 2013-09-17 09:23 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-19538 | ICPIM-19537 ReportingWS queries will return ISO date format | All |  | Garrett S. | Jaimes Shonkwiler | PHP | Pass | 2013-09-17 09:22 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-19523 | ICPIM-19521 Get ViewStates via VisualizationWS using special characters (PHP) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 16:05 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19522 | ICPIM-19521 Query View States via VisualizationWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 16:05 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-19508 | ICPIM-19503 ASPLC-04 User can place an Asset within an Enclosure at set position- TC |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-16 15:27 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-19509
Test Case | ICPIM-19507 | ICPIM-19504 Get Roles via RoleManagementWS using special characters (PHP) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 15:26 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19506 | ICPIM-19504 Get Roles via RoleManagementWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 15:26 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19505 | ICPIM-19504 Add Role via RoleManagementWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 15:26 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19501 | ICPIM-19500 ASPLC-03 User can place an Asset in an Enclosure at any location-TC |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-16 15:19 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-19499 | ICPIM-19498 ASPLC-02 User can place an Enclosure with a Row at set location-TC |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-16 15:13 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-19497 | ICPIM-19495 QueryCompleteReports via ReportingWS using special characters (PHP) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 15:00 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19496 | ICPIM-19495 QueryCompleteReports via ReportingWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 15:00 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19494 | ICPIM-19491 Query Notification via NotificationWS using special characters (PHP) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 14:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19493 | ICPIM-19491 Query Notification via NotificationWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 14:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19492 | ICPIM-19491 Add notification via NotificationWS using special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 14:48 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19490 | ICPIM-19488 Get Mapview MapviewWS using special characters PHP | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:35 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19489 | ICPIM-19488 Get Mapview MapviewWS using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:35 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19487 | ICPIM-19484 Query Manufacturer TemplateWS using special characters PHP | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 14:27 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19485 | ICPIM-19484 Query Manufacturer TemplateWS using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-16 14:27 | 1800 | 5400 | 0 | 100% | 1800 | 5400 | 0 | 100%
Test Case | ICPIM-19482 | ICPIM-19480 Query devices VirtualMachine using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:18 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-19481 | ICPIM-19480 Create Devices VirtualMachine using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:18 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100%
Test Case | ICPIM-19479 | ICPIM-19477 Test Case: ICPIM-19079 | All |  | Loan Ha | Loan Ha | Web Service | Pass | 2013-09-16 14:08 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100% |  | ICPIM-19544, AUTO-186
Test Case | ICPIM-19478 | ICPIM-19471 Query favorite UserProfile using special characters REST | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:07 | 1800 | 2160 | 0 | 100% | 1800 | 2160 | 0 | 100%
Test Case | ICPIM-19473 | ICPIM-19471 Add favorite UserProfile using special characters REST | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 14:01 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-19466 | ICPIM-19462 Query Asset Management using special characters PHP | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 13:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19464 | ICPIM-19462 Query Asset Management using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 13:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19463 | ICPIM-19462 Add Asset Management using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-16 13:12 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19387 | ICPIM-14642 Multiselection Options (Auto-Space Selected) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 16:28 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19386 | ICPIM-14642 Multiselection Options (Align Selected) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 16:01 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19385 | ICPIM-14642 Main Menu (Print) TC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 15:13 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-19384 | ICPIM-14642 Main Menu (Save For Class, Create From Class) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-10 14:36 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-19383 | ICPIM-14642 Main Menu (Anchor All Items, Unanchor All Items, Unanchor Item) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-10 14:09 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19382 | ICPIM-14642 Main Menu (Update Connections, Reload Dashboard, Paste) TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 13:27 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19381 | ICPIM-14642 Main Menu (Back) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-10 12:44 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-19380 | ICPIM-14642 Settings - Information TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 11:16 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19379 | ICPIM-14642 Settings - Interface TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-09-10 10:40 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19378 | ICPIM-14642 Settings - Performance TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-10 10:25 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-19375 | ICPIM-14642 Settings - Background (Gradient) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-10 08:35 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-19371 | ICPIM-14642 Settings - Background (None, Solid) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-09 15:27 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-19370 | ICPIM-14642 New (Line, Box, Ellipse, Poly Line) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-09 15:21 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19369 | ICPIM-19365 Test case: Configure Work Project DeCommission- Work Project CR-30 (17392 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-09 15:21
Test Case | ICPIM-19368 | ICPIM-19365 Test case: Configure Work Project DeCommission- Policies CR-30 (17392 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-09-09 15:19
Test Case | ICPIM-19367 | ICPIM-19365 Test case: Configure Work Project DeCommission- Destination & Time CR-30 (17392 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-09 15:16 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100%
Test Case | ICPIM-19366 | ICPIM-19365 Test case: Configure Work Project DeCommission- Remove/Move CR-30 (17392 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-09 15:14 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-19364 | ICPIM-14642 New (Text, Bitmap) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-09 14:11 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19360 | ICPIM-14642 Zoom (In, Out) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-09 13:57 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-19359 | ICPIM-14642 Thick Client: Dashboard Item Delete Tests | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-09-09 13:35 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-33574
Test Case | ICPIM-19346 | ICPIM-19345 ASPLC-01: Place an Enclosure within a Row (No Pads) |  |  | Rachna Muthanna | Rachna Muthanna | Web Service | Pass | 2013-09-06 15:24 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-19336 | ICPIM-19332 Query task via taskManagement using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-06 11:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19335 | ICPIM-19332 Add task via taskManagement using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-06 11:42 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-19334 | ICPIM-19332 Query task via taskManagement with special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-06 11:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19333 | ICPIM-19332 Add task via taskManagement using special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-06 11:42 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19331 | ICPIM-19329 Add Jaspersoft msi to CPIM installer | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | All | Pass | 2013-09-06 10:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19330 | ICPIM-19329 Update Intel DCM to version 3.5 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | All | Pass | 2013-09-06 10:54 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19328 | ICPIM-13471 Intel DCM installer updated to version 3.5 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Invalid | 2013-09-06 10:51
Test Case | ICPIM-19327 | ICPIM-13471 Jaspersoft Component added to Installer | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Invalid | 2013-09-06 10:45
Test Case | ICPIM-19323 | ICPIM-19317 Logout via Authentication using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Fail | 2013-09-06 09:38 | 1800 | 630 | 1170 | 35% | 1800 | 630 | 1170 | 35% |  | ICPIM-20404
Test Case | ICPIM-19322 | ICPIM-19317 Logout via Authenication using special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-06 09:26 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19320 | ICPIM-19317 Login via Authentication using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Fail | 2013-09-06 08:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-20404
Test Case | ICPIM-19318 | ICPIM-19317 Login via Authenication using special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Fail | 2013-09-06 08:56 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19316 | ICPIM-19312 Query User via UserManagementWS using special characters PHP | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-06 08:44 | 1800 |  | 1800 | 0% | 1800 |  | 1800 | 0%
Test Case | ICPIM-19314 | ICPIM-19312 Query User via UserManagement for special characters (Web Services) | All |  | Garrett S. | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-06 08:44 | 1800 | 3600 | 0 | 100% | 1800 | 3600 | 0 | 100%
Test Case | ICPIM-19309 | ICPIM-19278 Update via ChangeManagement using special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-05 16:02 | 1800 | 2700 | 0 | 100% | 1800 | 2700 | 0 | 100%
Test Case | ICPIM-19308 | ICPIM-19278 Add " " via ChangeManagementWS using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-05 15:49 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19307 | ICPIM-19294 Test case: Configure Work Project Commission- Submit the WP for Commissioning CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 15:43 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-19306 | ICPIM-19278 Query " " via ChangeManagementWS using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-09-05 15:41 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19305 | ICPIM-19294 Test case: Configure Work Project Commission- Network Setting CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-09-05 15:41 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-20951, ICPIM-21660
Test Case | ICPIM-19304 | ICPIM-19294 Test case: Configure Work Project Commission- Power Connectivity Setting CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 15:39 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-20948
Test Case | ICPIM-19301 | ICPIM-19294 Test case: Configure Work Project Commission- Spatial Setting CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 15:36 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-20944
Test Case | ICPIM-19300 | ICPIM-19294 Test case: Configure Work Project Commission- Change Location CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-09-05 15:34 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-21981
Test Case | ICPIM-19299 | ICPIM-19180 Add Asset ChangeManagement using special characters Web Services | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | Invalid | 2013-09-05 15:34 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19295 | ICPIM-19294 Test case: Configure Work Project Commission- Set Location CR-29 (17391 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 15:15 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-19280 | ICPIM-19278 Query via ChangeManagement for special characters (Web Services) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-05 13:28 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19276 | ICPIM-19275 Test Case: WM-06 (18638) | All |  | Loan Ha | Loan Ha | PHP | Pass | 2013-09-05 12:48 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-20771
Test Case | ICPIM-19271 | ICPIM-23087 Delegate Work - Delegate Work Actions by Administrator | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-09-05 11:12 | 14400 | 15600 | 0 | 100% | 14400 | 15600 | 0 | 100% |  | ICPIM-20771, ICPIM-21940, ICPIM-20778, ICPIM-20787, ICPIM-22057
Test Case | ICPIM-19265 | ICPIM-19264 View Work Action - Edit Work Action (Back End) | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-09-05 11:03 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-20842, ICPIM-20856, ICPIM-22017
Test Case | ICPIM-19262 | ICPIM-19259 View Work Action (Back End) | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-09-05 10:56 | 14400 | 14400 | 0 | 100% | 14400 | 14400 | 0 | 100% |  | ICPIM-20835, ICPIM-20838, ICPIM-20842, ICPIM-20856
Test Case | ICPIM-19261 | ICPIM-19251 Test case: Search for location-Server to set locations against the Work Project CR-28 (17390 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 10:53 | 7200 | 1800 | 5400 | 25% | 7200 | 1800 | 5400 | 25%
Test Case | ICPIM-19260 | ICPIM-19251 Test case: Search for location-Server Results - CR-28 (17390 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Invalid | 2013-09-05 10:52 | 10800 |  | 10800 | 0% | 10800 |  | 10800 | 0%
Test Case | ICPIM-19258 | ICPIM-19251 Test case: Search for location-LOB; Datastore Filters - CR-28 (17390 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 10:50 | 7200 | 3600 | 3600 | 50% | 7200 | 3600 | 3600 | 50%
Test Case | ICPIM-19257 | ICPIM-19251 Test case: Search for location -Resource Requirements CR-28 (17390 ) | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-09-05 10:49 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25%
Test Case | ICPIM-19252 | ICPIM-23410 Single CR - Comment | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-09-05 10:38 | 10800 | 5400 | 5400 | 50% | 10800 | 5400 | 5400 | 50% |  | ICPIM-19909, ICPIM-19813
Test Case | ICPIM-19248 | ICPIM-39836 Change Management - Install CR: Complete an Install CR Schedule task | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-09-05 10:29 |  | 4800 | 0 | 100% |  | 4800 | 0 | 100%
Test Case | ICPIM-19213 | ICPIM-19180 Query Asset ChangeManagement using special characters Web Services | All |  | Garrett S. | Jaimes Shonkwiler | Web Service | Pass | 2013-09-04 15:30 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-19218
Test Case | ICPIM-19181 | ICPIM-19180 Query Asset ChangeManagement using special characters PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Pass | 2013-09-03 15:41 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-19033 | ICPIM-21266 Cancel Change Request - Status Update and Notification | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-27 13:37 | 14400 | 16200 | 0 | 100% | 14400 | 16200 | 0 | 100% |  | ICPIM-19930, ICPIM-19935, ICPIM-19939, ICPIM-20313
Test Case | ICPIM-19016 | ICPIM-19004 Test Case: ICPIM-18294 | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-27 13:16 | 10800 | 12600 | 0 | 100% | 10800 | 12600 | 0 | 100% |  | ICPIM-19782
Test Case | ICPIM-18885 | ICPIM-18881 User can schedule a report to Run (via PHP query) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | Pass | 2013-08-22 15:04 | 5400 | 5400 | 0 | 100% | 5400 | 5400 | 0 | 100%
Test Case | ICPIM-18878 | ICPIM-18273 PHP Response results for QueryReportData and Query CompleteReports should match |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-08-22 14:25 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-18867 | ICPIM-18841 Test Case: ADMIN-05 (16739) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-22 12:53 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-18875
Test Case | ICPIM-18847 | ICPIM-18841 Test Case: ADMIN-05 (16738) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-22 11:02 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-18846 | ICPIM-18828 Remove a task type group |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-22 10:57 | 1800 | 3000 | 0 | 100% | 1800 | 3000 | 0 | 100% |  | ICPIM-19122
Test Case | ICPIM-18845 | ICPIM-18828 Create a task type group |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-22 10:56 | 5400 | 3600 | 1800 | 66% | 5400 | 3600 | 1800 | 66%
Test Case | ICPIM-18809 | ICPIM-18808 Test Case: ADMIN-03 (16735) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-22 10:01 | 14400 | 10800 | 3600 | 75% | 14400 | 10800 | 3600 | 75%
Test Case | ICPIM-18807 | ICPIM-18806 Associate 1 or more email addresses to a team |  |  | Garrett S. | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-22 09:34 | 3600 | 900 | 2700 | 25% | 3600 | 900 | 2700 | 25% |  | ICPIM-18811
Test Case | ICPIM-18797 | ICPIM-18165 Jaspersoft Query report (back end) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | Pass | 2013-08-21 14:12 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100%
Test Case | ICPIM-18695 | ICPIM-14642 Unanchor Item (Box, Ellipse, Poly Line) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-19 13:39 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-18694 | ICPIM-18689 Auto-Mapping | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Pass | 2013-08-19 13:32 |  | 4500 | 0 | 100% |  | 4500 | 0 | 100%
Test Case | ICPIM-18693 | ICPIM-18689 Agent Data Source: Map Source | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-08-19 13:32 |  | 6000 | 0 | 100% |  | 6000 | 0 | 100%
Test Case | ICPIM-18692 | ICPIM-18689 Configure Agent Attributes For Polling | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-08-19 13:32 |  | 3000 | 0 | 100% |  | 3000 | 0 | 100%
Test Case | ICPIM-18691 | ICPIM-18689 Configuration and Connectivity to Intel DCM | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Pass | 2013-08-19 13:32 |  | 12000 | 0 | 100% |  | 12000 | 0 | 100%
Test Case | ICPIM-18690 | ICPIM-18689 Install Intel DCM (via installer) | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Pass | 2013-08-19 13:32 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-18687 | ICPIM-14642 Unanchor Item (Line, Bitmap, Text) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-19 13:18 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18685 | ICPIM-14642 Anchor Item (Box, Ellipse, Poly Line) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-19 13:01 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-18683 | ICPIM-14642 Anchor Item (Text, Bitmap, Line) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-19 12:49 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18673 | ICPIM-14642 Dashboard (Zoom Selected, Fit to Window, Default) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 16:15 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-18672 | ICPIM-14642 Copy and Paste (Ellipse, Poly Line, Ctrl keys) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 16:02 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18671 | ICPIM-14642 Copy and Paste (Bitmap, Box) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 15:51 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18670 | ICPIM-18668 Connect dialog must not allow for Multi-Connector connections- Test case | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-08-15 15:43 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-18614, ICPIM-22341, ICPIM-35613
Test Case | ICPIM-18669 | ICPIM-14642 Copy and Paste (Line, Text) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 15:38 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18666 | ICPIM-14642 Order (Bring Forward, Send Backward) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 15:06 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18665 | ICPIM-14642 Order (Bring to Front, Send to Back) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 14:53 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-18664 | ICPIM-14642 Format-Line Properties (Information) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 14:10 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-18663 | ICPIM-14642 Format-Line Properties (Color) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 13:59 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-18659 | ICPIM-14642 Format-Line Properties (Solid, Dashed, Dotted) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 13:38 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-18658 | ICPIM-14642 Format-Bitmap Properties (Aspect Ratio, Information) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 13:12 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18657 | ICPIM-14642 Format-Bitmap Properties (Viewer) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 13:01 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-18649 | ICPIM-14642 Format-Bitmap Properties (Dashed, Dotted) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 09:25 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18648 | ICPIM-14642 Format-Bitmap Properties (Border, None, Solid) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-15 09:10 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18600 | ICPIM-18325 Error Verification (user assigns tasks) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-13 11:04 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-18598 | ICPIM-18325 User views and assigns a task (not currently assigned) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-13 09:32 | 7200 | 4800 | 2400 | 66% | 7200 | 4800 | 2400 | 66% |  | ICPIM-19410, ICPIM-20304
Test Case | ICPIM-18592 | ICPIM-18091 Re-Auto Map (manually activate auto-map for unmapped DEA devices) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 16:05 | 12600 | 14400 | 0 | 100% | 12600 | 14400 | 0 | 100%
Test Case | ICPIM-18590 | ICPIM-14714 Portfolio - Advanced Search: SKU, Inventory, Production | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-12 15:30 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100%
Test Case | ICPIM-18586 | ICPIM-18324 Admin user configures a date search filter (Time Status) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 15:02 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18585 | ICPIM-18324 Admin user: Configure an assignee search filter |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 15:01 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18584 | ICPIM-18324 User Configures Line of Business search filter |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 14:52 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18580 | ICPIM-18324 User adds a task status search filter |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 13:32 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18573 | ICPIM-18100 Schema: Search Next - TEST CASE | All |  | Rachna Muthanna | Rachna Muthanna |  | Pass | 2013-08-12 12:40 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-17071
Test Case | ICPIM-18571 | ICPIM-18324 User selects to configure a Task Type search filter |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 11:26 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18570 | ICPIM-18324 Admin user selects to add a search filter |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 11:19 | 3600 | 1500 | 2100 | 41% | 3600 | 1500 | 2100 | 41%
Test Case | ICPIM-18568 | ICPIM-18566 Previous Work processed for task is unaffected by Relinquish action | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-12 11:02 | 7200 | 1800 | 5400 | 25% | 7200 | 1800 | 5400 | 25%
Test Case | ICPIM-18567 | ICPIM-18566 User Relinquishes an Assigned Task | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | Fail | 2013-08-12 10:49 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-21030, ICPIM-20253, ICPIM-21042
Test Case | ICPIM-18565 | ICPIM-18326 Task filtering (colorization) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Invalid | 2013-08-12 10:42 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-18564 | ICPIM-18326 Filtering and grouping tasks (from task management) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Fail | 2013-08-12 10:38 | 7200 | 1800 | 5400 | 25% | 7200 | 1800 | 5400 | 25% |  | ICPIM-20307
Test Case | ICPIM-18554 | ICPIM-18094 Viewer-Set initial state on Viewer to 'Select Mode'- Test Case | All |  | Rachna Muthanna | Rachna Muthanna |  | Fail | 2013-08-09 13:01 | 3600 | 4800 | 0 | 100% | 3600 | 4800 | 0 | 100% |  | ICPIM-22054, ICPIM-20299, ICPIM-16722
Test Case | ICPIM-18552 | ICPIM-18097 Viewer: Hide ToolBar - Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-08-09 12:48 | 3600 | 9000 | 0 | 100% | 3600 | 9000 | 0 | 100% |  | ICPIM-16723
Test Case | ICPIM-18550 | ICPIM-18549 Schema: "Storage Device" module name- TEST CASE | All |  | Rachna Muthanna | Rachna Muthanna |  | Pass | 2013-08-09 12:23 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50% |  | ICPIM-16467
Test Case | ICPIM-18539 | ICPIM-14642 Format-Text Properties (URL, Aspect Ratio, Information) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-08 16:00 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18535 | ICPIM-14642 Format-Text Properties (Font, Font Color, Shadow Color, Shadow Location) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-08 14:04 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-18531 | ICPIM-18530 Dashboard- Toolbar Icons - Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-08-08 13:58 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100% |  | ICPIM-18527, ICPIM-16724
Test Case | ICPIM-18516 | ICPIM-18102 Trace- Power Redundancy (Viewer) - Test Case | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-08-08 10:22 | 14400 | 7200 | 7200 | 50% | 14400 | 7200 | 7200 | 50% |  | ICPIM-17997
Test Case | ICPIM-18511 | ICPIM-14714 Portfolio - Advanced Search: Test Case: 17561 | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-07 15:38 | 14400 | 3900 | 10500 | 27% | 14400 | 3900 | 10500 | 27%
Test Case | ICPIM-18414 | ICPIM-18259 Error events when creating tasks |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP, Web Service | Invalid | 2013-08-06 14:34 | 1800 | 600 | 1200 | 33% | 1800 | 600 | 1200 | 33%
Test Case | ICPIM-18380 | ICPIM-18259 Submit a task via web services |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | Pass | 2013-08-06 12:22 | 7200 | 3000 | 4200 | 41% | 7200 | 3000 | 4200 | 41%
Test Case | ICPIM-18363 | ICPIM-18273 Web Service Response results for QueryReportData and Query CompleteReports should match |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-08-06 10:48 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100%
Test Case | ICPIM-18337 | ICPIM-18287 GUI displays Dates (Color indicators) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-08-06 09:01 | 3600 | 1800 | 1800 | 50% | 3600 | 1800 | 1800 | 50%
Test Case | ICPIM-18333 | ICPIM-18287 User selects and expands an assigned task |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Fail | 2013-08-06 08:58 | 7200 | 900 | 6300 | 12% | 7200 | 900 | 6300 | 12% |  | ICPIM-20236
Test Case | ICPIM-18257 | ICPIM-17569 Test Case: 15597 | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-08-02 14:28 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-18255 | ICPIM-18249 Follow Up CR from Verify CR task |  |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-08-02 14:00 | 7200 | 6600 | 600 | 91% | 7200 | 6600 | 600 | 91% |  | ICPIM-20168, ICPIM-20262, ICPIM-20156
Test Case | ICPIM-18254 | ICPIM-18249 Follow Up CR - Send a CR Follow-up Email | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-02 13:59 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75%
Test Case | ICPIM-18253 | ICPIM-18247 Reject CR from Verify CR task | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-02 13:58 | 10800 | 10800 | 0 | 100% | 10800 | 10800 | 0 | 100% |  | ICPIM-20131, ICPIM-20153, ICPIM-20159, ICPIM-20163
Test Case | ICPIM-18252 | ICPIM-23032 Tasks - Authorize CR - Authorize CR Passed Flow | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-08-02 13:57 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100% |  | ICPIM-20131, ICPIM-20134, ICPIM-20143, ICPIM-20150, ICPIM-20159, ICPIM-20163, ICPIM-20259, ICPIM-20140, ICPIM-20241
Test Case | ICPIM-18251 | ICPIM-27435 Change Management - Edit Work Projects: Unlock WP | All |  | An Vo | Loan Ha | Web Client | Pass | 2013-08-02 13:49 | 14400 | 15300 | 0 | 100% | 14400 | 15300 | 0 | 100% |  | ICPIM-19194, ICPIM-19424
Test Case | ICPIM-18250 | ICPIM-27435 Change Management - Edit Work Projects: View the details of WP | All |  | An Vo | Loan Ha | Web Client | Pass | 2013-08-02 13:48 | 14400 | 17400 | 0 | 100% | 14400 | 17400 | 0 | 100% |  | ICPIM-19110, ICPIM-19137
Test Case | ICPIM-18233 | ICPIM-18165 Jaspersoft Single Sign On Add User and Authentication | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-08-02 10:48 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100% |  | ICPIM-18546
Test Case | ICPIM-18212 | ICPIM-18165 User Management Web service shall return the user's account name (for Jaspersoft) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-08-01 12:39 | 1800 | 1800 | 0 | 100% | 1800 | 1800 | 0 | 100% |  | ICPIM-19454, ICPIM-18546
Test Case | ICPIM-18166 | ICPIM-18165 Analytics shall have a flag that will express the process state of the asset (In Process, Deleted, etc) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Pass | 2013-07-31 14:53 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-18153 | ICPIM-18152 Test Case: ADMIN-06 (16740) | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-07-30 15:45 | 7200 | 10800 | 0 | 100% | 7200 | 10800 | 0 | 100% |  | ICPIM-18383, ICPIM-18415
Test Case | ICPIM-18122 | ICPIM-17719 Analytics syscat - Thermals data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:59 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18121 | ICPIM-17719 Analytics syscat - Storage data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:59 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18120 | ICPIM-17719 Analytics syscat - Space data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:59 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18118 | ICPIM-17719 Analytics syscat - PowerValue data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:59 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18117 | ICPIM-17719 Analytics syscat - PowerSource data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18116 | ICPIM-17719 Analytics syscat - PowerCircuit data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-17837
Test Case | ICPIM-18115 | ICPIM-17719 Analytics syscat - Other data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-17837
Test Case | ICPIM-18114 | ICPIM-17719 Analytics syscat - Network data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:58 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18113 | ICPIM-17719 Analytics syscat - Maintenance data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:57 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18112 | ICPIM-17719 Analytics syscat - Location data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:57 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18111 | ICPIM-17719 Analytics syscat - Inventory data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:57 | 600 | 600 | 0 | 100% | 600 | 600 | 0 | 100%
Test Case | ICPIM-18110 | ICPIM-17719 Analytics syscat - Financials data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:56 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-18108 | ICPIM-17719 Analytics syscat - Compute data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:54 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-18107 | ICPIM-17719 Analytics syscat - Asset data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:48 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100%
Test Case | ICPIM-18104 | ICPIM-17719 Analytics Syscat - setup and configuration for testing | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-30 14:16 | 10800 | 10800 | 0 | 100% | 10800 | 10800 | 0 | 100%
Test Case | ICPIM-18029 | ICPIM-18028 IA Proxy performance tests (verification of 3D viewer removal from IA reservation dialog) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Invalid | 2013-07-26 12:48
Test Case | ICPIM-17923 | ICPIM-39055 Associate Assets - Unlock and Remove Associated Assets | All |  | Rachna Muthanna | Melissa C. | Web Client | Pass | 2013-07-24 01:04 | 900 | 900 | 0 | 100% | 900 | 900 | 0 | 100%
Test Case | ICPIM-17922 | ICPIM-39055 Associate Assets - Remove Associated Assets | All |  | Rachna Muthanna | Melissa C. | Web Client | Pass | 2013-07-24 01:03 | 900 | 1080 | 0 | 100% | 900 | 1080 | 0 | 100%
Test Case | ICPIM-17890 | ICPIM-17708 Web UI - Ghost bar | All |  | Tien Pham | Loan Ha | Web Client | Pass | 2013-07-19 14:21 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75%
Test Case | ICPIM-17810 | ICPIM-39055 Associate Assets- Associate Production Assets | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-07-18 15:29 | 7200 | 5400 | 1800 | 75% | 7200 | 5400 | 1800 | 75% |  | ICPIM-18623, ICPIM-19891
Test Case | ICPIM-17795 | ICPIM-39055 Associate Assets - Search Assets in Production | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-07-18 12:10 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-18607
Test Case | ICPIM-17735 | ICPIM-39055 Associate Assets - Search Assets in Inventory | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-07-17 13:23 | 7200 | 9000 | 0 | 100% | 7200 | 9000 | 0 | 100% |  | ICPIM-18607
Test Case | ICPIM-17717 | ICPIM-39055 Associate Asset - Associate SKU Assets | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-07-17 10:30 | 7200 | 7200 | 0 | 100% | 7200 | 7200 | 0 | 100% |  | ICPIM-18623, ICPIM-18626
Test Case | ICPIM-17716 | ICPIM-8364 Failover Report (SG3) |  |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Pass | 2013-07-17 10:28 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17710 | ICPIM-17537 Run BF1 Stranded Power Report |  |  | Jaimes Shonkwiler | Alok Ghodke | Windows Client | Invalid | 2013-07-16 17:05
Test Case | ICPIM-17634 | ICPIM-17486 Change Management - Add Work Projects | All |  | An Vo | Loan Ha | Web Client | Pass | 2013-07-16 14:22 | 14400 | 26700 | 0 | 100% | 14400 | 26700 | 0 | 100% |  | ICPIM-19153, ICPIM-19156, ICPIM-19432
Test Case | ICPIM-17379 | ICPIM-14642 Format-Text Properties (Border, Solid, Dashed, Dotted) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-07-12 10:43 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-17283 | ICPIM-15488 Search Templates- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-10 11:00 | 7200 | 8100 | 0 | 100% | 7200 | 8100 | 0 | 100%
Test Case | ICPIM-17273 | ICPIM-17264 CLONE - Alarm Manager > Affected Equipment- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17272 | ICPIM-17264 CLONE - Alarm Manager > Alarm Options dropdown- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17271 | ICPIM-17264 CLONE - Alarm Manager > Alarm tab- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2013-07-09 14:58 | 3600 | 10800 | 0 | 100% | 3600 | 10800 | 0 | 100% |  | ICPIM-17215
Test Case | ICPIM-17270 | ICPIM-17264 CLONE - Alarm Manager > Affected Items -Highlight/Clear: TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17269 | ICPIM-17264 CLONE - Alarm Manager > Remove Alarm- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17268 | ICPIM-17264 CLONE - Alarm Manager > Modify Alarm- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100% |  | ICPIM-17276
Test Case | ICPIM-17267 | ICPIM-17264 CLONE - Alarm Manager > Viewer: Filters and Buttons- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17266 | ICPIM-17264 CLONE - Creating Alarms via Script- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17265 | ICPIM-17264 CLONE - Creating Alarms via Web Services- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 14:58 | 3600 | 7200 | 0 | 100% | 3600 | 7200 | 0 | 100%
Test Case | ICPIM-17254 | ICPIM-17205 Alarm Manager > Affected Equipment- TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-07-09 11:14 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-17252 | ICPIM-12703 WebUI - Login Rendered Page | All |  | Mai Nguyen | Rachna Muthanna | Web Client | Pass | 2013-07-09 10:59 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-17249
Test Case | ICPIM-17227 | ICPIM-17205 Alarm Manager > Alarm Options dropdown- TC |  |  | An Vo | Rachna Muthanna | Windows Client | Pass | 2013-07-08 15:37 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-17226 | ICPIM-17205 Alarm Manager > Alarm tab- TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Invalid | 2013-07-08 15:24 |  | 0 |  | 100% |  | 0 |  | 100%
Test Case | ICPIM-17225 | ICPIM-17205 Alarm Manager > Affected Items -Highlight/Clear: TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Invalid | 2013-07-08 15:12
Test Case | ICPIM-17220 | ICPIM-17205 Alarm Manager > Remove Alarm- TC |  |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2013-07-08 14:52 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-33832
Test Case | ICPIM-17214 | ICPIM-17205 Alarm Manager > Modify Alarm- TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Invalid | 2013-07-08 14:15 |  | 0 |  | 100% |  | 0 |  | 100%
Test Case | ICPIM-17212 | ICPIM-17205 Alarm Manager > Viewer: Filters and Buttons- TC |  |  | An Vo | Rachna Muthanna | Windows Client | Fail | 2013-07-08 13:13 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-33826
Test Case | ICPIM-17210 | ICPIM-17205 Creating Alarms via Script- TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Invalid | 2013-07-08 12:37 |  | 0 |  | 100% |  | 0 |  | 100%
Test Case | ICPIM-17206 | ICPIM-17205 Creating Alarms via Web Services- TC |  |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Fail | 2013-07-08 11:06 |  | 0 |  | 100% |  | 0 |  | 100%
Test Case | ICPIM-17193 | ICPIM-17248 Display Visual Work Action Item TC | All |  | QA Queue DO NOT DEACTIVATE | Loan Ha | PHP | New | 2013-07-08 09:09 |  | 0 |  | 100% |  | 0 |  | 100%
Test Case | ICPIM-17168 | ICPIM-17167 Creating a New Line Of Business. | All |  | Mai Nguyen | Rachna Muthanna | Windows Client | Fail | 2013-07-05 15:11 | 3600 | 5400 | 600 | 90% | 3600 | 5400 | 600 | 90% |  | ICPIM-16334, ICPIM-33749
Test Case | ICPIM-17137 | ICPIM-17107 Opsdb updateAsset timeout testing (using HTTPS variant) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-05 09:03 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0%
Test Case | ICPIM-17133 | ICPIM-17107 Change Sync: Add Power Strip to Opsdb | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:34 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17132 | ICPIM-17107 Change Sync: Add Enclosure to Opsdb | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:31 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17131 | ICPIM-17107 Change Sync: Add Filer to Opsdb | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:29 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17130 | ICPIM-17107 Change Sync: Add an invalid Asset to Opsdb | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:27 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17129 | ICPIM-17107 Change Sync: Add Asset to Opsdb | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:27 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17128 | ICPIM-17107 End to End Sync: after full sync, change multiple devices and filers within OpsDb to a non-active status, action another full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:09 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17127 | ICPIM-17107 End to End Sync: after full sync, add multiple , devices, and filers within OpsDb, action another full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:06 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17126 | ICPIM-17107 End to End Sync: after full sync, move multiple , devices, and filers within OpsDb, action another full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 15:05 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17125 | ICPIM-17107 End to End Sync: manually move enclosures, devices, filers from the iCDC database that were placed by the sync, action a full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:30 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17124 | ICPIM-17107 End to End Sync: Test 3: manually delete enclosures, devices, filers from the iCDC database that were placed by the sync, action a full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:27 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17123 | ICPIM-17107 End to End Sync: Manually add assets within the iCDC database using enclosures, devices and filers, action a full sync | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:24 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17122 | ICPIM-17107 End to End Sync: beginning with an infrastructure only db, action a full sync. (will take several hours) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:21
Test Case | ICPIM-17121 | ICPIM-17107 Asset Management Log Viewer: Asset CollisionLibrary Not Found | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:10 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17120 | ICPIM-17107 Asset Management Log Viewer: Asset CollisionAsset attempting to be placed in an unauthorized location | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:07 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17119 | ICPIM-17107 Asset Management Log Viewer: Asset CollisionSpatial Placement Failed | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 14:05 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17109 | ICPIM-17107 Asset Management Log Viewer: Asset Collision | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-07-03 13:33 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-17108 | ICPIM-17107 Opsdb Quick Sync Verification | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Service | New | 2013-07-03 13:17 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100% |  | ICPIM-11202
Test Case | ICPIM-16709 | ICPIM-14303 Previous VM Manager dialog VM mappings (settings) retained | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | Invalid | 2013-06-12 12:35
Test Case | ICPIM-16598 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Download as PNG | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-06-07 14:30 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-16594 | ICPIM-12585 Portfolio - Pie Chart: Legend | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-07 14:18 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-16511 | ICPIM-12585 Portfolio - Pie Chart: Pie Segment/Slice | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 15:08 |  | 2100 | 0 | 100% |  | 2100 | 0 | 100%
Test Case | ICPIM-16506 | ICPIM-12585 Pie Chart - Ability to toggle off and on the use of the chart as a selectable item. | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-06-05 14:38 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16502 | ICPIM-12585 Portfolio - Pie Chart: Maximize mode | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 14:26 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-10964
Test Case | ICPIM-16500 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Email | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 14:15 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-16499 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Download as PDF | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-06-05 13:29 | [9 empty] | ICPIM-34363, ICPIM-35324
Test Case | ICPIM-16498 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Download as CSV | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-06-05 12:54 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16497 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Toggle between Chart and Data table | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 12:36 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16496 | ICPIM-12585 Portfolio - Pie Chart - Maximize mode: Table view (tabular data) | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 12:08 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16494 | ICPIM-12585 Portfolio - Pie Chart: Pie chart UI | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-06-05 11:57 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-10964, ICPIM-14740, ICPIM-15220
Test Case | ICPIM-16442 | ICPIM-16431 Trigger the Event Notification | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16441 | ICPIM-16431 Web Interface | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16440 | ICPIM-16431 Reports, Dashboards | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16439 | ICPIM-16431 Virtual Machine | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16438 | ICPIM-16431 IT Build Out | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16437 | ICPIM-16431 Power Build Out | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16436 | ICPIM-16431 Facilities Build Out | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16435 | ICPIM-16431 Template, Library Item, and 3D Object Build Out | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16434 | ICPIM-16431 Class Creation and Datastore Definitions | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16433 | ICPIM-16431 User Administration | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16432 | ICPIM-16431 System Configuration and Setup | All |  | Ron Norris | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:54
Test Case | ICPIM-16430 | ICPIM-16419 Trigger the Event Notification | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16429 | ICPIM-16419 Web Interface | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16428 | ICPIM-16419 Reports, Dashboards | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16427 | ICPIM-16419 Virtual Machine | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16426 | ICPIM-16419 IT Build Out | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16425 | ICPIM-16419 Power Build Out | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16424 | ICPIM-16419 Facilities Build Out | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16423 | ICPIM-16419 Template, Library Item, and 3D Object Build Out | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16422 | ICPIM-16419 Class Creation and Datastore Definitions | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16421 | ICPIM-16419 User Administration | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16420 | ICPIM-16419 System Configuration and Setup | All |  | Garrett S. | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:51
Test Case | ICPIM-16418 | ICPIM-16407 Trigger the Event Notification | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16417 | ICPIM-16407 Web Interface | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16416 | ICPIM-16407 Reports, Dashboards | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16415 | ICPIM-16407 Virtual Machine | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16414 | ICPIM-16407 IT Build Out | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16413 | ICPIM-16407 Power Build Out | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16412 | ICPIM-16407 Facilities Build Out | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16411 | ICPIM-16407 Template, Library Item, and 3D Object Build Out | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16410 | ICPIM-16407 Class Creation and Datastore Definitions | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16409 | ICPIM-16407 User Administration | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16408 | ICPIM-16407 System Configuration and Setup | All |  | Rachna Muthanna | Jaimes Shonkwiler | Windows Client | Pass | 2013-05-22 14:47
Test Case | ICPIM-16406 | ICPIM-16395 Trigger the Event Notification | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16405 | ICPIM-16395 Web Interface | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16404 | ICPIM-16395 Reports, Dashboards | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16403 | ICPIM-16395 Virtual Machine | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16402 | ICPIM-16395 IT Build Out | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16401 | ICPIM-16395 Power Build Out | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16400 | ICPIM-16395 Facilities Build Out | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16399 | ICPIM-16395 Template, Library Item, and 3D Object Build Out | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16398 | ICPIM-16395 Class Creation and Datastore Definitions | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16397 | ICPIM-16395 User Administration | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16396 | ICPIM-16395 System Configuration and Setup | All |  | Loan Ha | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:43
Test Case | ICPIM-16394 | ICPIM-16383 Trigger the Event Notification | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:32
Test Case | ICPIM-16393 | ICPIM-16383 Web Interface | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:31
Test Case | ICPIM-16392 | ICPIM-16383 Reports, Dashboards | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:30
Test Case | ICPIM-16391 | ICPIM-16383 Virtual Machine | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:29
Test Case | ICPIM-16390 | ICPIM-16383 IT Build Out | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:28
Test Case | ICPIM-16389 | ICPIM-16383 Power Build Out | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:26
Test Case | ICPIM-16388 | ICPIM-16383 Facilities Build Out | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:25
Test Case | ICPIM-16387 | ICPIM-16383 Template, Library Item, and 3D Object Build Out | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:24
Test Case | ICPIM-16386 | ICPIM-16383 Class Creation and Datastore Definitions | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:23
Test Case | ICPIM-16385 | ICPIM-16383 User Administration | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:22
Test Case | ICPIM-16384 | ICPIM-16383 System Configuration and Setup | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-05-22 14:20
Test Case | ICPIM-16353 | ICPIM-16346 Export Asset Cooling | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:11 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0%
Test Case | ICPIM-16352 | ICPIM-16346 Export Asset Network | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:11 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0%
Test Case | ICPIM-16351 | ICPIM-16346 Export Asset Space | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:10 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0%
Test Case | ICPIM-16350 | ICPIM-16346 Export Asset Power Connectivity | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:10 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0%
Test Case | ICPIM-16349 | ICPIM-16346 Export Asset Power | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:09 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0% |  | ICPIM-17002, ICPIM-17259
Test Case | ICPIM-16348 | ICPIM-16346 Export Asset Data | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:09 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0%
Test Case | ICPIM-16347 | ICPIM-16346 Export Asset and Classes | All |  | Garrett S. | Melissa C. | Windows Client | Invalid | 2013-05-15 13:08 | 21600 |  | 21600 | 0% | 21600 |  | 21600 | 0% |  | ICPIM-17245
Test Case | ICPIM-16329 | ICPIM-12699 Platform - Help: Navigating within Help | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-05-13 18:30 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-16328 | ICPIM-12699 Platform - Help: Accessing Help | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-05-13 18:03 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-16323 | ICPIM-15805 Non-existent Cache Directory TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-05-13 14:57 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-16312
Test Case | ICPIM-16314 | ICPIM-15805 Cache Folders at Non-default Install Location TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-05-13 10:33 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-16186 | ICPIM-12703 Authentication timeout UI - no password fill-in TC | All |  | Ron Norris | Ron Norris | Web Client | Fail | 2013-04-29 10:45 | 600 |  | 600 | 0% | 600 |  | 600 | 0%
Test Case | ICPIM-16158 | ICPIM-16157 Ancestors and Children TRUE TC | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-04-25 14:58
Test Case | ICPIM-16154 | ICPIM-13034 Configuration Dialog Accessible via MapView (Dashboard) | All |  | Trinh Nguyen | Garrett S. | Windows Client | Pass | 2013-04-25 13:39 |  | 300 | 0 | 100% |  | 300 | 0 | 100% |  | ICPIM-11147
Test Case | ICPIM-16153 | ICPIM-13034 MapView (Dashboard) Print Features | All |  | Trinh Nguyen | Garrett S. | Windows Client | Pass | 2013-04-25 13:33 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-16151 | ICPIM-13034 Drill Down and Back in MapView (Dashboards) | All |  | Trinh Nguyen | Garrett S. | Windows Client | Pass | 2013-04-25 13:13 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100% |  | ICPIM-22216, ICPIM-11151
Test Case | ICPIM-16149 | ICPIM-13034 MapView (Dashboards) Editable | All |  | Trinh Nguyen | Garrett S. | Windows Client | Pass | 2013-04-25 12:27 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-16143, ICPIM-11129, ICPIM-11139
Test Case | ICPIM-16148 | ICPIM-13034 Dashboard Zoom/Fit to Window Features | All |  | Trinh Nguyen | Garrett S. | Windows Client | Pass | 2013-04-25 10:55 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-11143, ICPIM-11145, ICPIM-11153
Test Case | ICPIM-16098 | ICPIM-16078 Can update work action status and optionally submit a comment TC | All |  | Ron Norris | Ron Norris | Web Service | New | 2013-04-23 13:30 | [9 empty] | ICPIM-16124
Test Case | ICPIM-16088 | ICPIM-16078 Can retrieve work actions associated with team to which user belongs | All |  | Ron Norris | Ron Norris | Web Service | New | 2013-04-23 11:37
Test Case | ICPIM-16087 | ICPIM-16078 Ability to Modify Location or Equipment on Work Task. TC | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-23 11:20
Test Case | ICPIM-16086 | ICPIM-16078 Can retrieve all text relating to work actions for hierarchy item for current user. TC | All |  | Ron Norris | Ron Norris | Web Service | New | 2013-04-23 11:11
Test Case | ICPIM-16083 | ICPIM-16065 Clear Visual Work Actions TC | All |  | Loan Ha | Loan Ha | Web Service | Pass | 2013-04-23 10:34 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-13829
Test Case | ICPIM-16082 | ICPIM-16065 Refresh Visual Work Action TC | All |  | Loan Ha | Loan Ha | Web Service | Pass | 2013-04-23 10:24 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-13827
Test Case | ICPIM-16081 | ICPIM-16065 Query for Visual Work Action TC | All |  | Loan Ha | Loan Ha | Web Service | Pass | 2013-04-23 09:57 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-13825
Test Case | ICPIM-16054 | ICPIM-16048 Shall return template identifier, label name, manufacturer and model | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-04-22 15:30
Test Case | ICPIM-16053 | ICPIM-16048 Shall provide an interface to query for Templates: by Dimension | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-04-22 15:28
Test Case | ICPIM-16050 | ICPIM-16048 Shall provide an interface to query for Templates: by Model | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-04-22 15:26
Test Case | ICPIM-16049 | ICPIM-16048 Shall provide an interface to query for Templates: by Manufacturer | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-04-22 15:25
Test Case | ICPIM-16037 | ICPIM-15797 Email Share Window Subject Line Pre-Populated with Information About Current View | All |  | Vinh Nguyen | Garrett S. | Web Client | Pass | 2013-04-19 16:59 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-16036 | ICPIM-15797 Emails Include iTRACS Standard Branding and Copyright Information | All |  | Vinh Nguyen | Garrett S. | Web Client, Web Service | Pass | 2013-04-19 16:48 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16021 | ICPIM-15756 Mapview Visual Work Action Item TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-04-19 15:05
Test Case | ICPIM-16018 | ICPIM-14303 Visual Filter for Hypervisors | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-04-19 14:58
Test Case | ICPIM-16008 | ICPIM-15988 Network Chart - Fiber_Switch_Ports -TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 14:21
Test Case | ICPIM-16007 | ICPIM-15988 Network Chart - Fiber_Positions-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 14:20
Test Case | ICPIM-16006 | ICPIM-15988 Network Chart - Copper_Switch_Ports-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 14:19
Test Case | ICPIM-16005 | ICPIM-15988 Network Chart - Copper_Positions-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 14:17 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-16004 | ICPIM-15988 Thermal Chart - "Temperature (C/F)"-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-04-19 14:15 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34518, ICPIM-22061
Test Case | ICPIM-16003 | ICPIM-15988 Thermal Chart - "Humidity (%)"-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 14:11 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-15758, ICPIM-22061
Test Case | ICPIM-16002 | ICPIM-15988 Power Chart - Outputs-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:38
Test Case | ICPIM-16001 | ICPIM-15988 Power Chart - Inputs-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:36
Test Case | ICPIM-16000 | ICPIM-15988 Power Chart - "Current (A)" -TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:35
Test Case | ICPIM-15999 | ICPIM-15988 Power Chart - "Load (kW)" -TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:33 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15998 | ICPIM-15988 Power Chart - "Current_Totals (A)"-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:31
Test Case | ICPIM-15995 | ICPIM-15988 Power Chart - "Power_Totals (kW)"-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:13 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15994 | ICPIM-15988 Power Chart - "Load_Totals (PUE)"-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:11
Test Case | ICPIM-15993 | ICPIM-15988 Space Chart - Breaker_Slots-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:09
Test Case | ICPIM-15992 | ICPIM-15988 Space Chart - Switch_Cards-TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:07 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15991 | ICPIM-15988 Space Chart - Shelf (U) -TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:05 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15990 | ICPIM-15988 Space Chart - Blade -TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 13:03 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15989 | ICPIM-15988 Space Chart - Cabinet | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-19 11:14 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15987 | ICPIM-15839 Portfolio - Trace: Cables | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 11:00 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15979 | ICPIM-15839 Portfolio - Trace: Trace Pane controls | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-19 09:39 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15978 | ICPIM-13083 Security Config Rest Service Returns Security Info if User is Authenticated TC | All |  | Loan Ha | Ron Norris | PHP | New | 2013-04-19 09:10 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-15977 | ICPIM-13083 Security Config Rest Service Does Not Return Security Info without Login Credentials TC | All |  | Trinh Nguyen | Ron Norris | PHP | Pass | 2013-04-19 08:58 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15940 | ICPIM-15797 Web Service - Error Message Returned When Mail Can't Be Sent | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-18 15:38
Test Case | ICPIM-15939 | ICPIM-14589 Hotspots for Area;Rows; Floor mounted Assets and Enclosure pads (5-8) TC | All |  | Rachna Muthanna | Rachna Muthanna | PHP | Pass | 2013-04-18 15:29
Test Case | ICPIM-15938 | ICPIM-15797 User can supply valid template in Share.email rest request and data returns in that format | All |  | Ron Norris | Ron Norris | Web Service | New | 2013-04-18 15:24
Test Case | ICPIM-15935 | ICPIM-15797 Editable To, Cc, Bcc, Subject and Body fields in Email Modal Window | All |  | Vinh Nguyen | Garrett S. | Web Client | Pass | 2013-04-18 15:00 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-15932 | ICPIM-15797 Blank Data Returned For Non-Existent Templates | All |  | Ron Norris | Ron Norris | Web Service | New | 2013-04-18 14:56
Test Case | ICPIM-15930 | ICPIM-15797 Modal Window Displayed When Email Widget is Clicked | All |  | Vinh Nguyen | Garrett S. | Web Client | Pass | 2013-04-18 14:17 |  | 360 | 0 | 100% |  | 360 | 0 | 100%
Test Case | ICPIM-15927 | ICPIM-15797 Error Message Displayed When Mail Can't Be Sent | All |  | Vinh Nguyen | Ron Norris | Web Client | Pass | 2013-04-18 13:57 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-12324
Test Case | ICPIM-15926 | ICPIM-15839 Portfolio - Trace: Trace Property pane | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-18 13:42 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-15695
Test Case | ICPIM-15925 | ICPIM-14714 Portfolio - Advanced Search: Share, view | All |  | Loan Ha | Loan Ha | Web Client | Pass | 2013-04-18 13:27 | 3600 | 11100 | 0 | 100% | 3600 | 11100 | 0 | 100% |  | ICPIM-15910, ICPIM-15922, ICPIM-17935, ICPIM-18555, ICPIM-19514, ICPIM-15908, ICPIM-16115, ICPIM-20316, ICPIM-21452, ICPIM-20319, ICPIM-14812, ICPIM-14820
Test Case | ICPIM-15924 | ICPIM-15797 From Address Populated with Current User's Email Address | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-18 12:56
Test Case | ICPIM-15919 | ICPIM-15839 Portfolio - Trace: Trace Hierarchy pane | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-04-18 12:28 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-15701
Test Case | ICPIM-15918 | ICPIM-15797 Subject Line Populated with Human Readable and Context Appropriate Text | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-18 12:18
Test Case | ICPIM-15917 | ICPIM-15797 Share Service Should Allow Attachment of PDF File to Email | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-18 11:46
Test Case | ICPIM-15907 | ICPIM-13171 MyDCIM - User Roots - Default root | All |  | An Vo | Ron Norris | Web Client | Pass | 2013-04-18 10:46 | 3600 | 5400 | 0 | 100% | 3600 | 5400 | 0 | 100%
Test Case | ICPIM-15904 | ICPIM-34123 Portfolio - Quick Search: Search Hierarchy | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-18 10:15 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-15899 | ICPIM-13171 MyDCIM - User Roots - Error when navigating to inaccessible roots | All |  | An Vo | Ron Norris | Web Client | Pass | 2013-04-18 10:08 | 1800 | 9000 | 0 | 100% | 1800 | 9000 | 0 | 100% |  | ICPIM-17981
Test Case | ICPIM-15897 | ICPIM-13171 MyDCIM - User Roots - Roots of assets associated with user's LOB | All |  | An Vo | Ron Norris | Web Client | Fail | 2013-04-18 09:50 | 3600 | 10800 | 0 | 100% | 3600 | 10800 | 0 | 100% |  | ICPIM-17938, ICPIM-34742, ICPIM-34745
Test Case | ICPIM-15896 | ICPIM-15797 Email Templates Should Include User Data of Sender, Date, Time... | All |  | Vinh Nguyen | Garrett S. | Web Client, Web Service | Pass | 2013-04-18 09:43 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-15898
Test Case | ICPIM-15888 | ICPIM-14303 Security Rights VM Manager Dialog | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-04-17 17:30
Test Case | ICPIM-15887 | ICPIM-15797 Email Body To Contain Correct Template for Email Content or Attachment Type | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-17 17:01
Test Case | ICPIM-15884 | ICPIM-14303 Previous VM Manager dialog removed | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | Invalid | 2013-04-17 16:48
Test Case | ICPIM-15883 | ICPIM-15797 Email Body To Contain Correct Text for Email Content or Attachment Type | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-17 16:45
Test Case | ICPIM-15882 | ICPIM-13471 Web Services Removed | All |  | An Vo | Jaimes Shonkwiler | Windows Client | Fail | 2013-04-17 16:29 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-33903
Test Case | ICPIM-15869 | ICPIM-15839 Portfolio - Trace: Image View hovering | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-17 13:46 |  | 1200 | 2400 | 33% |  | 1200 | 2400 | 33% |  | ICPIM-15380, ICPIM-15833, ICPIM-15866, ICPIM-16132
Test Case | ICPIM-15865 | ICPIM-15839 Portfolio - Trace: Max/Min mode | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-17 12:21 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-15633, ICPIM-15638
Test Case | ICPIM-15864 | ICPIM-15839 Portfolio - Trace: Trace Access | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Fail | 2013-04-17 11:46 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-15761, ICPIM-15693, ICPIM-34521
Test Case | ICPIM-15858 | ICPIM-15805 Image Cache TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2013-04-17 10:48 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-15822, ICPIM-15801, ICPIM-15890, ICPIM-16014, ICPIM-33805, ICPIM-12438, ICPIM-12439, ICPIM-12441, ICPIM-12443, ICPIM-12446, ICPIM-12447, ICPIM-12454, ICPIM-12467, ICPIM-12469, ICPIM-12470, ICPIM-12471, ICPIM-12472, ICPIM-12473, ICPIM-12474, ICPIM-12576, ICPIM-12577, ICPIM-12578, ICPIM-12579, ICPIM-12580, ICPIM-12581, ICPIM-13578, ICPIM-13580
Test Case | ICPIM-15846 | ICPIM-15797 Specify HTML or Rich Text in Sharing Email | All |  | Garrett S. | Garrett S. | Web Service | New | 2013-04-16 16:49 | [9 empty] | ICPIM-12314
Test Case | ICPIM-15819 | ICPIM-14672 Image Cache (WS) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-04-16 11:07 | [9 empty] | ICPIM-15822, ICPIM-15890, ICPIM-12437, ICPIM-12438, ICPIM-12439, ICPIM-12441, ICPIM-12442, ICPIM-12443, ICPIM-12445, ICPIM-12451, ICPIM-12452, ICPIM-12453, ICPIM-12454, ICPIM-12582, ICPIM-12583, ICPIM-13578, ICPIM-13580
Test Case | ICPIM-15798 | ICPIM-15797 Create PDF via PHP | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-04-15 13:35
Test Case | ICPIM-15796 | ICPIM-15805 Clearing Image Cache by Class Group TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-04-15 13:21 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-15799, ICPIM-15801, ICPIM-15996, ICPIM-16145, ICPIM-10087
Test Case | ICPIM-15781 | ICPIM-12704 Portfolio - Advanced Navigation: Navigation | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-15 09:32 | 1800 | 900 | 900 | 50% | 1800 | 900 | 900 | 50%
Test Case | ICPIM-15779 | ICPIM-13004 Portfolio - Bar Char: Download as CSV | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-15 09:25 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-14743
Test Case | ICPIM-15777 | ICPIM-34129 Portfolio - Portfolio view: Navigating performance | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-04-15 09:18 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-15703
Test Case | ICPIM-15768 | ICPIM-13904 Clearing Mapview Cache by Class TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-04-12 16:22 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-15892, ICPIM-15996, ICPIM-7145
Test Case | ICPIM-15757 | ICPIM-15756 Mapview Links Hotspots TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-04-12 14:31 | [9 empty] | ICPIM-15766, ICPIM-16031, ICPIM-10569
Test Case | ICPIM-15755 | ICPIM-14303 Virtual Machine Manager TC | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | Invalid | 2013-04-12 14:16 | [9 empty] | ICPIM-15752
Test Case | ICPIM-15734 | ICPIM-14642 Format-Text Properties (Fill, Color) TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-04-12 10:38 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-15733 | ICPIM-14860 About CPIM Browser Interface - Read Only | All |  | Loan Ha | Jaimes Shonkwiler | Web Client | Pass | 2013-04-12 10:22 | 900 |  | 900 | 0% | 900 |  | 900 | 0%
Test Case | ICPIM-15729 | ICPIM-14642 Dashboard Context Menu TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-04-12 09:34 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-15721 | ICPIM-15714 QueryUserSettings TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-04-12 08:12 | [9 empty] | ICPIM-15724
Test Case | ICPIM-15715 | ICPIM-15714 QueryUserSettingsOnType TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-04-11 16:17 | [9 empty] | ICPIM-14273
Test Case | ICPIM-15618 | ICPIM-15542 Visualization (Web Service) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-04-09 15:43 | [9 empty] | ICPIM-15507, ICPIM-15558, ICPIM-15561, ICPIM-15609, ICPIM-15616, ICPIM-15543, ICPIM-15545
Test Case | ICPIM-15615 | ICPIM-15611 Quick Search (Paged Search- Result)- TC | All |  | Rachna Muthanna | Rachna Muthanna | PHP | Pass | 2013-04-09 15:25
Test Case | ICPIM-15614 | ICPIM-15611 Quick Search (Performing 'Contains' Search)- TC | All |  | Rachna Muthanna | Rachna Muthanna | PHP | Pass | 2013-04-09 15:20
Test Case | ICPIM-15613 | ICPIM-15611 Quick Search (Search)- TC | All |  | Rachna Muthanna | Rachna Muthanna | PHP | Pass | 2013-04-09 14:15
Test Case | ICPIM-15612 | ICPIM-15611 Quick Search (Classes and templates) TC | All |  | Rachna Muthanna | Rachna Muthanna | PHP | Pass | 2013-04-09 14:07
Test Case | ICPIM-15607 | ICPIM-28722 Ensure RF Code Assets are Correctly Auto-Mapped to CPIM Assets By Name | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-04-09 12:49 |  | 14100 | 300 | 97% |  | 14100 | 300 | 97% |  | ICPIM-15636, ICPIM-15643, ICPIM-26015
Test Case | ICPIM-15596 | ICPIM-28722 Configure RF Code DEA and Instance Connectivity |  |  | Thuy Tran | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-04-08 16:07 |  | 15300 | 0 | 100% |  | 15300 | 0 | 100% |  | ICPIM-15620, ICPIM-15622
Test Case | ICPIM-15578 | ICPIM-14303 Verify VMware code removed from CPIM code base | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | Invalid | 2013-04-04 13:49
Test Case | ICPIM-15527 | ICPIM-13471 Each Installer Component is installable via standalone MSI | All |  | An Vo | Jaimes Shonkwiler | Windows Client | Fail | 2013-04-02 08:33 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-35053, ICPIM-35058
Test Case | ICPIM-15523 | ICPIM-13014 Each DEA must be licenseable | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-04-01 14:33 | 10800 | 1800 | 9000 | 16% | 10800 | 1800 | 9000 | 16% |  | ICPIM-26996
Test Case | ICPIM-15520 | ICPIM-13014 DEAs use HTTPS by Default | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-04-01 14:11
Test Case | ICPIM-15501 | ICPIM-15488 Import Templates- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 13:08 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15500 | ICPIM-14642 Adding to Dashboard TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-03-29 13:05 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-15499 | ICPIM-14642 Search - Find Dashboards TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-03-29 12:43 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-15498 | ICPIM-15488 Add Connection Point- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 11:10 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15497 | ICPIM-14642 Accessing Dashboard via (Create, Connect, Disconnect) TC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2013-03-29 11:06 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-15496 | ICPIM-15488 Add Door- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 11:04 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15495 | ICPIM-15488 Add Datalink- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 11:01 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15494 | ICPIM-15488 Add Rectangle- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:59 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15493 | ICPIM-15488 Add Image- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:52 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15492 | ICPIM-15488 Add Label- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:44 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15491 | ICPIM-15488 Add Slot- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:42 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15490 | ICPIM-15488 Add Connector- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:41 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15489 | ICPIM-15488 Designer Tab- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-29 10:27 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-15487 | ICPIM-15477 Data Connections Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:09
Test Case | ICPIM-15486 | ICPIM-15477 Power Connections Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:08
Test Case | ICPIM-15485 | ICPIM-15477 Library Items Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:08
Test Case | ICPIM-15484 | ICPIM-15477 Rename Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:07
Test Case | ICPIM-15483 | ICPIM-15477 Datastore Values Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:07
Test Case | ICPIM-15482 | ICPIM-15477 Module Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:07
Test Case | ICPIM-15481 | ICPIM-15477 Panel Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:06
Test Case | ICPIM-15480 | ICPIM-15477 Enclosure Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:06
Test Case | ICPIM-15479 | ICPIM-15477 Row Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:06
Test Case | ICPIM-15478 | ICPIM-15477 Basic Import | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | New | 2013-03-29 10:04
Test Case | ICPIM-15150 | ICPIM-15839 Portfolio - Trace: Asset level 11 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-27 10:31 | [9 empty] | ICPIM-15378, ICPIM-15730, ICPIM-15793
Test Case | ICPIM-15142 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 11 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-27 10:31 |  | 2760 | 0 | 100% |  | 2760 | 0 | 100%
Test Case | ICPIM-15108 | ICPIM-15107 User Management (Get UserInfo) TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-25 15:44 | [9 empty] | ICPIM-13764
Test Case | ICPIM-15106 | ICPIM-14094 Advanced Search (Data Stores) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-03-25 13:41 | [9 empty] | ICPIM-6941
Test Case | ICPIM-15074 | ICPIM-15839 Portfolio - Trace: Asset level 10 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-25 08:58 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-15073 | ICPIM-15065 Portfolio - Chart Level 10: Thermals Gauges | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-25 08:58 | 1800 | 1860 | 0 | 100% | 1800 | 1860 | 0 | 100% |  | ICPIM-35276, ICPIM-35282, ICPIM-35279
Test Case | ICPIM-15072 | ICPIM-15065 Portfolio - Chart Level 10: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-25 08:58 | 1200 | 1260 | 0 | 100% | 1200 | 1260 | 0 | 100%
Test Case | ICPIM-15071 | ICPIM-15065 Portfolio - Chart Level 10: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Invalid | 2013-03-25 08:58 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-15070 | ICPIM-15065 Portfolio - Chart Level 10: Line Gauge | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-25 08:58 | 1200 | 1260 | 0 | 100% | 1200 | 1260 | 0 | 100% |  | ICPIM-35273
Test Case | ICPIM-15069 | ICPIM-15065 Portfolio - Chart Level 10: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-25 08:58 | 1800 | 1860 | 0 | 100% | 1800 | 1860 | 0 | 100% |  | ICPIM-35232, ICPIM-35270
Test Case | ICPIM-15068 | ICPIM-15065 Portfolio - Chart Level 10: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-25 08:58 | 1800 | 1860 | 0 | 100% | 1800 | 1860 | 0 | 100% |  | ICPIM-35232, ICPIM-35270
Test Case | ICPIM-15067 | ICPIM-15065 Portfolio - Chart Level 10: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-25 08:58 | 1800 | 1860 | 0 | 100% | 1800 | 1860 | 0 | 100% |  | ICPIM-34509, ICPIM-35270
Test Case | ICPIM-15066 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 10 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-25 08:58 |  | 1260 | 0 | 100% |  | 1260 | 0 | 100%
Test Case | ICPIM-14974 | ICPIM-14623 Row Editor (Pre-Req)- Create Rows TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-22 08:55 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-14930 | ICPIM-34123 Portfolio - Quick Search: Save, Share Results list | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-03-20 16:24 | [9 empty] | ICPIM-17646, ICPIM-17651, ICPIM-17636, ICPIM-17649, ICPIM-17653
Test Case | ICPIM-14925 | ICPIM-14889 Portfolio - Sharing: Email | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-20 15:19 | [9 empty] | ICPIM-14926, ICPIM-15782, ICPIM-16159, ICPIM-16167, ICPIM-15645
Test Case | ICPIM-14924 | ICPIM-14714 Portfolio - Advanced Search: Save, Update, Delete | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-03-20 15:13 | 3600 | 13500 | 0 | 100% | 3600 | 13500 | 0 | 100% |  | ICPIM-15163, ICPIM-16225, ICPIM-18543, ICPIM-20099, ICPIM-20937, ICPIM-27965, ICPIM-27968, ICPIM-9760, ICPIM-9764, ICPIM-9772, ICPIM-9776, ICPIM-9780, ICPIM-9784, ICPIM-9788, ICPIM-9796, ICPIM-9800, ICPIM-9804, ICPIM-9808, ICPIM-9812, ICPIM-9816
Test Case | ICPIM-14923 | ICPIM-14889 Portfolio - Sharing: Print | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-20 14:53
Test Case | ICPIM-14919 | ICPIM-12697 Executing Reports | All |  | Loan Ha | Melissa C. | Web Client | Fail | 2013-03-20 14:01 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-22446, ICPIM-15437, ICPIM-20735, ICPIM-15439, ICPIM-15443, ICPIM-15451, ICPIM-17674, ICPIM-17712, ICPIM-22002, ICPIM-15679, ICPIM-15707
Test Case | ICPIM-14918 | ICPIM-12697 Report Navigation | All |  | Loan Ha | Melissa C. | Web Client | Fail | 2013-03-20 14:01 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-17707, ICPIM-15912, ICPIM-15677, ICPIM-21021, ICPIM-22426, ICPIM-16122
Test Case | ICPIM-14892 | ICPIM-14889 Portfolio - Sharing: PDF | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-20 10:06 | 1800 | 1500 | 300 | 83% | 1800 | 1500 | 300 | 83% |  | ICPIM-14906, ICPIM-15648, ICPIM-15653, ICPIM-16102, ICPIM-34363, ICPIM-35324
Test Case | ICPIM-14891 | ICPIM-14889 Portfolio - Sharing: CSV | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-20 09:50
Test Case | ICPIM-14890 | ICPIM-14889 Portfolio - Sharing: PNG | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-20 09:41
Test Case | ICPIM-14872 | ICPIM-14871 BMS (electrical and environmental import tests) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-03-19 10:16 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100%
Test Case | ICPIM-14864 | ICPIM-14860 About CPIM Browser Interface - Browser Requirements | All |  | Tien Pham | Jaimes Shonkwiler | PHP, Web Client | Fail | 2013-03-19 08:54 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34553
Test Case | ICPIM-14863 | ICPIM-14860 About Browser Interface - General Licensing | All |  | Tien Pham | Jaimes Shonkwiler | PHP, Web Client | Fail | 2013-03-19 08:51 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34553
Test Case | ICPIM-14861 | ICPIM-14860 About CPIM Browser Interface - Software License Agreement | All |  | Tien Pham | Jaimes Shonkwiler | PHP, Web Client | Pass | 2013-03-19 08:50 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14856 | ICPIM-14416 Pull back property data for Level 11: No Properties Returned | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:28
Test Case | ICPIM-14855 | ICPIM-14416 Pull back property data for Level 10 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:27
Test Case | ICPIM-14854 | ICPIM-14416 Pull back property data for Level 9: null data | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:25
Test Case | ICPIM-14853 | ICPIM-14416 Pull back property data for Level 8 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:24
Test Case | ICPIM-14852 | ICPIM-14416 Pull back property data for Level 7 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:21
Test Case | ICPIM-14851 | ICPIM-14416 Pull back property data for Level 5 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:19
Test Case | ICPIM-14850 | ICPIM-14416 Pull back property data for Level 4 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:16
Test Case | ICPIM-14849 | ICPIM-14416 Pull back property data for Level 3: missing UPS | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:13 | [9 empty] | ICPIM-14795
Test Case | ICPIM-14848 | ICPIM-14416 Pull back property data for Level 2 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-18 16:11
Test Case | ICPIM-14837 | ICPIM-14828 UI Design: Building- Level 4:- TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-03-18 14:20
Test Case | ICPIM-14829 | ICPIM-14828 UI Design: Site- Level 3:- TC | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-03-18 11:25
Test Case | ICPIM-14739 | ICPIM-14714 Portfolio - Advanced Search: by LOB, template, location | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-03-13 16:24 | 3600 | 18000 | 0 | 100% | 3600 | 18000 | 0 | 100% |  | ICPIM-17335, ICPIM-17354, ICPIM-17932, ICPIM-18013, ICPIM-18561, ICPIM-17331, ICPIM-20934, ICPIM-39743, ICPIM-5809, ICPIM-5813, ICPIM-5825, ICPIM-9712, ICPIM-9716, ICPIM-9720, ICPIM-9724, ICPIM-9728, ICPIM-9732, ICPIM-9736, ICPIM-9740, ICPIM-9748, ICPIM-14326
Test Case | ICPIM-14731 | ICPIM-14714 Portfolio - Advanced Search: by Name | All |  | Loan Ha | Loan Ha | Web Client | Fail | 2013-03-13 14:55 | 3600 | 10800 | 0 | 100% | 3600 | 10800 | 0 | 100% |  | ICPIM-14838, ICPIM-15100, ICPIM-15382, ICPIM-17337, ICPIM-17915, ICPIM-18558, ICPIM-17406, ICPIM-27932, ICPIM-5801, ICPIM-5805, ICPIM-5833, ICPIM-9684, ICPIM-9688, ICPIM-9692, ICPIM-9696, ICPIM-9700, ICPIM-13851, ICPIM-14320, ICPIM-5829, ICPIM-9708
Test Case | ICPIM-14673 | ICPIM-14303 VMware Class Additions for Schema | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-03-11 10:02
Test Case | ICPIM-14668 | ICPIM-28722 Install the RF Code DEA | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-03-11 07:55 |  | 4800 | 0 | 100% |  | 4800 | 0 | 100% |  | ICPIM-14669
Test Case | ICPIM-14645 | ICPIM-14642 Accessing Dashboard via (Dictionary, Properties) TC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2013-03-08 12:56 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14644 | ICPIM-14642 Accessing Dashboard via (Trace, Viewer) TC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2013-03-08 08:51 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14643 | ICPIM-14642 Accessing Dashboard via (Navigator, Toolbar, Browser) TC | All |  | Vinh Nguyen | Loan Ha | Windows Client | Pass | 2013-03-08 08:40 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-7835
Test Case | ICPIM-14641 | ICPIM-14633 Manage: Search (Import, Export) | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:16 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-14640 | ICPIM-14633 Manage: Search (Edit, Delete, Copy) | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:15 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100%
Test Case | ICPIM-14639 | ICPIM-14633 Edit: Rename | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:12 |  | 300 | 0 | 100% |  | 300 | 0 | 100%
Test Case | ICPIM-14638 | ICPIM-14633 Edit: Connectivity | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Fail | 2013-03-08 08:12 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-32826
Test Case | ICPIM-14637 | ICPIM-14633 Edit: Power | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:12 |  | 600 | 0 | 100% |  | 600 | 0 | 100%
Test Case | ICPIM-14636 | ICPIM-14633 Edit: Create | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:12 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14635 | ICPIM-14633 Manage: Create | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:12 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14634 | ICPIM-14633 Manage: Search (Class, Manufacturer, Template, Name) | All |  | Vinh Nguyen | Jaimes Shonkwiler | Windows Client | Pass | 2013-03-08 08:11 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-14630 | ICPIM-14623 Row Pad Editor - Commissioning Enclosure Pads- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-07 15:55
Test Case | ICPIM-14629 | ICPIM-14623 Row Pad Editor - Position: TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-07 15:53
Test Case | ICPIM-14628 | ICPIM-14623 Row Pad Editor - Creation: From Library- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-07 15:52
Test Case | ICPIM-14627 | ICPIM-14623 Row Pad Editor - Creation: Build Pads- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-07 15:52 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-14626 | ICPIM-14623 Row Pad Editor - Creation: Clone Pads- TC | All |  | Rachna Muthanna | Rachna Muthanna | Windows Client | Pass | 2013-03-07 15:51 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-14611 | ICPIM-14303 VMware DEA Attribute Mapping | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-03-07 07:51 | [9 empty] | ICPIM-14612
Test Case | ICPIM-14608 | ICPIM-14598 Strip out Cable Routes and Doors (9) TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-06 15:51 | [9 empty] | ICPIM-14562, ICPIM-12085
Test Case | ICPIM-14606 | ICPIM-15839 Portfolio - Trace: Asset level 9 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-06 15:36 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14605 | ICPIM-14594 Portfolio - Chart Level 9: Thermals Gauges | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-06 15:35 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100% |  | ICPIM-35276, ICPIM-35282, ICPIM-35279
Test Case | ICPIM-14604 | ICPIM-14594 Portfolio - Chart Level 9: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-06 15:33 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100%
Test Case | ICPIM-14603 | ICPIM-14594 Portfolio - Chart Level 9: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-06 15:31 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100%
Test Case | ICPIM-14602 | ICPIM-14594 Portfolio - Chart Level 9: Line Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-06 15:27 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100% |  | ICPIM-35267
Test Case | ICPIM-14601 | ICPIM-14594 Portfolio - Chart Level 9: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-06 15:25 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100% |  | ICPIM-35232, ICPIM-35224
Test Case | ICPIM-14599 | ICPIM-14598 No Image Available (9) TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-06 15:25 | [9 empty] | ICPIM-12086
Test Case | ICPIM-14597 | ICPIM-14594 Portfolio - Chart Level 9: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-06 15:24 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100% |  | ICPIM-35156, ICPIM-35232, ICPIM-35224
Test Case | ICPIM-14596 | ICPIM-14594 Portfolio - Chart Level 9: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-06 15:22 |  | 3660 | 0 | 100% |  | 3660 | 0 | 100% |  | ICPIM-35232, ICPIM-35212, ICPIM-35224
Test Case | ICPIM-14595 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 9 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-06 15:21 |  | 2760 | 0 | 100% |  | 2760 | 0 | 100%
Test Case | ICPIM-14591 | ICPIM-14589 No Image Available (5-8) TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-06 14:14 | [9 empty] | ICPIM-12016
Test Case | ICPIM-14590 | ICPIM-14531 Portfolio - Chart Level 8: Gauge Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-06 14:08 |  | 1260 | 0 | 100% |  | 1260 | 0 | 100% |  | ICPIM-34518
Test Case | ICPIM-14588 | ICPIM-14565 Render List Widget W/O Image TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-06 12:25 | [9 empty] | ICPIM-12123
Test Case | ICPIM-14576 | ICPIM-14565 Strip out Cable Routes TC | All |  | Loan Ha | Loan Ha | PHP | New | 2013-03-06 10:56 | [9 empty] | ICPIM-14579, ICPIM-12122
Test Case | ICPIM-14570 | ICPIM-13014 Add Data Source: Intel DCM | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-03-06 09:25 | [9 empty] | ICPIM-14571
Test Case | ICPIM-14569 | ICPIM-13014 Device Auto Mapping | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-03-06 09:03 | [9 empty] | ICPIM-14566
Test Case | ICPIM-14557 | ICPIM-14549 Strip out Cable Routes and Doors TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-03-05 13:36 | [9 empty] | ICPIM-14562, ICPIM-12106
Test Case | ICPIM-14553 | ICPIM-14549 No Image Available (PHP) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-03-05 12:07 | [9 empty] | ICPIM-12107
Test Case | ICPIM-14541 | ICPIM-15839 Portfolio - Trace: Asset level 8 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:26 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14540 | ICPIM-14531 Portfolio - Chart Level 8: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:26 |  | 1260 | 0 | 100% |  | 1260 | 0 | 100%
Test Case | ICPIM-14539 | ICPIM-14531 Portfolio - Chart Level 8: Power Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:26 |  | 960 | 0 | 100% |  | 960 | 0 | 100%
Test Case | ICPIM-14538 | ICPIM-14531 Portfolio - Chart Level 8: Space Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:26 |  | 1260 | 0 | 100% |  | 1260 | 0 | 100%
Test Case | ICPIM-14537 | ICPIM-14531 Portfolio - Chart Level 8: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:26 |  | 1260 | 0 | 100% |  | 1260 | 0 | 100%
Test Case | ICPIM-14536 | ICPIM-14531 Portfolio - Chart Level 8: Line Gauge | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-05 09:25 |  | 2760 | 0 | 100% |  | 2760 | 0 | 100% |  | ICPIM-35267
Test Case | ICPIM-14535 | ICPIM-14531 Portfolio - Chart Level 8: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:25 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14534 | ICPIM-14531 Portfolio - Chart Level 8: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:25 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14533 | ICPIM-14531 Portfolio - Chart Level 8: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:25 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14532 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 8 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-05 09:25 |  | 960 | 0 | 100% |  | 960 | 0 | 100%
Test Case | ICPIM-14526 | ICPIM-14522 Filter/process for "no hotspot" empty image condition TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-03-04 15:30 | [9 empty] | ICPIM-10567
Test Case | ICPIM-14525 | ICPIM-13471 ChangeManagementWS dll to be added | All |  | An Vo | Jaimes Shonkwiler | Windows Client | Invalid | 2013-03-04 14:58 |  | 900 | 0 | 100% |  | 900 | 0 | 100%
Test Case | ICPIM-14520 | ICPIM-14494 String Data Report TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-03-04 12:51 | [9 empty] | ICPIM-13355
Test Case | ICPIM-14512 | ICPIM-15839 Portfolio - Trace: Asset level 7 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14511 | ICPIM-14502 Portfolio - Chart Level 7: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14510 | ICPIM-14502 Portfolio - Chart Level 7: Power Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14509 | ICPIM-14502 Portfolio - Chart Level 7: Space Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14508 | ICPIM-14502 Portfolio - Chart Level 7: Network Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14507 | ICPIM-14502 Portfolio - Chart Level 7: Line Guage | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100% |  | ICPIM-35215
Test Case | ICPIM-14506 | ICPIM-14502 Portfolio - Chart Level 7: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100% |  | ICPIM-35232
Test Case | ICPIM-14505 | ICPIM-14502 Portfolio - Chart Level 7: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100% |  | ICPIM-35232
Test Case | ICPIM-14504 | ICPIM-14502 Portfolio - Chart Level 7: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 60 | 0 | 100% |  | 60 | 0 | 100%
Test Case | ICPIM-14503 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 7 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-04 10:15 |  | 1560 | 0 | 100% |  | 1560 | 0 | 100%
Test Case | ICPIM-14501 | ICPIM-14494 Handle Multiple Params TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-03-04 09:16 | [9 empty] | ICPIM-15103, ICPIM-14514, ICPIM-13353
Test Case | ICPIM-14496 | ICPIM-14494 Add All User Flag TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-03-01 15:58 | [9 empty] | ICPIM-14517, ICPIM-16136, ICPIM-13351
Test Case | ICPIM-14487 | ICPIM-14303 VMware Licensing | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-03-01 14:33
Test Case | ICPIM-14482 | ICPIM-14463 Connectivity (WS) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-03-01 12:43 | [9 empty] | ICPIM-13357, ICPIM-13359, ICPIM-13361, ICPIM-13363, ICPIM-13365
Test Case | ICPIM-14480 | ICPIM-15839 Portfolio - Trace: Asset level 6 | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-03-01 12:06 |  | 60 | 0 | 100% |  | 60 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14479 | ICPIM-14470 Portfolio - Chart Level 6: Line/ Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-34771, ICPIM-35156
Test Case | ICPIM-14478 | ICPIM-14470 Portfolio - Chart Level 6: Network Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-01 12:06 |  | 360 | 0 | 100% |  | 360 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14477 | ICPIM-14470 Portfolio - Chart Level 6: Power Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-34771, ICPIM-35156
Test Case | ICPIM-14476 | ICPIM-14470 Portfolio - Chart Level 6: Space Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14475 | ICPIM-14470 Portfolio - Chart Level 6: Line Gauge | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-01 12:06 |  | 360 | 0 | 100% |  | 360 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14474 | ICPIM-14470 Portfolio - Chart Level 6: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14473 | ICPIM-14470 Portfolio - Chart Level 6: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-35232
Test Case | ICPIM-14472 | ICPIM-14470 Portfolio - Chart Level 6: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-01 12:06 |  | 660 | 0 | 100% |  | 660 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14471 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 6 | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-03-01 12:06 |  | 1560 | 0 | 100% |  | 1560 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14469 | ICPIM-14343 Remove Bypass Bypass backdoor | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Web Service | New | 2013-03-01 11:06
Test Case | ICPIM-14459 | ICPIM-28722 Ensure RF Code DEA is Appropriately Logging Errors |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 1500 | 600 | 71% |  | 1500 | 600 | 71%
Test Case | ICPIM-14456 | ICPIM-28722 Ensure More Than One RF Code Instance Can Be Configured in RF Code DEA |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 1800 | 600 | 75% |  | 1800 | 600 | 75%
Test Case | ICPIM-14454 | ICPIM-28722 Ensure RF Code Asset Manager Attributes are Polled and Populated At Every DEA Instance Start or Reset |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 5700 | 0 | 100% |  | 5700 | 0 | 100%
Test Case | ICPIM-14452 | ICPIM-28722 Ensure a Polling Interval Can be Set and Functions Correctly for RF Code DEA |  |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-03-01 10:16 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100%
Test Case | ICPIM-14451 | ICPIM-28722 Ensure Data Attributes from RF Code can be Manually Mapped to CPIM Datstores | All |  | Thuy Tran | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 11400 | 0 | 100% |  | 11400 | 0 | 100%
Test Case | ICPIM-14449 | ICPIM-14429 Ensure RF Code DEA Utilizes the Entity Name or the $zName (Zone Manager Name) as the Identifier for the Sensor Group (zone) |  |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Invalid | 2013-03-01 10:16
Test Case | ICPIM-14448 | ICPIM-28722 Ensure RF Code DEA Moves Assets To Match Hierarchy in RF Code Source System |  |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-03-01 10:16 |  | 15300 | 0 | 100% |  | 15300 | 0 | 100% |  | ICPIM-26008
Test Case | ICPIM-14447 | ICPIM-28722 Ensure RF Code DEA Can Be Run via Command Line | All |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100%
Test Case | ICPIM-14446 | ICPIM-28722 Ensure RF Code DEA Creates Its Log File in the Appropriate Location |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 1800 | 600 | 75% |  | 1800 | 600 | 75%
Test Case | ICPIM-14445 | ICPIM-28722 Ensure RF Code Supports Standard DEA Commands |  |  | Garrett S. | Jaimes Shonkwiler |  | Pass | 2013-03-01 10:16 |  | 2400 | 300 | 88% |  | 2400 | 300 | 88%
Test Case | ICPIM-14442 | Shall support communication with RF Code Asset Manager | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-03-01 09:19
Test Case | ICPIM-14439 | RF Code Asset Manager Attributes shall be polled at every DEA instance start up or reset | All |  | Garrett S. | Jaimes Shonkwiler | Data Exchange Agent | Pass | 2013-03-01 09:19
Test Case | ICPIM-14417 | ICPIM-14416 Pull back property data for Level 1 | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | PHP | New | 2013-03-01 08:11
Test Case | ICPIM-14411 | ICPIM-15839 Portfolio - Trace: Asset level 5 | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-02-28 15:35 | [9 empty] | ICPIM-34771
Test Case | ICPIM-14410 | ICPIM-14399 Portfolio - Chart Level 5: Line /Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-28 15:32 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14409 | ICPIM-14399 Portfolio - Chart Level 5: Power Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-28 15:30 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14408 | ICPIM-14399 Portfolio - Chart Level 5: Space Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-28 15:28 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14407 | ICPIM-14399 Portfolio - Chart Level 5: Network Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-28 15:26 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14406 | ICPIM-14399 Portfolio - Chart Level 5: Line Gauge | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-28 15:21 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771, ICPIM-35156
Test Case | ICPIM-14405 | ICPIM-14399 Portfolio - Chart Level 5: Network Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-28 15:15 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14404 | ICPIM-14399 Portfolio - Chart Level 5: Power Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-28 15:12 |  | 1200 | 0 | 100% |  | 1200 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14403 | ICPIM-14399 Portfolio - Chart Level 5: Space Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-28 15:10 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14402 | ICPIM-34129 Portfolio - Portfolio view: Asset Level 5 | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-28 15:08 |  | 2160 | 0 | 100% |  | 2160 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14392 | ICPIM-14271 Query/Set Pin TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-28 10:41 | [9 empty] | ICPIM-14314, ICPIM-12944, ICPIM-12961
Test Case | ICPIM-14389 | ICPIM-14271 Query/Set EmailAdress TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-28 10:13 | [9 empty] | ICPIM-14314, ICPIM-12943, ICPIM-12960
Test Case | ICPIM-14381 | ICPIM-14303 VMware Virtual Machine, Cluster, Hypervisor Add, Change | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-28 09:27 | [9 empty] | ICPIM-14393
Test Case | ICPIM-14380 | ICPIM-14303 VMware: Configure DEA and Instance Connectivity Verification | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-28 07:45 | [9 empty] | ICPIM-14550, ICPIM-14554, ICPIM-14558
Test Case | ICPIM-14379 | ICPIM-14271 Query/Set Title TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-27 16:18 | [9 empty] | ICPIM-14314, ICPIM-12942, ICPIM-12959
Test Case | ICPIM-14372 | ICPIM-14271 Query/Set First/Last/Initial TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-27 14:35 | [9 empty] | ICPIM-14314, ICPIM-12941, ICPIM-12958
Test Case | ICPIM-14369 | ICPIM-14336 Portfolio - Chart Level 4: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-02-27 14:21 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34771, ICPIM-35218
Test Case | ICPIM-14368 | ICPIM-14336 Portfolio - Chart Level 4: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-02-27 14:20 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34771, ICPIM-35218
Test Case | ICPIM-14367 | ICPIM-14336 Portfolio - Chart Level 4: PUE Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-02-27 14:18 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34771, ICPIM-35218
Test Case | ICPIM-14366 | ICPIM-14336 Portfolio - Chart Level 4: Pie Charts | All |  | Tien Pham | Rachna Muthanna | Web Client | Blocker | 2013-02-27 14:17 |  | 600 | 0 | 100% |  | 600 | 0 | 100% |  | ICPIM-34771, ICPIM-35218
Test Case | ICPIM-14356 | ICPIM-14343 Authentication (WS) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-27 12:26
Test Case | ICPIM-14338 | ICPIM-14332 Unified Schema Properties TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-27 10:42 | [9 empty] | ICPIM-14396, ICPIM-10651
Test Case | ICPIM-14337 | ICPIM-14303 Set associations between Hypervisors, Virtual Hosts and Applications (WS) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-27 09:55 | [9 empty] | ICPIM-14376
Test Case | ICPIM-14335 | ICPIM-14303 Create Hypervisors, Virtual Hosts and Applications (WS) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-27 09:20 | [9 empty] | ICPIM-14357, ICPIM-14360
Test Case | ICPIM-14334 | ICPIM-14332 Add Level Name/Id TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-27 08:38 | [9 empty] | ICPIM-14413, ICPIM-11224
Test Case | ICPIM-14333 | ICPIM-14303 Delete Hypervisors, Virtual Hosts and Applications (WS) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-27 08:35
Test Case | ICPIM-14331 | ICPIM-14303 Query for Hypervisors, Virtual Hosts and Applications (WS) | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-27 08:20 | [9 empty] | ICPIM-14373
Test Case | ICPIM-14328 | ICPIM-14303 Logging for all creation, update and removal operations | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-26 15:55
Test Case | ICPIM-14319 | ICPIM-14271 Teams_Assigned TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-26 14:47 | [9 empty] | ICPIM-13997
Test Case | ICPIM-14318 | ICPIM-14271 Query (All Teams) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-26 14:37 | [9 empty] | ICPIM-13999
Test Case | ICPIM-14308 | ICPIM-14135 Portfolio - Chart Level 3: Line/ Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-26 09:21 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14307 | ICPIM-14135 Portfolio - Chart Level 3: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-26 09:20 |  | 3000 | 0 | 100% |  | 3000 | 0 | 100% |  | ICPIM-34771, ICPIM-35221
Test Case | ICPIM-14306 | ICPIM-14135 Portfolio - Chart Level 3: PUE Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-26 09:19 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14305 | ICPIM-14135 Portfolio - Chart Level 3: Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-26 09:15 |  | 2700 | 0 | 100% |  | 2700 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14304 | ICPIM-14303 VMware Installer | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-02-26 08:00
Test Case | ICPIM-14272 | ICPIM-14271 Query/Set Password TC | All |  | Garrett S. | Loan Ha | Web Service | New | 2013-02-25 15:14 | [9 empty] | ICPIM-14314, ICPIM-15835, ICPIM-12945, ICPIM-12962
Test Case | ICPIM-14249 | ICPIM-14248 Security Config (WS) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-25 14:39 | [9 empty] | ICPIM-3698
Test Case | ICPIM-14241 | ICPIM-14127 Mapview Cache (WS) TC | All |  | Loan Ha | Loan Ha | Web Service | New | 2013-02-25 11:13 | [9 empty] | ICPIM-15799, ICPIM-10007, ICPIM-10047, ICPIM-10051, ICPIM-10055, ICPIM-10059, ICPIM-10063, ICPIM-10067, ICPIM-10083, ICPIM-10087, ICPIM-13318, ICPIM-13766, ICPIM-13904
Test Case | ICPIM-14118 | ICPIM-14094 Advanced Search (Locations) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-22 08:20 | [9 empty] | ICPIM-6921
Test Case | ICPIM-14117 | ICPIM-14094 Advanced Search (LOB) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-22 08:18 | [9 empty] | ICPIM-6925
Test Case | ICPIM-14099 | ICPIM-39398 Portfolio - List View: Loads up conditions | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 14:01 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100% |  | ICPIM-34771, ICPIM-35218
Test Case | ICPIM-14098 | ICPIM-14090 Portfolio - Chart Level 2: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 13:57 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14097 | ICPIM-14090 Portfolio - Chart Level 2: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-21 13:43 |  | 2400 | 0 | 100% |  | 2400 | 0 | 100% |  | ICPIM-34771, ICPIM-35221
Test Case | ICPIM-14096 | ICPIM-14094 Advanced Search (Equip Templates) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-21 13:33 | [9 empty] | ICPIM-6937
Test Case | ICPIM-14092 | ICPIM-14090 Portfolio - Chart Level 2: PUE Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-21 11:06 |  | 2100 | 0 | 100% |  | 2100 | 0 | 100% |  | ICPIM-34771, ICPIM-35232
Test Case | ICPIM-14091 | ICPIM-14090 Portfolio - Chart Level 2: Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-21 11:02 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-35232, ICPIM-35209
Test Case | ICPIM-14085 | ICPIM-39398 Portfolio - List View: Functionalities | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 09:49 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100% |  | ICPIM-34771, ICPIM-17346, ICPIM-17350, ICPIM-15660, ICPIM-15662, ICPIM-15664, ICPIM-15666, ICPIM-17348, ICPIM-15671
Test Case | ICPIM-14084 | ICPIM-14082 Map View (PHP) TC | All |  | Garrett S. | Loan Ha | PHP | New | 2013-02-21 09:39 | [9 empty] | ICPIM-15061, ICPIM-13220
Test Case | ICPIM-14083 | ICPIM-14053 Portfolio - Charts Level 1: Line/Area Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 09:33 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-34771
Test Case | ICPIM-14081 | ICPIM-14053 Portfolio - Charts Level 1: Bar Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 09:21 |  | 2100 | 0 | 100% |  | 2100 | 0 | 100%
Test Case | ICPIM-14080 | ICPIM-14053 Portfolio - Charts Level 1: PUE Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-21 09:17 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100%
Test Case | ICPIM-14079 | ICPIM-14053 Portfolio - Charts Level 1: Pie Chart | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-02-21 09:09 |  | 1500 | 0 | 100% |  | 1500 | 0 | 100% |  | ICPIM-35232, ICPIM-35209
Test Case | ICPIM-14071 | ICPIM-14058 Incorrect Site | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:26
Test Case | ICPIM-14070 | ICPIM-14058 Filter | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:23
Test Case | ICPIM-14069 | ICPIM-14058 Fulfillment | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:22
Test Case | ICPIM-14068 | ICPIM-14058 Remove\Delete Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:21
Test Case | ICPIM-14067 | ICPIM-14058 Multi-Select Clear Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:20
Test Case | ICPIM-14066 | ICPIM-14058 Clear Planned Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:20
Test Case | ICPIM-14065 | ICPIM-14058 Manually Create IA Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:19
Test Case | ICPIM-14064 | ICPIM-14058 Partial Fill | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:18
Test Case | ICPIM-14062 | ICPIM-14058 Space conflict Cabinet | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:12
Test Case | ICPIM-14061 | ICPIM-14058 Space conflict Loose Gear | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:10
Test Case | ICPIM-14060 | ICPIM-14058 Cabinet Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:07
Test Case | ICPIM-14059 | ICPIM-14058 Loose Gear Reservation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler |  | Invalid | 2013-02-20 17:04
Test Case | ICPIM-14039 | ICPIM-13904 Viewing Mapview Cache Settings TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-02-20 09:23 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-11235
Test Case | ICPIM-14035 | ICPIM-13904 Adding/Editing Mapview Cache Setting TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Fail | 2013-02-19 16:24 |  | 10800 | 0 | 100% |  | 10800 | 0 | 100% |  | ICPIM-14041, ICPIM-14044, ICPIM-33865, ICPIM-33888, ICPIM-7177, ICPIM-7181, ICPIM-10011
Test Case | ICPIM-14031 | ICPIM-13904 Sorting Class Mapview Cache settings TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-02-19 15:51 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100% |  | ICPIM-7165, ICPIM-7169, ICPIM-7173, ICPIM-13944
Test Case | ICPIM-13995 | ICPIM-13904 Configure Mapview Cache Settings TC | All |  | Mai Nguyen | Loan Ha | Windows Client | Pass | 2013-02-18 13:12 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-15154, ICPIM-14025, ICPIM-7149, ICPIM-7153, ICPIM-7157, ICPIM-7161, ICPIM-10031, ICPIM-13944
Test Case | ICPIM-13913 | ICPIM-13471 Modify Installation | All |  | Mai Nguyen | Jaimes Shonkwiler | Windows Client | Fail | 2013-02-14 16:56 |  | 14400 | 0 | 100% |  | 14400 | 0 | 100% |  | ICPIM-20651, ICPIM-26891, ICPIM-33894, ICPIM-34072, ICPIM-35061
Test Case | ICPIM-13906 | ICPIM-13471 Upgrade Installation | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Windows Client | Invalid | 2013-02-14 14:03 | [9 empty] | ICPIM-16983, ICPIM-17069, ICPIM-13907
Test Case | ICPIM-13905 | ICPIM-13708 Switch Connectivity (By Location) Report TC | All |  | Loan Ha | Loan Ha | Windows Client | Fail | 2013-02-14 13:17 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-11779, ICPIM-11780, ICPIM-33882
Test Case | ICPIM-13707 | ICPIM-13083 Platforms Drop Down Menu TC | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2013-02-08 13:42 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-13751, ICPIM-13756, ICPIM-21323, ICPIM-8348
Test Case | ICPIM-13684 | ICPIM-13708 Switch Connectivity (Entire Database) Report TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-02-07 09:56 |  | 9000 | 0 | 100% |  | 9000 | 0 | 100% |  | ICPIM-11778
Test Case | ICPIM-13681 | ICPIM-34123 Portfolio - Quick Search: Results list | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-02-06 17:44 | 2400 |  | 2400 | 0% | 2400 |  | 2400 | 0% |  | ICPIM-17364, ICPIM-20739, ICPIM-20740, ICPIM-17366, ICPIM-3138, ICPIM-3142, ICPIM-3146, ICPIM-3150, ICPIM-3154, ICPIM-6389, ICPIM-6393, ICPIM-10743, ICPIM-14324, ICPIM-12827, ICPIM-12831, ICPIM-12833, ICPIM-12835, ICPIM-12837, ICPIM-12839, ICPIM-12841, ICPIM-12843, ICPIM-12845, ICPIM-12849, ICPIM-12851, ICPIM-12853, ICPIM-12855, ICPIM-12857, ICPIM-12859
Test Case | ICPIM-13609 | ICPIM-13034 Map View Timestamp Display TC | All |  | Loan Ha | Loan Ha | Windows Client | Pass | 2013-02-04 13:12 |  | 7200 | 0 | 100% |  | 7200 | 0 | 100% |  | ICPIM-11131, ICPIM-11133, ICPIM-11135, ICPIM-11137
Test Case | ICPIM-13597 | ICPIM-13230 Portfolio - Line Chart: Graph lines | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:53 | 2700 | 2100 | 600 | 77% | 2700 | 2100 | 600 | 77%
Test Case | ICPIM-13596 | ICPIM-13230 Portfolio - Line Chart: Time scroll bar | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:52 | 2700 | 2100 | 600 | 77% | 2700 | 2100 | 600 | 77%
Test Case | ICPIM-13595 | ICPIM-13230 Portfolio - Line Chart: Download as CSV | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:48 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-13594 | ICPIM-13230 Portfolio - Line Chart: Send email | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:45 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-13593 | ICPIM-13230 Portfolio - Line Chart: Download as PNG | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:44 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-13592 | ICPIM-13230 Portfolio - Line Chart: Maximize mode | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:41 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75%
Test Case | ICPIM-13591 | ICPIM-13230 Portfolio - Line Chart: Legend | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-02-01 14:39 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-13473 | ICPIM-13471 Complete Installation | All |  | Tien Pham | Jaimes Shonkwiler | Windows Client | Fail | 2013-01-29 15:27 |  | 16200 | 0 | 100% |  | 16200 | 0 | 100% |  | ICPIM-33894
Test Case | ICPIM-13440 | ICPIM-13014 Manage Data Exchange Agents Button Dialog | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-01-29 13:09
Test Case | ICPIM-13420 | ICPIM-11221 Auto-Mapping | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-01-29 10:01 | [9 empty] | ICPIM-13441
Test Case | ICPIM-13348 | ICPIM-11221 Agent Data Source: Map Source | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-01-28 13:55
Test Case | ICPIM-13347 | ICPIM-11221 Configure Agent Attributes For Polling | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-01-28 13:53
Test Case | ICPIM-13231 | ICPIM-13230 Portfolio - Line Chart: Download as PDF | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-01-24 08:21 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66% |  | ICPIM-13323, ICPIM-13329, ICPIM-13332, ICPIM-13335, ICPIM-13450, ICPIM-13326
Test Case | ICPIM-13178 | ICPIM-11221 Configuration and Connectivity to HP Insight Manager | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-01-22 16:20
Test Case | ICPIM-13165 | ICPIM-13163 Portfolio - Gauge Chart: Maximize mode not available | All |  | Tien Pham | Rachna Muthanna | Web Client | Fail | 2013-01-21 15:13 | 900 | 600 | 300 | 66% | 900 | 600 | 300 | 66%
Test Case | ICPIM-13164 | ICPIM-13083 Security Config TC | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2013-01-21 13:28 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-13175, ICPIM-21308
Test Case | ICPIM-13044 | ICPIM-13034 Map View (Dashboard) Displays/Feature is Present TC | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2013-01-18 09:13 |  | 900 | 0 | 100% |  | 900 | 0 | 100% |  | ICPIM-13341, ICPIM-13910, ICPIM-11129
Test Case | ICPIM-13033 | ICPIM-40305 Web UI - Direct URL: URL Navigation | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-17 18:10 |  | 2100 | 0 | 100% |  | 2100 | 0 | 100% |  | ICPIM-8778
Test Case | ICPIM-13032 | ICPIM-11167 Favorites - Manage Favorites: Deleting Favorites | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-17 17:52 | 1200 | 1200 | 0 | 100% | 1200 | 1200 | 0 | 100% |  | ICPIM-17906, ICPIM-13712
Test Case | ICPIM-13031 | ICPIM-12703 Authentication UI | All |  | Melissa C. | Melissa C. | Web Client | Pass | 2013-01-17 17:23 | 900 |  | 900 | 0% | 900 |  | 900 | 0% |  | ICPIM-17572, ICPIM-17576, ICPIM-17574, ICPIM-9165
Test Case | ICPIM-13030 | ICPIM-12703 Logging in and Out | All |  | Melissa C. | Melissa C. | Web Client | Pass | 2013-01-17 17:09 | 1200 |  | 1200 | 0% | 1200 |  | 1200 | 0% |  | ICPIM-8755, ICPIM-8758, ICPIM-10830, ICPIM-14886, ICPIM-17579
Test Case | ICPIM-13029 | ICPIM-13028 Opsdb Quick Sync Verification | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Service | New | 2013-01-17 15:48 | [9 empty] | ICPIM-11202
Test Case | ICPIM-13026 | ICPIM-13021 Roots (Setting roots) TC | All |  | Trinh Nguyen | Loan Ha | Windows Client | Pass | 2013-01-17 13:50 | 3600 | 3600 | 0 | 100% | 3600 | 3600 | 0 | 100%
Test Case | ICPIM-13023 | ICPIM-13004 Portfolio - Bar Char: Legend | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-01-17 13:18 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-15284, ICPIM-15352, ICPIM-13338, ICPIM-13453, ICPIM-15366, ICPIM-15816
Test Case | ICPIM-13015 | ICPIM-13014 Configure Data Source to Data Exchange Agent | All |  | Jaimes Shonkwiler | Jaimes Shonkwiler | Data Exchange Agent | New | 2013-01-17 10:55 | [9 empty] | ICPIM-13010
Test Case | ICPIM-13011 | ICPIM-13004 Portfolio - Bar Char: Download as PNG | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-01-17 10:14 | 1800 | 1200 | 600 | 66% | 1800 | 1200 | 600 | 66%
Test Case | ICPIM-13006 | ICPIM-13004 Portfolio - Bar Char: Maximize/ Minimize | All |  | Tien Pham | Rachna Muthanna | Web Client | Pass | 2013-01-17 09:48 |  | 1800 | 0 | 100% |  | 1800 | 0 | 100%
Test Case | ICPIM-13005 | ICPIM-11221 Install HP Insight Manager (via installer) | All |  | Garrett S. | Jaimes Shonkwiler | Business Logic | Invalid | 2013-01-17 09:48 | [9 empty] | ICPIM-13007
Test Case | ICPIM-12998 | ICPIM-12697 Saving/Sending Reports | All |  | Loan Ha | Melissa C. | Web Client | Pass | 2013-01-16 16:34 |  | 3600 | 0 | 100% |  | 3600 | 0 | 100% |  | ICPIM-17649, ICPIM-17677
Test Case | ICPIM-12706 | ICPIM-12704 Portfolio - Advanced Navigation: Advanced navigation UI | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-16 15:20 | 1500 | 1500 | 0 | 100% | 1500 | 1500 | 0 | 100% |  | ICPIM-10767, ICPIM-15957
Test Case | ICPIM-12705 | ICPIM-12704 Portfolio - Advanced Navigation: Portfolio, Search, Report buttons | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-16 15:07 | 1200 | 900 | 300 | 75% | 1200 | 900 | 300 | 75% |  | ICPIM-17362, ICPIM-13000
Test Case | ICPIM-12698 | ICPIM-12703 Login/ logout | All |  | Rachna Muthanna | Rachna Muthanna | Web Client | Pass | 2013-01-16 14:19 | 3600 |  | 3600 | 0% | 3600 |  | 3600 | 0% |  | ICPIM-13536, ICPIM-14830, ICPIM-15157, ICPIM-15749, ICPIM-14047, ICPIM-14773, ICPIM-14780, ICPIM-15200, ICPIM-16028, ICPIM-15170, ICPIM-15172
Test Case | ICPIM-11170 | ICPIM-11167 Favorites - Manage Favorites: UI | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-09 18:39 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80%
Test Case | ICPIM-11169 | ICPIM-11167 Favorites - Manage Favorites: Viewing Favorites | All |  | Tien Pham | Melissa C. | Web Client | Pass | 2013-01-09 18:00 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-15953, ICPIM-14650, ICPIM-20707, ICPIM-22079
Test Case | ICPIM-11168 | ICPIM-11167 Favorites - Manage Favorites: Editing Favorites | All |  | Tien Pham | Melissa C. | Web Client | Fail | 2013-01-09 17:57 | 1500 | 1200 | 300 | 80% | 1500 | 1200 | 300 | 80% |  | ICPIM-11781, ICPIM-14656, ICPIM-14659, ICPIM-17900, ICPIM-20710, ICPIM-20719, ICPIM-20725, ICPIM-14662, ICPIM-20707, ICPIM-20728, ICPIM-22082
Test Case | ICPIM-10985 | ICPIM-14522 When queried via PHP, there is a standardized API return for Viz | All |  | Garrett S. | Jaimes Shonkwiler | Web Service | New | 2013-01-08 07:54 | [9 empty] | ICPIM-10655
Generated at Thu Jul 23 00:37:11 MST 2015 by Duy Vu using JIRA 5.1.5#784-sha1:6c729937863f5b4cf7f0dd89a7db4e505415af41.

## TYR - Schedule & RS Allocation (hidden)
| Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
 | time axis 2015-05-19 to 2015-10-16
Schedule | bar: 2015-05-19 to 2015-05-22; 2015-05-25 to 2015-05-29; 2015-06-01 to 2015-06-05; 2015-06-08 to 2015-06-12; 2015-06-15 to 2015-06-19; 2015-06-22 to 2015-06-26; 2015-06-29 to 2015-07-03; 2015-07-06 to 2015-07-10; 2015-07-13 to 2015-07-17; 2015-07-20 to 2015-07-24; 2015-07-27 to 2015-07-31; 2015-08-03 to 2015-08-07; 2015-08-10 to 2015-08-14; 2015-08-17 to 2015-08-21; 2015-08-24 to 2015-08-28; 2015-08-31 to 2015-09-01; 2015-09-03 to 2015-09-04; 2015-09-07 to 2015-09-11; 2015-09-14 to 2015-09-18; 2015-09-21 to 2015-09-25; 2015-09-28 to 2015-10-02; 2015-10-05 to 2015-10-09; 2015-10-12 to 2015-10-16
Phase 1 | bar: 2015-05-19 to 2015-05-22; 2015-05-25 to 2015-05-29; 2015-06-01 to 2015-06-05; 2015-06-08 to 2015-06-12; 2015-06-15 to 2015-06-19; 2015-06-22 to 2015-06-26; 2015-06-29 to 2015-07-03; 2015-07-06 to 2015-07-10; 2015-07-13 to 2015-07-17; 2015-07-20 to 2015-07-24; 2015-07-27 to 2015-07-30
Phase 2 | bar: 2015-07-31; 2015-08-03 to 2015-08-07; 2015-08-10 to 2015-08-14; 2015-08-17 to 2015-08-21; 2015-08-24 to 2015-08-28; 2015-08-31 to 2015-09-01; 2015-09-03 to 2015-09-04; 2015-09-07 to 2015-09-11; 2015-09-14 to 2015-09-18; 2015-09-21 to 2015-09-25; 2015-09-28 to 2015-10-02; 2015-10-05 to 2015-10-09; 2015-10-12 to 2015-10-16
Component Areas | 2015-05-19: Pre-Activities; 2015-05-30: Execution
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22
Windows Client | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Web Client | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2
DEA/ Web Service | 2 | 2 | 2 | 2 | 2.5 | 2.5 | 2 | 2 | 2 | 2.5 | 2.5 | 2 | 2 | 2 | 2 | 2 | 2.5 | 2.5 | 2 | 2 | 2 | 2.5